## Sheet1
Project Knowledge Areas (PMI/PMBOK) | SPV | Project Manager | PMO Support | Compliance Manager | Performance Manager | Contract Manager
Direct and Manage Work | I | A+R | I | I | I | I
Manage Project Knowlegde | I | A+R | C | C | C | C
Monitor and Control Work | I | A+R | C | C | C | C
Change Control | I | A+R | C | C | C | C
Stakeholder Management | C | A+R | I | R | I | I
Resource Management | I | A+R | C | C | C | C
Risk Management | I | A | R | C | C | C
Schedule Management | I | A | R | C | C | C
Communications Management | I | A | R | C | C | C
Scope Management | I | A | I | C | C | R
Finance Management | I | A | I | C | C | R
Resource Management | I | A | I | C | C | R
Procurement Management | I | A | I | C | C | R
HSE Management | I | A | I | R | C | C
Quality Management | I | A | I | R | C | C
Interface Management | I | A | I | C | R | C
Design Management | I | A | I | C | R | C
Testing and Commissioning | I | A | I | C | R | C