Request For Proposal for

Environmental & Social Impact Assessment

Sorouh Energy

1st November 2022

| Rev. | Purpose of Issue | Date | Originator | Approved |
| --- | --- | --- | --- | --- |
| 1.00 | Request to Bidders Jenin | 1st Dec 2021 | Mr. Rijswijk | Mr. Ayyad |
| 2.00 | Request to Bidders Jenin | 23rd Dec 2021 | Mr. Rijswijk | Mr. Ayyad |
| 3.00 | Internal version Sorouh Energy | N.A. | N.A. | N.A. |
| 4.00 | Request to Bidders Jenin | 1st Nov 2022 | Mr. Rijswijk | Mr. Ayyad |

Table of Contents

1	Definitions	3

2	Project Background	4

3	RFP Outline	5

3.1	Objective	5

3.2	Award criteria	6

4	Data sheet	7

5	Terms of Reference (TOR)	8

5.1	Scope of Work (SOW)	8

5.2	Reference Framework	9

5.3	Deliverables & Milestones	10

5.4	Project Management	12

6	Proposal requirements	13

6.1	Minimum Administrative Requirements	13

6.2	Technical Proposal	13

6.3	Financial Proposal	14

Annexure I – Data sheet	15

Annexure II – Minimum Administrative Requirements	16

Annexure III – Terms and Conditions	17

Annexure IV – Example index and content of the ESIA report	18

Annexure V – Project reporting template	22

# Definitions

| Abbreviation or Term | Definition |
| --- | --- |
| ADB SPS | Asian Development Bank – Safeguard Policy Statement |
| AOI | Area of Interest |
| Bidder | A business entity or consortium that submits its Proposal according and in response to this RFP |
| Consultant | The Bidder selected by SPV, bound by a signed contract |
| EBRD | European Bank for Reconstruction and Development |
| E&S | Environmental and Social |
| ESIA | Environmental and Social Impact Assessment |
| ESAP | Environmental and Social Action Plan |
| ESMP | Environmental and Social Management Plan |
| EPA | Environmental Protection Agency |
| FIDIC | International Federation of Consulting Engineers |
| GHG | Greenhouse gas |
| IFC PS | International Finance Corporation – Performance Standard |
| NGO | Non-governmental Organization |
| Price | Total cost of the Proposal, containing all related costs for all the work required |
| Proposal | The offer made by the Bidder according to this RFP, for consideration or acceptance by SPV |
| RFP | Request for Proposal |
| SPV | Special Purpose Vehicle “Sorouh Energy” |
| WtE | Waste-to-Energy |

# Project Background

The company Sorouh Energy – formerly known as ‘the Northern Consortium’ – consisting of strong and knowledgeable partners in the field of Waste-to-Energy (WtE) plants, has the ambition to develop and construct a world-class “beyond Best Available Technology” facility in Jenin, with a capacity of processing around 1,200 tons of waste per day (the Project). The proposed plant will produce around net 35-40 MW (~310 GWh) of electricity to be sold to the grid, depending on the caloric value of the waste.

In March 2021, the Northern Consortium (now called Sorouh Energy) finished first in the Palestinian Authority Ministry of Local Government international tender Project No. MOLG2020-1/20. The project was awarded subject to conditions in Q3 2021 (award letter can be provided on request). The SPV currently negotiating the project contracts for the waste concession and power purchase agreement (PPA). As soon as these are completed, the feasibility studies will start.

Sorouh Energy is specifically set up to pursue opportunities in Palestine to develop WtE plants with Harvest Waste’s High Efficiency WtE technology based on and similar to the AEB WtE plant in Amsterdam, The Netherlands. This reference plant uses the world’s most efficient technology for generating electricity from waste and it will treat the current and future municipal solid waste of Jenin. WtE technology minimizes land requirements and produces baseload clean energy. In addition to that, the remaining slag from the incineration process can be recycled to further reduce landfills and provide valuable inert materials and metals for the construction industry.

An Environmental and Social Impact Assessment (ESIA) is a mandatory legal requirement in Palestine as well as for project funders: development banks, commercial banks, and possible other investors to the project.

Sorouh Energy is committed to address all the requirements set by Palestine laws as well as international environmental and social standards and involve all stakeholders potentially affected by the project regarding environmental and social issues. Therefore, Sorouh Energy (hereafter “SPV”) is requesting Proposals from accredited consulting firms in performing an ESIA following internationally acceptable standards.

For any further information please contact

Name:		Mr. L. Rijswijk

Email:		l.rijswijk@harvestwaste.com

Tel:		+31650224330

# RFP Outline

## Objective

The objective of the Sorouh Energy is to provide a state-of-the-art High Efficiency Waste-to-Energy disposal facility for residual municipal solid waste located in the north of the West Bank. The facility will treat the waste using the proven HE WtE technology turning it into baseload power which can be consumed by the local authorities reducing reliability on foreign produced power and diverting waste from landfills in the West Bank which are at full capacity. Emissions from the WtE facility to be developed will follow the current strict European Emission standards setting a benchmark for WtE outside Europe.

The ESIA aims to inform project funders, decision-makers, the public and any other stakeholders of the environmental and social consequences of implementing the WtE plant, including its ancillary facilities and any residues still requiring landfilling. This ESIA aims to identify, predict, analyse, and quantify the environmental and social impacts in the project area of influence during the various stages from pre-construction, throughout construction and during operation.

It also identifies alternatives and mitigation measures to reduce the environmental effect of the WtE plant through environmental and social mitigation/management plans. Finally, the ESIA serves as an important role in obtaining permits and licenses for Construction and Operational phase.

For the ESIA, the requirements are defined in paragraph Terms of Reference (TOR)

## Award criteria

| Section | Criterium | Max. points |
| --- | --- | --- |
| 1 – Minimum administrative requirements | Pass – Fail All requirements must be met by the Bidder. If one item will not be met, the Proposal will not be evaluated. | N/A |
| 2 – Technical Proposal | Project Approach Bidder to provide a description of its company and project approach, including a project schedule with a visible critical path. Milestones, stipulated in the previous paragraph, must be included in the schedule. If the Bidder decides to participate as a consortium, the split of scope must be made known. The project approach will be assessed in conjunction with the planning. | 25 |
|  | Project references Bidder to provide references. The better these references match with the TOR of this RFP, the higher this item will be valued. | 25 |
|  | Project team Bidders’ proposed project team and CV’s will be evaluated on applicable references | 25 |
| 3 – Financial Proposal | Price level The lump sum price in USD. The award of points is made relative to the lowest price. Best bidder gets 25 points. The % deviation from the lowest price is also the % that is deducted from 25 points. Calculation example below | 25 |

Calculation example award of points for financial proposal

Bidder 1 		– 	USD 100,000  –  lowest bidder = reference for calculation	-	25 points

Bidder 2 		– 	USD 120,000  –  20% higher than lowest bid			-	20 points

Bidder 3 		– 	USD 150,000  –  50% higher than lowest bid			-	12,5 points

# Data sheet

Sorouh Energy will provide the following project information as a part of this RFP, as input for the Bidders’ Proposal:

- Feasibility Study Waste-to-Energy options on the West Bank, November 18th, 2018. This study - part of the RFP documents - considered alternative waste treatment options.

- SPV’s bid proposal for Jenin, including (amongst others):

All information provided will be verified and validated during feasibility phase. The assumptions, assessments, statements, and information contained in this Data sheet, may not be complete. This information may only be used to develop a Proposal.

Sorouh Energy will provide the following project information within the Feasibility Phase of the project.

| Indicative Moment (months) | Start of EISA: t = 0 |
| --- | --- |
| t = 1m | (Preliminary) results of the permit analysis |
| t = 3m | Emissions to be generated by plant, based on the technology and first waste composition results. To be used for stack emissions and dispersion model |
| t = 5m | Resource’s requirements and sources (e.g. drinking water) during the different phases |
| Other information needed, will need to be agreed between SPV and Consultant in the first month after assignment. |  |

For study results and reporting, each Bidder should, therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments, statements, and information contained in this Data Sheet and obtain independent advice from appropriate sources.

This Data sheet information set is provided in Annexure I.

# Terms of Reference (TOR)

This TOR is the basis for the request for proposal, consultancy agreement and the final ESIA. The TOR consists of three parts:

- Scope of Work provides a non-exhaustive list of activities to be performed by the Consultant.

- Reference Framework provides criteria, standards, and guidelines against which the Consultant must assess the project.

- Deliverables & Milestones specifies the minimum requirements that reports and results must comply with.

- Project Management prescribes what SPV expects from Consultant with regard to basic project management areas like progress reporting, planning, variations, etc.

## Scope of Work (SOW)

In general, the ESIA follows the steps provided in this paragraph.

Stakeholder Engagement will be executed during all phases. A stakeholder engagement plan must be developed in the first phase.

- Scoping and Baseline; ensure that there is a wide consensus on the eventual shape and emphasis of the impact assessment, provides guidance during the rest of the assessment process and partly represents the results of the stakeholder consultations at this stage. An inventory of available baseline data is conducted, and missing data identified. Activities during the scoping phase:

  - Kick off meeting

  - Site Reconnaissance

  - Develop a preliminary project description.

  - Develop a preliminary environmental, ecological, and social baseline

  - Develop preliminary anticipated environmental impacts and mitigation measures

- ESIA phase

  - Impact Assessment and Mitigation: evaluate the socioeconomic and environmental impacts of the planned project and its alternatives, and then identify the mitigation measures to reduce those impacts.

  - Impact Management: prepare the plans required for addressing mitigation measures and other project risks, such as technological failures and natural disasters.

- Reporting: Pull together all the research and work done during the previous steps into a comprehensive, structured document, ensuring that the ESIA report contains all the key components.

- Review and Licensing: Designated authorities review the ESIA report to determine if the planned project will get a license or if it requires amendment.

## Reference Framework

| No | Reference |
| --- | --- |
| 1 | International standards & guidelines - IFC Performance Standards on Environmental & Social Sustainability 1-8 and related guidance notes for each Performance Standard. - EBRD’s Environmental and Social Policy 2019 and its incorporated Environmental and Social Performance Requirements (PRs) - EU ESIA Directive (as updated) - World Bank Group EHS - Sector specific guidelines for Waste Management Facilities, - World Bank Group EHS - Sector specific guidelines for Electrical Power Transmission and Distribution Other applicable international environmental and social legislation to be determined by Bidder. |
| 2 | Technical Standards - EU directive EU2010/75 updated BREF 2019, following ALARA principle - EU Waste Framework Directive, EU Landfill Directive, EU Industrial Emissions Directive, EU Groundwater Directive - Quality Assurance Management Plan QAMP guidelines: ANSI, ASME ISO-9712 - Engineering standards according to DIN-EN |
| 3 | National Policies, Strategies, Laws and Legislations - Local Authorities Law No.1 (1997), - National Strategy for Solid Waste Management (NSSWM) 2017-2022 - Environment Law No.7 (1999) amended in 2013, Public Health Law No.20 (2004), modified Palestinian Basic Law 2005 Article (33), - Joint Services Councils (JSCs) Bylaw approved by cabinet (2016), - Solid Waste Management cabinet decision No. 3 (2019) Other applicable national environmental and social law & legislation to be determined by Bidder. |
| 5 | All ILO conventions signed and ratified by Palestine Authorities/Occupied Territories, all ILO conventions covering core labor standards and all ILO conventions covering the basic terms and conditions of employment; |
| 6 | Certifications as applicable ISO14001, ISO450001 and SA8000 |

## Deliverables & Milestones

| Activity | Deliverable / result | Minimum Requirement | Milestone |
| --- | --- | --- | --- |
| Kick off meeting | Workshop | Introduce key personnel from Sorouh Energy and Bidder Introduce Consultants’ the project approach: - organisation, roles & responsibilities - project schedule & milestones - communication - involved stakeholders - proposed deliverables - indicate required initial data | M1 t = 0 |
| Scoping and Baseline | Intermediate report The report shall provide sufficient insights and confidence for Sorouh Energy and its key stakeholders to proceed or not with the ESIA phase of the project | Memo: Main preliminary observations and identified red flags and/or potential major issues. Attached to the memo: Scoping report - The project and its components. - The preliminary key potential environmental, social, health and safety risks and impacts. - Preliminary mitigation measures embedded in the project design to manage project risks. Stakeholder Engagement Plan - Shortlist of all stakeholders - Methods for stakeholder engagement - Planning for stakeholder engagement - Results of initial consultation with key stakeholders | M2 t + 12 weeks |

| Activity | Deliverable / result | Minimum Requirement | Milestone |
| --- | --- | --- | --- |
| ESIA phase & Reporting | Draft report | According to Reference Framework and Consultants’ experience | M3 t + 24 weeks |
| Review SPV | Review report | Review of draft report by Sorouh Energy and relevant authorities | t + 28 weeks |
| Final report | Final report | According to Reference Framework and Consultants’ experience | M4 t + 32 weeks |

## Project Management

### Project reporting

In general, project baselines define starting points for

- project scope (according to this RFP)

- project schedule (based on the RFP milestones)

- project cost (financial proposal)

These baselines are fixed reference points to measure and compare the project’s progress against. This allows SPV to assess the performance of the project over time. Any proposed changes to a baseline document, will be subject to variations management.

The SPV will hold weekly update meetings with Consultant. This will be done online or live, subject to availability.

As a minimum, a formal monthly progress report is requested for:

- Project progress, Summary of last developments and next steps, in brief wording

- Project schedule: schedule baseline vs actual and a forecast

- Project risks Log: top 3-5 risks, including suggested mitigations and impact value

- Project variations Log: variation requests status impacting budget & schedule

The project reporting template is provided in Annexure V.

### Project Scheduling

The project schedule must serve to:

- represent how and when the project will deliver the project scope

- serve as a tool for communication and managing stakeholders’ expectations

- serve as a basis for performance reporting

The Consultants’ project schedule must be made available in editable format, preferably in Microsoft Projects, Excel or comparable.

### Variations management

The Consultant may request a change. Issues, found while the project work is performed, could lead to a ‘variation, and may modify any deliverable of project baseline and requires a variations request, to be made by the initiator.

Only approved variations may be executed and, after approval, will be incorporated into a revised baseline. Inspections can be used to verify whether a variation request has been followed up according to the approval.

# Proposal requirements

The language of the proposal must be in English. All deliverables required from the Bidder shall be submitted in electronic form, consisting of the following sections.

## Minimum Administrative Requirements

Proposals which comply with minimum requirements and criteria will be the subject to evaluation. Minimum administrative requirements will be evaluated using ‘pass or fail’ criteria. If one of these requirements is not met, Sorouh Energy holds the right to not evaluate the proposal. The list of administrative requirements is provided in Annexure II. Bidder will have to provide a signed version of Annexure II.

## Technical Proposal

| Type | Requirement | Proof (free format) |
| --- | --- | --- |
| Project Approach | - A description of the methods applied, applicable standards, the proposed management structure, how it plans to ensure the quality of its performance; and its capability to quickly mobilize required experts. - A project schedule, specified in weeks, including visible critical path and milestones - If the Bidder decides to participate as a consortium, the consortium members and split of scope must be made known. | Description Gantt chart Consortium companies, split of scope |
| Project References | - Demonstration of experience in similar projects for (international) financial Institutions like IFC, the World Bank or Asian Development Bank - Demonstration of references of projects from which the ESIA report was accepted by notified body | Reference list, for each project, include: - Project description - Client name - Start date & completion date |
| Project team | - Project team lead - The assignment must be carried out by a qualified [team of] independent local expert(s), with appropriate environmental and social auditing background and experience in the sector and region. Combined roles may be performed by one person but should ensure sufficient capacity to deliver the required deliverables. | - Organogram of the project organisation - CV of Project Manager and project team members |

## Financial Proposal

### Financial proposal outline

Bidder must include a financial section, with the following content:

- The Price, based on lump sum

- A breakdown of the Price in separate cost items according to the items in paragraph Error! Reference source not found. with specification of hourly effort of each project member.

- Its liability cap to the SPV, expressed in USD amount and as percentage (%) of its lump sum proposal.

- Standard hourly rate tables for consideration due to variations

### Payment Milestones

Please note that the ESIA will comprise of a milestone (M2) at which time a decision is made, to continue with the ESIA, as required by lenders of the SPV.

| # | Description | Deliverable | Payment |
| --- | --- | --- | --- |
| M1 | Kick-off Meeting | Minutes of the workshop | 30% |
| M2 | Intermediate report | Consultant’s intermediate report | 30% |
| M3 | Draft report | Consultant’s report with draft study results | 10% |
| M4 | Final report | Consultant’s final report | 30% |

The final payment term is set on 30%. This expresses the importance for the SPV to obtain the final report according to schedule.

# Annexure I – Data sheet

# Annexure II – Minimum Administrative Requirements

Regarding this RFP, I the undersigned with authority on behalf of [name of Bidder Company]

Name:		[……………………………………………………………………]

Position:	[……………………………………………………………………]

Company:	[……………………………………………………………………]

declare that the Proposal complies with the requirements, provided in the table below:

| No | Requirement | Initials |
| --- | --- | --- |
| 1 | Bidder is not in a state of bankruptcy, insolvency, or receivership |  |
| 2 | Bidder is not subject to the suspension of its business activities |  |
| 3 | Bidder is not subject to any pending criminal lawsuits |  |
| 4 | Bidder is not listed on any debarment list published by multilateral financial institutions |  |
| 5 | Bidder has no conflicts of interest in undertaking this assignment |  |
| 6 | Bidder agrees to sign a Non-Disclosure Agreement with the SPV |  |

Although the requirements will apply to all subcontractors as well, the Consultant will be liable for its application.

This Statement has been made truthfully.

[signature]

[date]

# Annexure III – Terms and Conditions

In general, Consultant must cooperate with information requests from the SPV’s lenders (i.e. access to the Consultant’s books, accounts and records, access to the Consultant’s premises).

FIDIC Client / Consultant Model Services Agreement, Fifth edition 2017 will be applicable.

Some clauses will be subject to negotiation with the selected Bidder.

- The SPV proposes to include additions and amendments to ‘Part A Particular Conditions’

- The SPV proposes to include additions and amendments to ‘Part B Additional or Amended Clauses’ of the FIDIC Client / Consultant Model Services Agreement’

Part A and Part B are provided on the next pages.

# Annexure IV – Example index and content of the ESIA report

- Executive summary. The summary should be a brief non-technical description of the salient features of the project, the existing environment of the project site, the key environmental (meaning environmental, social, health, biodiversity, labour, safety, and security) impact, a concise summary of significant findings and recommended mitigation actions from the ESAP and EMP. The summary must include a clear compliance overview table, providing for each item of the Reference Framework at least the following information per key requirement:

- Description of the requirement

- Compliance status, differentiating between minor and major gaps to completion

- Description of the observed situation/compliance gap

- Recommended follow-up

- Introduction. Background of the proposed project, objectives and justification of the proposed project, problem statement and brief project outline, objectives of ESIA, methodologies and technologies adopted in the ESIA, and an overview of approvals needed.

- Project description. Provide detailed project description with a focus on:

  - understanding the environmental and social setting and sensitivities for the proposed project.

  - the technical components as known at this stage (including description of project site, project layout plan, and an overview of the major project components of both permanent and temporary structures), also presenting those components that are yet to be defined and indicating associated options; and

  - likely activities to take place during the project phases (planning, construction, and operations).

- Analysis of alternatives. Systematically compares feasible alternatives - including the "without project" situation - for the proposed project site, technology, design, and operation in terms of:

  - their potential environmental and social impacts.

  - the feasibility of mitigating these impacts.

  - their capital and recurrent costs.

  - their suitability under local conditions.

  - their institutional, training, and monitoring requirements.

For each of the alternatives, quantifies the environmental impacts to the extent possible, and attaches economic values where feasible.

- Policy, legal, and administrative framework. Identifies the policy, legal, and administrative framework within which the ESIA is carried out. This will include the national and state specific regulations (including permits, licenses, and approvals). The Consultant will analyse local/national assessment and permitting requirements and the international environmental and social requirements and compare them within a gap analysis in tabular format.

- Land ownership and proposed land acquisition process review. Identify the Project footprint and land acquisition needs. Review the land acquisition process proposed for the project and its applicable requirements versus existing land acquisition regulations in the country. Determine past and current land uses, any legacy or land acquisition issues.

- Environmental, ecological, and social baseline. Assesses and define the baseline of the study area, including (but not limited to) the following characteristics:

- Physical (topography, geology, climate and meteorology, hydrology, noise, air quality and aesthetic and visual resources)

- Historical & archaeological importance (physical or cultural)

- Biological /Ecological resources (terrestrial, avian or marine)

- Socio-economic conditions (of communities and local government)

- Climate change scenario predictions (temperature, wind speed, floods, etc)

including any changes anticipated before the project commences. Also considers current and proposed development activities within the project area but not directly connected to the project. Data should be relevant to decisions about project location, design, operation, or mitigatory measures. The section indicates the accuracy, reliability, and sources of the data. The Consultant will review available environmental and social baseline data (e.g. that already gathered by local governmental and possibly non-governmental organisations).  Gaps will be identified between available baseline data and the need for recent and relevant data necessary to conduct an ESIA commensurate and proportional to the potential impacts and issues of the Project. The Consultant will identify actions to fill these baseline data gaps including any further environmental or social baseline studies that would be required (e.g. intrusive investigations for soil contamination, biodiversity studies, water quality baseline studies, socio-demographic studies, studies of land-tenure, livelihoods & economic strategies, cultural heritage or archaeological studies, etc.).

- Information disclosure, consultation, and participation. Identify all key stakeholders (government, NGOs, CSOs, academicians, etc.) including vulnerable groups in the project area (youth, female, ethnic minorities, waste pickers, etc.) in the project AOI and analyse their perspectives of the project and include measures to engage with them. Conduct stakeholders’ consultation that ensures that all key stakeholders are aware of the objectives and potential E&S impacts of the proposed project, and that their views are incorporated into the projects’ design as appropriate. A conclusion regarding broad community support must be provided. Stakeholder engagement shall be undertaken during the preparation of the ESIA in accordance with national regulations and IFC PS 1 and EBRD PR10. The result of the stakeholder identification, analysis, and public consultation activities prior to ESIA finalization should be reflected in a dedicated chapter of the ESIA. As part of the engagement with stakeholders, assess necessity of security protection for assets and personnel which include if needed a security team trained in human rights.

- Anticipated environmental impacts and mitigation measures. Map the envisaged facility and its production process and predicts and assesses the project's potential direct and indirect, long and short-term, positive and negative, cumulative and incremental impacts. Where possible, effects should be quantified, uncertainties highlighted, and the basis of predictions stated and justified all according to the SoW and Reference Framework. The assessment identifies mitigation measures and any residual negative impacts that cannot be mitigated. It also includes a potential schedule and cost of each area of concern. It explores opportunities for environmental enhancement, identifies and estimates the extent and quality of available data, key data gaps, and uncertainties associated with predictions, and specifies topics that do not require further attention. It provides an assessment of the project’s gross and net GHG emissions. Assesses the project vulnerability to potential climate hazards.

- Environmental and Social Management Plan (ESMP). The ESMP is expected to be a framework to guide the private party in the implementation of the mitigations and should be as specific as possible based on the status of the project design. Once the design is finalized, the ESMP will be further developed and updated through a series of plans and procedures, based on the design and any additional study required.

The ESMP should be submitted including the following:

  - A summary of the anticipated significant adverse environmental impacts together with the mitigation measures for each anticipated significant/non-significant adverse environmental and social impact throughout the project cycle and residual impact if any. Mitigation measure should be specific as much as possible.

  - Management Programs. Action plans and potential improving procedures to avoid, minimize or compensate the risks and impacts identified. Include plan on how to deal with potential resettlement, habitat sensitiveness and biodiversity.

  - Organizational Capacity and Competency. Definition of key roles, responsibilities, and authorities to implement the Environmental and Social Management System (ESMS)

  - Emergency Preparedness and response.

    - Identification of potential accidents and emergency situations

    - Provide necessary procedures for each identified emergency that clearly explain what actions need to be taken in such case.

  - Monitoring plan

    - Parameters to be monitored

    - Proposed locations of sampling points

    - Methodology for monitoring

    - Frequency of monitoring

    - Responsible agency / agencies

    - Availability of funds, expertise and facilities including budget/cost considerations

  - Implementation arrangement

    - Implementation schedule of the impact mitigation plan showing phasing and coordination with overall project implementation

    - Institutional framework, indicating who is responsible for carrying out the mitigation and monitoring.

    - Capital and recurrent costs to implement mitigation and monitoring measures described above (as per requirement of IFC PS and ADB SPS). Identify the availability and source of funds to implement the measures including for capacity development activities.

ESMP is expected to be a framework to guide to the SPV in the implementation of the mitigations and should be as specific as possible based on the status of the project design. Once the design is finalized, the ESMP will be further developed and updated through a series of management plans and procedures based on the design and any additional study required. Should be split into: Detailed design and planning phase, Pre- construction Phase- site preparation, Construction phase and Operations and Maintenance phase mitigation measures.

- Conclusion and recommendation. The environmental and social acceptability of the proposed project and key findings and recommendations of the assessment should be given. The consultants should make a firm recommendation on one of the alternatives based on the findings of the assessment. Any programme to improve general environmental and social conditions can also be stated here.

- Appendixes

- List of report authors; individuals and organizations.

- Public consultation report:

  - A summary of public outreach activities including audience, number of persons, organizations involved, concerns raised, responses to comments

  - Comments made by the public NGOs and other agencies during the formal and informal scoping meetings

  - Summary of response to comments

  - Actual copies of written comments including meeting minutes

- Technical supporting documents (maps, plans, charts, studies, etc).

- References: written materials both published and unpublished, used in study preparation, including sources of data & Information.

# Annexure V – Project reporting template

www.harvestwaste.com

Bidder is allowed to participate as a Consortium. In that case, the minimum administrative requirements must also be met by the subcontractors

Bidder to include company quality standards like ISO9001/14001/45001, if applicable

For all references, the current version applies

As Low As Reasonable Achievable

Consultant to provide its reports in the English language

According to reference framework

According to reference framework

As specified in FIDIC White (5th Edition)

Envisaged lenders: Invest International Capital BV, IFC, EBRD, amongst others

This may include, but is not limited to, a prediction of the CO2 emissions (or equivalent) avoidance as well as the estimation of the number of (direct/indirect) jobs created.