## Slide 1
Project Element | Progress Sched / Perf | Status | Key Issues / Actions
R166A Neville Dodds |  | CR1404 Tape – Work underway to produce trial tapes. Target for tape delivery is year end 16 | 
R166B Jim Latto / Vineet Jha |  | Materials engineering resource allocated to project – all materials categorisation and specifications to be handed over for progression Senior product development engineer allocated to progress test rig design and online monitoring for results (Including fibre optic system) | Scope creep – Rosebank 10” – additional work to be accounted for. Change control process needs to be implemented to capture additional requirements. DNV engaged as consultants to ensure all development and qualification work within R166 program is in compliance with PB requirements
R166C Andrew Batchelor |  | Work ongoing and some savings in timescale have already been realised. Andrew and team is progressing well and more progress / time saving is expected as design / build matures. | Resource within manufacturing needs to be addressed to maintain progress. CAPEX engineer is due to leave GE and may affect the progress of the factory preparation for module 1..
R166D Fabio Pires (C1876) |  | Petrobras draft specification for qualification received and initial review complete. Worksop held in Rio WC 5th Sep to discuss changes / requirements | Next Libra workshop will be end Nov 16. Prior to this, we will produce a draft qualification spec with DNV . RFP for Libra due end Sep for FEED study
R166F Jim Latto |  | IR tape consolidation head delivered and installed DTR sample delivered to ETA in San Antonio – Team in attendance to setup and commence testing Mid-scale Thermal Cycle ongoing at ETA | RPSEA contract / commitment due to end Sep 16. R166 program will be responsible for funding and Completion of the DTR test from October. Requirement expected and covered in 2016 / 17 Budget.
R166 Composites Development Program – Summary Sep 16