## Project Budget
Cost Baseline
Title:
FS - Cost Baseline
WBS | Activity | Responsible | Hours | €/hour | Total Projected | Actual Cost | Projected X Actual
01.Information Collection | 1.1 Pre-select suppliers for gather rely upon data | Local representative
01.Information Collection | 1.2 Sign contracts with suppliers | AWECT
01.Information Collection* | 1.3 Waste analisys Study | Local supplier |  |  | 8500 |  | 8500
01.Information Collection* | 1.3 Site analisys (soil analysis, climate, access, interfaces) | Local supplier |  |  | 18050 |  | 18050
01.Information Collection* | 1.3 Grid study | Local supplier |  |  | 30050 |  | 30050
01.Information Collection* | 1.3 Environmental analisys (land, retention times, emissions, social, health, aestethic) | Local supplier | - | - | 42100 |  | 42100
01.Information Collection* | 1.3 Well Water Study | Local supplier |  |  |  |  | 0
01.Information Collection* | 1.3 Waste Management Study | Local supplier |  |  | 60000 |  | 60000
01.Information Collection | 1.4 Validate other inputs via desk study | AWECT |  |  | 320000 |  | 320000
01.Information Collection | 1.5 Validate economic assumptions (CAPEX, OPEX, Revenues) | Local representative |  |  |  |  | 0
02. Create conceptual design (technical) | 2.1 Plant block diagram with the main mass flows. | W&G |  |  |  |  | 0
02. Create conceptual design (technical) | 2.2 Basic overall functional process description. | W&G |  |  |  |  | 0
02. Create conceptual design (technical) | 2.3 Plant Flow Diagrams of the process with all the main components (Grate and Boiler, Flue Gas Treatment, Water-Steam- Cycle) | W&G |  |  |  |  | 0
02. Create conceptual design (technical) | 2.4 Design of the main components (boiler, turbine/generator, condenser and flue gas treatment) and model the water-steam cycle | W&G |  |  |  |  | 0
02. Create conceptual design (technical) | 2.5 Elaboration of the logistics of waste delivery and dimension the tipping area, bunker and waste cranes | W&G |  |  |  |  | 0
02. Create conceptual design (technical) | 2.6 A comprehensive report which includes all the results of the conceptual design | W&G |  |  |  |  | 0
03 Create Business Case | 3.1 Estimation based on prices for comparable components which we have obtained from other projects in Europe | AWECT
03 Create Business Case | 3.1 Local market prices for equipment deliveries, where possible with input and support from Local Partner for regional price comparisons | Local Partner
03 Create Business Case | 3.1 Estimation from Local market prices for civil works based on approximate bills of quantities; | Local Partner
03 Create Business Case | 3.1 Create OPEX estimate (+/- 20%) | AWECT
03 Create Business Case | 3.4 Develop financial model, e.g. with input from conceptual design | AWECT
04. Create Feasibility Study report with all results | 3.5 Create a proposed plan and timeline for the long lead itemsnecessary for realizing a WtE plant | AWECT + W&G
04. Create Feasibility Study report with all results | 3.6 Make a final presentation to local partners, sponsors and if necessary the relevant Authorities | AWECT
Total |  |  |  |  | 478700 | 0 | 478700
* Price based on input from Indian market