## Schddule baseline LOI-COD (hidden)
Critical path items | Duration | Feasibility Phase | Definition Phase | Total costs | 2023 | [5 empty] | 2024 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
[5 empty] | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2
[5 empty] | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d
Project Development | 18 mth
WP1-Procurement |  | 0 | 50000 | 50000
Consultants for feasibility studies | 1 mth | bar: Q3 j
EPC contract development | 6 mth
EPC contracting | 3 mth | bar: Q3 j to Q3 m
WP2 - Contract & Legal
Setup & funding of SVP
Develop & negotiate PPA, Waste Concession | 6 mth | 150000 | 250000 | 400000
WP3 - Feasibilty & Design
Feasibility Study | 6 mth | bar: Q3 j to Q4 j
Permit Assessment | 1 mth | 10000 | 0 | 10000 | bar: Q3 f
Waste Charachterization Study | 2 x 2 mth | 90000 | 0 | 90000 | bar: Q3 f to Q3 m; Q4 j to Q1 j
Grid Interconnection Study | 2 mth | 60000 | 0 | 60000 | bar: Q3 f to Q3 m
Geotechnical study (soil, climate, logistics) | 2 mth | 25000 | 0 | 25000 | bar: Q3 f to Q3 m
Waste Management Study | 3 mth | 35000 | 0 | 35000 | bar: Q4 a to Q4 j
Environmental & Social Impact Assessment (EISA) | 6 mth | 75000 | 140000 | 215000 | bar: Q3 f to Q1 j
Conceptual Design & Feasibility Report | 3 mth | 325000 | 0 | 325000 | bar: Q4 m to Q1 j
Basic Design & Employer requirements | 6 mth | 0 | 675000 | 675000 | bar: Q1 j to Q2 d
WP4-Permits and Public Relations | 9 mth | 0 | 0 | 0
WP5-Funding |  | 25000 | 555000 | 580000
Preselect lenders | 3 mth
Develop lenders agreement | 9 mth | bar: Q1 j to Q3 m
Finalize lenders contracts | 3 mth | bar: Q4 a to Q4 j
EPC | 30 mth | 795000 | 1620000 | 2415000
Detailed Design | 6 mth | bar: Q1 j to Q2 d
Procurement & Construction | 18 mth | bar: Q3 j to Q4 j
Testing, Commissioning and Startup | 6 mth | bar: Q1 j to Q2 d
Project Milestones
Award = t = 0 | 2023-01-01
Project Feasible Y/N? = t + 6 | 2023-07-01
Technical Close = t + 12 | 2024-01-01
Financial Close = t + 18 | 2024-07-01

## LoI-COD (hidden)
Critical path | Duration | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d
Feasibility and Definition Phase | 18 mth | bar: Q1 j to Q2 j
WP1-Procurement
Consultants for feasibility studies | 1 mth
HE equipment | 6 mth
EPC and O&M | 9 mth
WP2 - Contract & Legal
Develop & negotiate PPA, Waste Concession, Land | 12 mth
WP3 - Feasibilty & Design
Feasibility Study | 6 mth
Permit Assessment | 1 mth | bar: Q1 f
Waste Charachterization Study | 2 x 2 mth | bar: Q1 f to Q1 m; Q2 j to Q3 j
Grid Interconnection Study | 2 mth | bar: Q1 f to Q1 m
Geotechnical study (soil, climate, logistics) | 2 mth | bar: Q1 f to Q1 m
Waste Management Study | 3 mth | bar: Q2 a to Q2 j
Environmental & Social Impact Assessment (EISA) | 10 mth | bar: Q1 f to Q4 n
Financial Modeling | 1 mth | bar: Q3 j
Conceptual Design & Feasibility Report | 3 mth | bar: Q2 m to Q3 j
Basic Design | 6 mth
WP4-Permits and Public Relations | 10 mth
WP5-Funding
Preselect lenders | 3 mth
Develop lenders agreement | 9 mth
Finalize lenders contracts | 3 mth
EPC Phase | 36 mth | bar: Q3 j to Q2 j
Detailed Design | 6 mth
Procurement long lead items | 12 mth
Construction non critical parts of WtE | 21 mth
Construction of process works, including HE equipment | 12 mth
Testing, Commissioning and Startup | 6 mth | bar: Q2 j
Key Milestones
Award | t = 0 | bar: Q1 j
Project Feasible Y/N? | t + 6 mth | bar: Q3 j
Technical Close: design freeze | t + 12 mth | bar: Q1 j
Financial Close (FC) | t + 18 mth | bar: Q2 j
Detailed design accepted by SPV | FC + 6 mth | bar: Q4 d
Finalize construction works | FC + 24 mth | bar: Q4 d
Commercial Operation Date | FC + 30 mth | bar: Q2 j

## Development baseline
Critical path items | Duration | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4 | [11 empty] | Year 5
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
|  | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d | j | f | m | a | m | j | j | a | s | o | n | d
Project Development | 18 mth
WP1-Procurement
Consultants for feasibility studies | 1 mth | bar: Q1 j
EPC employer requirements & contract development | 12 mth
EPC contracting | 3 mth | bar: Q1 j to Q1 m
WP2 - Contract & Legal
Setup & funding of SVP
Develop & negotiate PPA, Waste Concession, Land | 12 mth
WP3 - Feasibilty & Design
Feasibility Study | 6 mth | bar: Q1 j to Q2 j
Permit Assessment | 1 mth | bar: Q1 f
Waste Charachterization Study | 2 x 2 mth | bar: Q1 f to Q1 m; Q3 j to Q3 a
Grid Interconnection Study | 2 mth | bar: Q1 f to Q1 m
Geotechnical study (soil, climate, logistics) | 2 mth | bar: Q1 f to Q1 m
Waste Management Study | 3 mth | bar: Q2 a to Q2 j
Environmental & Social Impact Assessment (EISA) | 6 mth | bar: Q1 f to Q3 j
Conceptual Design & Feasibility Report | 3 mth | bar: Q2 a to Q2 j
Basic Design | 6 mth | bar: Q3 j to Q4 d
WP4-Permits and Public Relations | 9 mth
WP5-Funding
Preselect lenders | 3 mth
Develop lenders agreement | 9 mth | bar: Q3 j to Q1 m
Finalize lenders contracts | 3 mth | bar: Q2 a to Q2 j
EPC | 30 mth
Detailed Design | 6 mth | bar: Q3 j to Q4 d
Procurement & Construction | 18 mth | bar: Q1 j to Q2 j
Testing, Commissioning and Startup | 6 mth | bar: Q3 j to Q4 d

## Development baseline II slide
|  | Year 1 |  |  |  | Year 2
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
SPV project development | Duration
EPC selection & contract development | 12 mth
EPC contracting | 3 mth
Develop & negotiate PPA, Waste Concession, Land | 6 mth
Feasibility Study | 6 mth
Basic design & employer requirements | 6 mth
Obtain permits | 9 mth
Preselect lenders | 3 mth
Develop lenders agreement | 9 mth
Finalize lenders contracts | 3 mth
SPV team (in Full Time Equivalent) | Name | FTE | FTE | FTE | FTE | FTE | FTE
Project Director | TBD | 0.5 | 0.5 | 1 | 1 | 1 | 1
PMO support | TBD | 0.5 | 0.5 | 1 | 1 | 1 | 1
Procurement Manager | TBD | 0.5 | 0.5 | 1 | 1 | 1 | 1
Technical Manager | TBD | 0.5 | 0.5 | 1 | 1 | 1 | 1
Finance Manager | TBD | 0.5 | 0.5 | 1 | 1 | 1 | 1
HQ Support (in Full Time Equivalent) | Name | FTE | FTE | FTE | FTE | FTE | FTE
Director Operations | Lars | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2
Procurement Director | Starts 1/5/24 | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2
Technical Director | Jim | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2
Finance Manager | Bas | 0.5 | 0.4 | 0.2 | 0.2 | 0.2 | 0.2