| Project Code | R166 | Project Sponsor | Alberto Matucci |
| --- | --- | --- | --- |
| Project Name | Composite Flexible Pipe | Project Manager | Jim Latto |
| WBS | R166.B.5.C.7.4 | Principal Engineer | Neville Dodds |
| Document Ref | R166.B.5.C.7.4 | Owner | David Finch |
| Revision | 0 | Revision Date | 15/05/17 |
| Work Package Title | Full-scale Testing - Touch Down Point Rig |  |  |

# Work Package Summary

|  | Description of test / group of Tests within work package. Why is the test / group of tests needed? What will data generated from this test / group of tests be used for? |
| --- | --- |

This work package contains all testing to be performed at full scale in a bespoke touch down point (TDP) rig.  The TDP rig will be used to simulate tension, pressure, bending and temperature loading conditions with or without full scale end fittings.

The TDP rig will used to address client specific requirements on touch down point loads and will also be used to test operational loading condition scenarios including installation, re-termination and combined loading.  The TDP rig will also be used to condition samples to the required end of life loading cases and will enable the verification of modelling tools and methodologies

Several full-scale qualification / verification requirements use the lifetime approach.  This approach requires that several full-scale tests are carried out using a single sample.  The reason for this is to ensure that damage from multiple scenarios is considered when calculating the qualified pipe service life.  Where this is the case, samples may be used across work packages and this must be taken into account when planning the sequence of execution.

Full scale verification of TDP loads:  Full scale sample testing would enable GE to check the performance of the pipe under the shear and compression loading conditions experienced at the pipe touch down point. This test will also enable GE to develop modelling tools by correlating data captured from full scale verification.

# Work Package Deliverables

|  | Specific deliverables, numbered with specific references to the project WBS and any relevant documentation that raises the requirement (API / DNV / FMECA Item etc.) |
| --- | --- |

| R166.B.5.C.7.4 Full-scale Testing - Touch Down Point Rig |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| P6 | Activity/Milestone | Target Start | Target Completion | Weeks | FMEA Ref. |
|  | Scope/Strategy/Specifications |  |  | 4.0 | 1.1, 5.11 |
|  | Concept Design |  |  | 4.0 |  |
|  | Detailed Design | 04.08.2017 | 01.09.2017 | 4.0 |  |
|  | Build/Manufacture | 15.09.2017 | 27.10.2017 | 6.0 |  |
|  | Commissioning |  |  | 2.0 |  |
| x | Test Programme |  |  | 2.0 |  |
| x | Test | 26.01.2018 | 13.07.2018 | 24.0 |  |
| x | Dissection (if required) |  |  | 2.0 |  |
|  | Work Package close out |  |  | 2.0 |  |
| x | Report | 03.08.2018 | 31.08.2018 | 4.0 |  |
|  | Design guidelines |  |  |  |  |
|  | Knowledge base |  |  |  |  |
|  | Dependent work packages |  |  |  |  |
|  | Total |  |  |  |  |

# Work Package Links / References

|  | Reference documents and links to documents (Where possible) Examples: API 17xx, DNV RP xx, FMECA - R166Exxx, Procedure - WSI ENGxxx, Design and business reviews |
| --- | --- |

1.  FMECA - Hyperlink

2.  DNV RP's- Hyperlink

3.  API- Hyperlink