## Task
Primary Id | FMECA Item | Evidence Item | Design Parameter or Operating Guideline | Main Issue | Evidence Item Description | Work Package Reference | Due Date | Status | Surname of Owner | Column1
| 1.1 | a | Collapse loading Handling & transportation Determination of manufacturing tolerances for the carcass profile | Carcass layer or interlock (due to incorrect profile)​ | Manufacturing Guidelines |  | 2017-06-30 | Backlog |  | x
| 1.1 | b | Collapse loading Handling & transportation Determination of manufacturing tolerances for the carcass profile | Carcass layer or interlock (due to incorrect profile)​ | Collapse modelling and methodology |  |  | Planning |  | x
| 1.1 | c | Collapse loading Handling & transportation Determination of manufacturing tolerances for the carcass profile | Carcass layer or interlock (due to incorrect profile)​ | Experimental results and correlation of evidence |  |  | In Progress |  | x
| 1.2 | a | Collapse loading. Handling & transportation. | Carcass layer or interlock (due to cracked carcass) | Manufacturing Guidelines |  |  | Complete |  | x
| 1.2 | b | Collapse loading. Handling & transportation. | Carcass layer or interlock (due to cracked carcass) | Collapse modelling and methodology |  |  |  |  | x
| 1.2 | c | Collapse loading. Handling & transportation. | Carcass layer or interlock (due to cracked carcass) | Experimental results and correlation of evidence |  |  |  |  | x
| 1.3 | a | Collapse loading Handling & transportation & Installation TDP compression | Loss of interlock (due to out of spec carcass) | Manufacturing Guidelines |  |  |  |  | x
| 1.3 | b | Collapse loading Handling & transportation & Installation TDP compression | Loss of interlock (due to out of spec carcass) | Operating Guidelines |  |  |  |  | x
| 1.3 | c | Collapse loading Handling & transportation & Installation TDP compression | Loss of interlock (due to out of spec carcass) | Collapse modelling and methodology |  |  |  |  | x
| 1.3 | d | Collapse loading Handling & transportation & Installation TDP compression | Loss of interlock (due to out of spec carcass) | Experimental results and correlation of evidence |  |  |  |  | x
| 1.4 | a | Collapse loading Handling & transportation TDP compression | Carcass layer or interlock failure (due to weld issue) | Manufacturing Guidelines |  |  |  |  | x
| 1.4 | b | Collapse loading Handling & transportation TDP compression | Carcass layer or interlock failure (due to weld issue) | Collapse modelling and methodology |  |  |  |  | x
| 1.4 | c | Collapse loading Handling & transportation TDP compression | Carcass layer or interlock failure (due to weld issue) | Experimental results and correlation of evidence |  |  |  |  | x
| 1.5 | a | Collapse loading Handling & transportation TDP compression (collapse under combined bending, dynamic compression and external pressure) | Carcass layer or interlock failure (due to non uniform loading) | Manufacturing Guidelines |  |  |  |  | x
| 1.5 | b | Collapse loading Handling & transportation TDP compression (collapse under combined bending, dynamic compression and external pressure) | Carcass layer or interlock failure (due to non uniform loading) | Collapse modelling and methodology |  |  |  |  | x
| 1.5 | c | Collapse loading Handling & transportation TDP compression (collapse under combined bending, dynamic compression and external pressure) | Carcass layer or interlock failure (due to non uniform loading) | Experimental results and correlation of evidence |  |  |  |  | x
| 2.1 | a | Transient and Combined cyclic pressure, temperature and axial stress Dry and flooded annulus | Carcass barrier interface sealing and slippage | Single layer program overview - DNV appraisal Manufacturing guidelines Local and global modelling combined with experimental correlation
| 2.2 | a | Transient and Combined cyclic pressure, temperature and axial stress Dry and flooded annulus | Controlling carcass nub ( full ingress scenario) and related behaviour | Single layer program overview - DNV appraisal Manufacturing guidelines - API 4th edition compliance Local and global modelling combined with experimental correlation
| 3.1 | a | Annulus, bore fluid conditions (evolution of material's properties, i.e., ageing, micro voids etc.) Nub (tip) geometry and tolerances Operational conditions such as pressure, thermal, RGD and bending cycling | Controlling carcass nub ( high KT scenario) and related behaviour | Single layer program overview - DNV appraisal Manufacturing guidelines - API 4th edition compliance Local and global modelling combined with experimental correlation - dynamic fatigue behaviour of 60512 material
| 3.2 | a | Long term performance of barrier under creep loading | Creep/stress rupture during storage and operation | Polymer material data review - creep FMECA item 5.1 refers - combined composite PA & barrier polymer creep data
| 3.3 | a | Inclusion acceptance criteria / or product (barrier) quality & performance thresholds | inclusion or moisture in barrier layer | QC procedures - manufacturing & material supply specification Barrier layer extrusion parameters / guidelines
| 3.4 | a | Start up and Shut Down Cyclic fatigue | Thermal stress in barrier layer | FMECA Item 5.4 - RGD performance of composite barrier interface Polymer material RGD categorisation data review - Note to include historical RGD data (WSI 008)
| 3.5 | a | Pressure loading Dynamic vessel movement Pipe handling or interaction with Sea bed Polymer layer Kt value guidelines / limitation refer - design methodology - Kt analysis, ageing (creep) and load case calculation for service life survival | Combined pressure and bend
| 4.1 | a | Reel storage Time dependent stress and creep performance | Long term storage on reel/ Stress rupture | Standard flexible testing data+ refer to 5.1 and 5.3
| 4.2 | a | Start up and shut down operation including RGD Changes in pressure during operation Delamination due to riser bending cycling and differential stiffness between the pressure armour and the barrier Accumulated fluids at the interface from barrier | Rapid gas decompression effect on polymer layer | FMECA Item 5.4 - RGD performance of composite barrier interface Prediction of barrier movement under the sealing mechanism (seal ring) and the establishment of criteria / limitations
| 5.1 | a | Stress rupture / Static fatigue | Creep/stress rupture during storage | Design Premise & prediction of small to large scale testing
| 5.1 | b |  |  | Test records / reporting for work package 1 deliverable | R166.B.5.C.5.1 Creep: Composite tape creep properties will be characterised at room temperature and elevated temperature.
| 5.1 | c |  |  | Test records / reporting for work package 2 deliverable
| 5.1 | d |  |  | Test records / reporting for work package 3 deliverable
| 5.1 | e |  |  | Test records / reporting for work package 4 deliverable
| 5.1 | f |  |  | Design tool calibration & simulation of actual field operating conditions
| 5.2 | a | Exceeding MBR that results in excessive strain and pipe failure | Normal and excessive Bending strain | Design Premise & prediction of small to large scale testing
| 5.2 | b |  |  | Test records / reporting for work package 1 deliverable
| 5.2 | c |  |  | Test records / reporting for work package 2 deliverable
| 5.2 | d |  |  | Test records / reporting for work package 3 deliverable
| 5.2 | e |  |  | Test records / reporting for work package 4 deliverable
| 5.2 | f |  |  | Design tool calibration & simulation of actual field operating conditions
| 5.3 | a | Storage Bend Radius Reeling time and rates Applied tension and twist reference (effect on EF) | Long term storage on reel/ Stress rupture | Refer to FMECA item 5.1 for evidence requirement
| 5.4 | a | Delta P (e.g. due to RGD) Rate of change Temperature Gas composition/ co2 and High Co2 content / supercritical under pressure | Rapid gas decompression | Detailed testing program to be proposed to DNV & LIBRA for endorsement Go / No-go decision gate proposed by GE for alternative test to PB spec. If no outcome is achieved the PB spec prevails.
| 5.5 | a | Low temperature during Installation | Low temperature brittle cracking | WP1 to WP2 & Thermal analysis (for end fitting) tool matched predictions before and after test.
| 5.6 | a | Pipe Fatigue (static and dynamic) during reeling and installation | cyclical fatigue (high strain) | Design Premise & prediction of small to large scale testing Test records / reporting for referenced work package deliverables (WP 1 to 4) Design tool calibration & simulation of actual field operating conditions
| 5.7 | a | Pipe Fatigue and Life of riser during operation. With reference to operational fluids and change of use WAG from Libra spec. | cyclical fatigue (Low strain) | Design Premise & prediction of small to large scale testing Test records / reporting for referenced work package deliverables (WP 1 to 4) Design tool calibration & simulation of actual field operating conditions
| 5.8 | a | Temperature changes during operation effecting CPA (thermal history due to Manufacturing process) | Thermal stress during Manufacturing | WP1 (Complete) to WP2 (Q3 17)
| 5.9 | a | Temperature changes during operation effecting CPA (thermal history due to operating parameters) | Thermal shock during operation (mainly EF) | Design Premise & prediction of small to mid scale testing Test records / reporting for referenced work package deliverables (WP 1 to 3) Design tool calibration & simulation of actual field operating conditions during thermal shock test
| 5.10 | a | Product acceptance criteria related to inclusion / voids/ moisture etc. | Defects, inclusion and flaws | WP 1 & 2 (Complete - WP 3 & 4 to be completed Evidence of methodology to define minimum defect size limitations for manufacturing QA / QC Third party approval of GE's internal QA process for composite pressure armour manufacture.
| 5.11 | a | Compressive loads and cyclical bending due to: Tensioner crushing during installation (including time dependent effect) Regular operating TDP due to bend collapse stress field Cyclical compressive axial loads due to vessel motion (tensile) | 1. Cyclical compression loads 2. Crush and slippage resistance of layers | Design Premise & prediction of small to large scale testing Test records / reporting for referenced work package deliverables (WP 1 to 4) Design tool calibration & simulation of actual field operating conditions
| 5.12 | a | Pressure loading Dynamic vessel movement Pipe handling or interaction with Sea bed | Combined pressure and bend loading | Design Premise & prediction of small to large scale testing Test records / reporting for referenced work package deliverables (WP 1 to 3) Design tool calibration & simulation of actual field operating conditions
| 5.13 | a | Operational Offshore dynamic conditions and OBR (Operating bending Radius), MBR (Minimum Bending Radius) Environmental Conditions Residual Strength of the CPA after the failure of a pre-determined agreed number of wires (3 TBC) in the tensile layer | Bend fatigue including twist / shear effect of tension on interface layers | Design Premise & prediction of small to large scale testing Test records / reporting for referenced work package deliverables (WP 1 to 4) Design tool calibration & simulation of actual field operating conditions
| 6.4 | a | Tensile capacity
| 6.5 | a | Tensile capacity
| 6.1 | a | Incorrect Permeation model, material selection Ingress of sea water from ambient external env due to breach of outer sheath or leakage at ports and sealing at End fitting or vent valve Condensation of water from internal fluids Stress induced due intern
| 6.3 | a | Tensile capacity
| 9.11 | a | Loads transferred from the pipe layers to the carcass termination, including own weight (self weight) Contact Pressure from the sealing system over the Seal contact area (resulting in excessive deformation of the carcass inwards) System to anchor the c | Carcass self weight and termination | WP1 Modelling & test result prediction WP 2,3 & 4 Testing & dissection (mid and full scale ) Model calibration & validation - Based on WP 2,3 & 4 & dissection results
| 9.21 | a | Axial strain, swaging and effect on pressure seal | Problems with Flexwear and related sleeve | Should dual layer design be included in future product qualification, the following points will apply: WP1 Modelling & test result prediction WP 2,3 & 4 Testing & dissection (mid and full scale ) Model calibration & validation - Based on WP 2,3 & 4 & dis
| 9.31 | a | Swaging and effect on pressure seal Swaging assembly component manufacturing and assembly tolerances | Problems with swaging with Barrier layer | Modelling & test result prediction WP 1,2 Testing & dissection (mid - scale) Model calibration & validation - Based on WP 1 & 2 dissection results
| 9.32 | a | Local heating during further layer End fitting terminations | Epoxy curing during EF assembly
| 9.33 | a | Specific to sealing system (ring) contact with barrier: Effect of thermal and pressure cycling (under weight of composite liner and carcass) Cyclic axial component due to tensile loading transfer to EF Barrier sealing degradation to exposure to fluid St | Self weight of carcass+ polymer on Liner seal effect of Axial strain
| 9.41 | a | thermal stress resulting in movement of the seal Refer to 9.33 for details of this failure mode | Same as above, but study the effect of thermal stress | FMECA item 9.33 refers
| 9.42 | a | Pressure and cyclical loads transfer generating additional tension; Thermal cycling; Component of own weight of composite pressure armour+liner+carcass not transferred to the tensile armour; General comment: A hundred percent contact pressure must b | Self weight of carcass+ polymer + bonded CPA thermal stress effect of Axial strain | WP1 Modelling & test result prediction WP 2,3 & 4 Testing & dissection (mid and full scale ) Model calibration & validation - Based on WP 2,3 & 4 & dissection results
| 9.43 | a | Stress concentration as described in section 8.5 of DNVGL-RP-F119:2015. - The composite pressure armour interaction from the termination point through to the free pipe body should not result in stress concentrations created by the ballooning effect. GE | effect of Axial stress& twist on tensile armour anchoring in epoxy wedge and CPA | WP1 Modelling & test result prediction WP 2 & 3 Testing & dissection (full scale ) Model calibration & validation - Based on WP 2 & 3 & dissection results

## Sheet1
|  |  | Evidence Item | Category
1.1 | a | Carcass Manufacturing Guidelines | 1.1.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.1 | b | Collapse modelling and methodology | 1.1.b - Collapse modelling and methodology | Design Methodology & Tools
1.1 | c | Collapse - Experimental results and correlation of evidence | 1.1.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.2 | a | Carcass Manufacturing Guidelines | 1.2.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.2 | b | Collapse modelling and methodology | 1.2.b - Collapse modelling and methodology | Design Methodology & Tools
1.2 | c | Collapse - Experimental results and correlation of evidence | 1.2.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.3 | a | Carcass Manufacturing Guidelines | 1.3.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.3 | b | Pipe Operating Guidelines | 1.3.b - Pipe Operating Guidelines | Design Methodology & Tools
1.3 | c | Collapse modelling and methodology | 1.3.c - Collapse modelling and methodology | Design Methodology & Tools
1.3 | d | Collapse - Experimental results and correlation of evidence | 1.3.d - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.4 | a | Carcass Manufacturing Guidelines | 1.4.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.4 | b | Collapse modelling and methodology | 1.4.b - Collapse modelling and methodology | Design Methodology & Tools
1.4 | c | Collapse - Experimental results and correlation of evidence | 1.4.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.5 | a | Carcass Manufacturing Guidelines | 1.5.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.5 | b | Collapse modelling and methodology | 1.5.b - Collapse modelling and methodology | Design Methodology & Tools
1.5 | c | Collapse - Experimental results and correlation of evidence | 1.5.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
2.1 | a | Local and global modelling combined with experimental correlation | 2.1.a - Local and global modelling combined with experimental correlation | Mid & Full Scale Testing & Methodology
2.1 | b | Single layer program overview - DNV appraisal | 2.1.b - Single layer program overview - DNV appraisal | Design Methodology & Tools
2.1 | c | Barrier & Carcass Manufacturing guidelines | 2.1.c - Barrier & Carcass Manufacturing guidelines | Design Methodology & Tools
2.2 | a | Single layer program overview - DNV appraisal / Approval | 2.2.a - Single layer program overview - DNV appraisal / Approval | Design Methodology & Tools
2.2 | b | Manufacturing guidelines - API 4th edition compliance | 2.2.b - Manufacturing guidelines - API 4th edition compliance | Design Methodology & Tools
2.2 | c | Local and global modelling combined with experimental correlation | 2.2.c - Local and global modelling combined with experimental correlation | Design Methodology & Tools
3.1 | a | Single layer program overview - DNV appraisal / Approval | 3.1.a - Single layer program overview - DNV appraisal / Approval | Design Methodology & Tools
3.1 | b | Manufacturing guidelines - API 4th edition compliance | 3.1.b - Manufacturing guidelines - API 4th edition compliance | Design Methodology & Tools
3.1 | c | Local and global modelling combined with experimental correlation - dynamic fatigue behaviour of 60512 material | 3.1.c - Local and global modelling combined with experimental correlation - dynamic fatigue behaviour of 60512 material | Design Methodology & Tools
3.1 | d | dynamic fatigue behaviour of 60512 material | 3.1.d - dynamic fatigue behaviour of 60512 material | Material Characterisation & Qualification
3.2 | a | Polymer material data review - creep | 3.2.a - Polymer material data review - creep | Material Characterisation & Qualification
3.2 | b | combined composite PA & barrier polymer creep data | 3.2.b - combined composite PA & barrier polymer creep data | Material Characterisation & Qualification
3.3 | a | QC procedures - manufacturing & material supply specification | 3.3.a - QC procedures - manufacturing & material supply specification | Design Methodology & Tools
3.3 | b | Barrier layer extrusion parameters / guidelines | 3.3.b - Barrier layer extrusion parameters / guidelines | Design Methodology & Tools
3.4 | a | RGD performance of composite barrier interface | 3.4.a - RGD performance of composite barrier interface | Material Characterisation & Qualification
3.4 | b | Polymer material RGD categorisation data review - Note to include historical RGD data (WSI 008) | 3.4.b - Polymer material RGD categorisation data review - Note to include historical RGD data (WSI 008) | Material Characterisation & Qualification
3.5 | a | Combined Pressure & Bend | 3.5.a - Combined Pressure & Bend | Mid & Full Scale Testing & Methodology
4.1 | a | Standard flexible testing data+ refer to 5.1 and 5.3 | 4.1.a - Standard flexible testing data+ refer to 5.1 and 5.3 | Material Characterisation & Qualification
4.2 | a | RGD performance of composite barrier interface | 4.2.a - RGD performance of composite barrier interface | Material Characterisation & Qualification
4.2 | b | Prediction of barrier movement under the sealing mechanism (seal ring) and the establishment of criteria / limitations | 4.2.b - Prediction of barrier movement under the sealing mechanism (seal ring) and the establishment of criteria / limitations | Material Characterisation & Qualification
5.1 | a | Design Premise & prediction of small to large scale testing | 5.1.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.1 | b | Test records / reporting for work package 1 deliverable | 5.1.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.1 | c | Test records / reporting for work package 2 deliverable | 5.1.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.1 | d | Test records / reporting for work package 3 deliverable | 5.1.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.1 | e | Test records / reporting for work package 4 deliverable | 5.1.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.1 | f | Design tool calibration & simulation of actual field operating conditions | 5.1.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.2 | a | Design Premise & prediction of small to large scale testing | 5.2.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.2 | b | Test records / reporting for work package 1 deliverable | 5.2.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.2 | c | Test records / reporting for work package 2 deliverable | 5.2.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.2 | d | Test records / reporting for work package 3 deliverable | 5.2.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.2 | e | Test records / reporting for work package 4 deliverable | 5.2.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.2 | f | Design tool calibration & simulation of actual field operating conditions | 5.2.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.3 | a | Refer to FMECA item 5.1 for evidence requirement | 5.3.a - Refer to FMECA item 5.1 for evidence requirement | Design Methodology & Tools
5.4 | a | Detailed testing program to be proposed to DNV & LIBRA for endorsement | 5.4.a - Detailed testing program to be proposed to DNV & LIBRA for endorsement | Mid & Full Scale Testing & Methodology
5.4 | b | Go / No-go decision gate proposed by GE for alternative test to PB spec. If no outcome is achieved the PB spec prevails | 5.4.b - Go / No-go decision gate proposed by GE for alternative test to PB spec. If no outcome is achieved the PB spec prevails | Mid & Full Scale Testing & Methodology
5.5 | a | Test records / reporting for work package 1 deliverable | 5.5.a - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.5 | b | Test records / reporting for work package 2 deliverable | 5.5.b - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.5 | c | Thermal analysis (for end fitting) tool matched predictions before and after test. | 5.5.c - Thermal analysis (for end fitting) tool matched predictions before and after test. | Mid & Full Scale Testing & Methodology
5.6 | a | Design Premise & prediction of small to large scale testing | 5.6.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.6 | b | Test records / reporting for work package 1 deliverable | 5.6.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.6 | c | Test records / reporting for work package 2 deliverable | 5.6.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.6 | d | Test records / reporting for work package 3 deliverable | 5.6.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.6 | e | Test records / reporting for work package 4 deliverable | 5.6.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.6 | f | Design tool calibration & simulation of actual field operating conditions | 5.6.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.7 | a | Design Premise & prediction of small to large scale testing | 5.7.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.7 | b | Test records / reporting for work package 1 deliverable | 5.7.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.7 | c | Test records / reporting for work package 2 deliverable | 5.7.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.7 | d | Test records / reporting for work package 3 deliverable | 5.7.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.7 | e | Test records / reporting for work package 4 deliverable | 5.7.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.7 | f | Design tool calibration & simulation of actual field operating conditions | 5.7.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.8 | a | WP1 (Complete) | 5.8.a - WP1 (Complete) | Material Characterisation & Qualification
5.8 | a | WP2 (Q3 17) | 5.8.a - WP2 (Q3 17) | Mid & Full Scale Testing & Methodology
5.9 | a | Design Premise & prediction of small to mid scale testing | 5.9.a - Design Premise & prediction of small to mid scale testing | Mid & Full Scale Testing & Methodology
5.9 | b | Test records / reporting for work package 1 deliverable | 5.9.b - Test records / reporting for work package 1 deliverable | Mid & Full Scale Testing & Methodology
5.9 | c | Test records / reporting for work package 2 deliverable | 5.9.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.9 | d | Test records / reporting for work package 3 deliverable | 5.9.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.9 | e | Design tool calibration & simulation of actual field operating conditions during thermal shock test | 5.9.e - Design tool calibration & simulation of actual field operating conditions during thermal shock test | Design Methodology & Tools
5.10 | a | Test records / reporting for work package 1 deliverable - Complete | 5.10.a - Test records / reporting for work package 1 deliverable - Complete | Manufacturing Process CPA
5.10 | b | Test records / reporting for work package 2 deliverable - Complete | 5.10.b - Test records / reporting for work package 2 deliverable - Complete | Manufacturing Process CPA
5.10 | c | Test records / reporting for work package 3 deliverable | 5.10.c - Test records / reporting for work package 3 deliverable | Manufacturing Process CPA
5.10 | d | Test records / reporting for work package 4 deliverable | 5.10.d - Test records / reporting for work package 4 deliverable | Manufacturing Process CPA
5.10 | e | Evidence of methodology to define minimum defect size limitations for manufacturing QA / QC | 5.10.e - Evidence of methodology to define minimum defect size limitations for manufacturing QA / QC | Manufacturing Process CPA
5.10 | f | Third party approval of GE's internal QA process for composite pressure armour manufacture. | 5.10.f - Third party approval of GE's internal QA process for composite pressure armour manufacture. | Manufacturing Process CPA
5.11 | a | Design Premise & prediction of small to large scale testing | 5.11.a - Design Premise & prediction of small to large scale testing | Design Methodology & Tools
5.11 | b | Test records / reporting for work package 1 deliverable | 5.11.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.11 | c | Test records / reporting for work package 2 deliverable | 5.11.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.11 | d | Test records / reporting for work package 3 deliverable | 5.11.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.11 | e | Test records / reporting for work package 4 deliverable | 5.11.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.11 | f | Design tool calibration & simulation of actual field operating conditions | 5.11.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.12 | a | Design Premise & prediction of small to large scale testing | 5.12.a - Design Premise & prediction of small to large scale testing | Design Methodology & Tools
5.12 | b | Test records / reporting for work package 1 deliverable | 5.12.b - Test records / reporting for work package 1 deliverable | Mid & Full Scale Testing & Methodology
5.12 | c | Test records / reporting for work package 2 deliverable | 5.12.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.12 | d | Test records / reporting for work package 3 deliverable | 5.12.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.12 | e | Design tool calibration & simulation of actual field operating conditions | 5.12.e - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.13 | a | Design Premise & prediction of small to large scale testing | 5.13.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.13 | b | Test records / reporting for work package 1 deliverable | 5.13.b - Test records / reporting for work package 1 deliverable | Design Methodology & Tools
5.13 | c | Test records / reporting for work package 2 deliverable | 5.13.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.13 | d | Test records / reporting for work package 3 deliverable | 5.13.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.13 | e | Test records / reporting for work package 4 deliverable | 5.13.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.13 | f | Design tool calibration & simulation of actual field operating conditions | 5.13.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
6.4 | a |  | 6.4.a - | SC_CO2 Work Stream
6.5 | a |  | 6.5.a - | SC_CO2 Work Stream
6.1 | a |  | 6.1.a - | SC_CO2 Work Stream
6.3 | a |  | 6.3.a - | SC_CO2 Work Stream
9.11 | a | WP1 Modelling & test result prediction | 9.11.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.11 | b | Work package 2 Testing & Dissection | 9.11.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11 | c | Work package 3 Testing & Dissection | 9.11.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11 | d | Work package 4 Testing & Dissection | 9.11.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11 | e | Model calibration & validation - Based on WP 2,3 & 4 & dissection results | 9.11.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.21 | a | WP1 Modelling & test result prediction | 9.21.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.21 | b | Work package 2 Testing & Dissection | 9.21.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21 | c | Work package 3 Testing & Dissection | 9.21.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21 | d | Work package 4 Testing & Dissection | 9.21.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21 | e | Model calibration & validation - Based on WP 2,3 & 4 & dissection results | 9.21.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.31 | a | Modelling & test result prediction | 9.31.a - Modelling & test result prediction | End Termination Design Methodology & Tools
9.31 | b | Work package 1 Testing & Dissection | 9.31.b - Work package 1 Testing & Dissection | End Termination Design Methodology & Tools
9.31 | c | Work package 2 Testing & Dissection | 9.31.c - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.31 | d | Model calibration & validation - Based on WP 1 & 2 dissection results | 9.31.d - Model calibration & validation - Based on WP 1 & 2 dissection results | End Termination Design Methodology & Tools
9.32 | a | Work package 2 Testing & Dissection | 9.32.a - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.33 | a | Test records / reporting for work package 1 deliverable | 9.33.a - Test records / reporting for work package 1 deliverable | End Termination Design Methodology & Tools
9.33 | b | Test records / reporting for work package 2 deliverable | 9.33.b - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
9.33 | c | Test records / reporting for work package 3 deliverable | 9.33.c - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
9.41 | a | FMECA item 9.33 refers | 9.41.a - FMECA item 9.33 refers | Design Methodology & Tools
9.42 | a | WP1 Modelling & test result prediction | 9.42.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.42 | b | Work package 2 Testing & Dissection | 9.42.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42 | c | Work package 3 Testing & Dissection | 9.42.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42 | d | Work package 4 Testing & Dissection | 9.42.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42 | e | Model calibration & validation - Based on WP 2,3 & 4 & dissection results | 9.42.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.43 | a | WP1 Modelling & test result prediction | 9.43.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.43 | b | Work package 2 Testing & Dissection | 9.43.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.43 | c | Work package 3 Testing & Dissection | 9.43.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.43 | d | Model calibration & validation - Based on WP 2 & 3 & dissection results | 9.43.d - Model calibration & validation - Based on WP 2 & 3 & dissection results | End Termination Design Methodology & Tools

## Sheet2
Evidence Item | Category
1.1.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.1.b - Collapse modelling and methodology | Design Methodology & Tools
1.1.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.2.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.2.b - Collapse modelling and methodology | Design Methodology & Tools
1.2.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.3.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.3.b - Pipe Operating Guidelines | Design Methodology & Tools
1.3.c - Collapse modelling and methodology | Design Methodology & Tools
1.3.d - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.4.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.4.b - Collapse modelling and methodology | Design Methodology & Tools
1.4.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
1.5.a - Carcass Manufacturing Guidelines | Design Methodology & Tools
1.5.b - Collapse modelling and methodology | Design Methodology & Tools
1.5.c - Collapse - Experimental results and correlation of evidence | Mid & Full Scale Testing & Methodology
2.1.a - Local and global modelling combined with experimental correlation | Mid & Full Scale Testing & Methodology
2.1.b - Single layer program overview - DNV appraisal | Design Methodology & Tools
2.1.c - Barrier & Carcass Manufacturing guidelines | Design Methodology & Tools
2.2.a - Single layer program overview - DNV appraisal / Approval | Design Methodology & Tools
2.2.b - Manufacturing guidelines - API 4th edition compliance | Design Methodology & Tools
2.2.c - Local and global modelling combined with experimental correlation | Design Methodology & Tools
3.1.a - Single layer program overview - DNV appraisal / Approval | Design Methodology & Tools
3.1.b - Manufacturing guidelines - API 4th edition compliance | Design Methodology & Tools
3.1.c - Local and global modelling combined with experimental correlation - dynamic fatigue behaviour of 60512 material | Design Methodology & Tools
3.1.d - dynamic fatigue behaviour of 60512 material | Material Characterisation & Qualification
3.2.a - Polymer material data review - creep | Material Characterisation & Qualification
3.2.b - combined composite PA & barrier polymer creep data | Material Characterisation & Qualification
3.3.a - QC procedures - manufacturing & material supply specification | Design Methodology & Tools
3.3.b - Barrier layer extrusion parameters / guidelines | Design Methodology & Tools
3.4.a - RGD performance of composite barrier interface | Material Characterisation & Qualification
3.4.b - Polymer material RGD categorisation data review - Note to include historical RGD data (WSI 008) | Material Characterisation & Qualification
3.5.a - Combined Pressure & Bend | Mid & Full Scale Testing & Methodology
4.1.a - Standard flexible testing data+ refer to 5.1 and 5.3 | Material Characterisation & Qualification
4.2.a - RGD performance of composite barrier interface | Material Characterisation & Qualification
4.2.b - Prediction of barrier movement under the sealing mechanism (seal ring) and the establishment of criteria / limitations | Material Characterisation & Qualification
5.1.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.1.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.1.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.1.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.1.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.1.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.2.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.2.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.2.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.2.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.2.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.2.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.3.a - Refer to FMECA item 5.1 for evidence requirement | Design Methodology & Tools
5.4.a - Detailed testing program to be proposed to DNV & LIBRA for endorsement | Mid & Full Scale Testing & Methodology
5.4.b - Go / No-go decision gate proposed by GE for alternative test to PB spec. If no outcome is achieved the PB spec prevails | Mid & Full Scale Testing & Methodology
5.5.a - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.5.b - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.5.c - Thermal analysis (for end fitting) tool matched predictions before and after test. | Mid & Full Scale Testing & Methodology
5.6.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.6.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.6.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.6.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.6.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.6.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.7.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.7.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.7.c - Test records / reporting for work package 2 deliverable | Material Characterisation & Qualification
5.7.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.7.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.7.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.8.a - WP1 (Complete) | Material Characterisation & Qualification
5.8.a - WP2 (Q3 17) | Mid & Full Scale Testing & Methodology
5.9.a - Design Premise & prediction of small to mid scale testing | Mid & Full Scale Testing & Methodology
5.9.b - Test records / reporting for work package 1 deliverable | Mid & Full Scale Testing & Methodology
5.9.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.9.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.9.e - Design tool calibration & simulation of actual field operating conditions during thermal shock test | Design Methodology & Tools
5.10.a - Test records / reporting for work package 1 deliverable - Complete | Manufacturing Process CPA
5.10.b - Test records / reporting for work package 2 deliverable - Complete | Manufacturing Process CPA
5.10.c - Test records / reporting for work package 3 deliverable | Manufacturing Process CPA
5.10.d - Test records / reporting for work package 4 deliverable | Manufacturing Process CPA
5.10.e - Evidence of methodology to define minimum defect size limitations for manufacturing QA / QC | Manufacturing Process CPA
5.10.f - Third party approval of GE's internal QA process for composite pressure armour manufacture. | Manufacturing Process CPA
5.11.a - Design Premise & prediction of small to large scale testing | Design Methodology & Tools
5.11.b - Test records / reporting for work package 1 deliverable | Material Characterisation & Qualification
5.11.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.11.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.11.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.11.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.12.a - Design Premise & prediction of small to large scale testing | Design Methodology & Tools
5.12.b - Test records / reporting for work package 1 deliverable | Mid & Full Scale Testing & Methodology
5.12.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.12.d - Test records / reporting for work package 3 deliverable | Design Methodology & Tools
5.12.e - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
5.13.a - Design Premise & prediction of small to large scale testing | Mid & Full Scale Testing & Methodology
5.13.b - Test records / reporting for work package 1 deliverable | Design Methodology & Tools
5.13.c - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
5.13.d - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
5.13.e - Test records / reporting for work package 4 deliverable | Mid & Full Scale Testing & Methodology
5.13.f - Design tool calibration & simulation of actual field operating conditions | Design Methodology & Tools
6.4.a - | SC_CO2 Work Stream
6.5.a - | SC_CO2 Work Stream
6.1.a - | SC_CO2 Work Stream
6.3.a - | SC_CO2 Work Stream
9.11.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.11.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.11.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.21.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.21.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.21.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.31.a - Modelling & test result prediction | End Termination Design Methodology & Tools
9.31.b - Work package 1 Testing & Dissection | End Termination Design Methodology & Tools
9.31.c - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.31.d - Model calibration & validation - Based on WP 1 & 2 dissection results | End Termination Design Methodology & Tools
9.32.a - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.33.a - Test records / reporting for work package 1 deliverable | End Termination Design Methodology & Tools
9.33.b - Test records / reporting for work package 2 deliverable | Mid & Full Scale Testing & Methodology
9.33.c - Test records / reporting for work package 3 deliverable | Mid & Full Scale Testing & Methodology
9.41.a - FMECA item 9.33 refers | Design Methodology & Tools
9.42.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.42.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42.d - Work package 4 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.42.e - Model calibration & validation - Based on WP 2,3 & 4 & dissection results | End Termination Design Methodology & Tools
9.43.a - WP1 Modelling & test result prediction | End Termination Design Methodology & Tools
9.43.b - Work package 2 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.43.c - Work package 3 Testing & Dissection | Mid & Full Scale Testing & Methodology
9.43.d - Model calibration & validation - Based on WP 2 & 3 & dissection results | End Termination Design Methodology & Tools

## data_cache (hidden)
Warning! Do not edit or delete this worksheet! You may hide this worksheet, and it will no longer appear after the February 2016 Office update is installed.
Column1 | Column2 | Column1
FMECA_Task_ | 0 | {"@odata.etag":"W/\"JzIxMzMyMTU1NDMn\"","PrimaryId":"000040","WP":"","FMECA_Item":"1.1","Design_parameter":"Collapse loading\n\nHandling & transportation\n\nDetermination of manufacturing tolerances for the carcass profile","Main_issue":"Carcass layer or interlock (due to incorrect profile)​","Evidence_Item":"a","Evidence_Item_Description":"Manufacturing Guidelines","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE3MTMwMzg5Jw==\"","PrimaryId":"000041","WP":"","FMECA_Item":"1.1","Design_parameter":"Collapse loading\n\nHandling & transportation\n\nDetermination of manufacturing tolerances for the carcass profile","Main_issue":"Carcass layer or interlock (due to incorrect profile)​","Evidence_Item":"b","Evidence_Item_Description":"Collapse modelling and methodology","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzgyNjQzODcxOCc=\"","PrimaryId":"000042","WP":"","FMECA_Item":"1.1","Design_parameter":"Collapse loading\n\nHandling & transportation\n\nDetermination of manufacturing tolerances for the carcass profile","Main_issue":"Carcass layer or interlock (due to incorrect profile)​","Evidence_Item":"c","Evidence_Item_Description":"Experimental results and correlation of evidence","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzY5Mzc1OTc2Jw==\"","PrimaryId":"000043","WP":"","FMECA_Item":"1.2","Design_parameter":"Collapse loading.\n\nHandling & transportation.","Main_issue":"Carcass layer or interlock (due to cracked carcass)","Evidence_Item":"a","Evidence_Item_Description":"Manufacturing Guidelines\nCollapse modelling and methodology\nExperimental results and correlation of evidence","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzExODY4NjAwMic=\"","PrimaryId":"000044","WP":"","FMECA_Item":"1.3","Design_parameter":"Collapse loading\n\nHandling & transportation & Installation\n\nTDP compression","Main_issue":"Loss of interlock (due to out of spec carcass)","Evidence_Item":"a","Evidence_Item_Description":"Manufacturing Guidelines\nOperating Guidelines\nCollapse modelling and methodology\nExperimental results and correlation of evidence","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"Jzg0MTc0NjcxNSc=\"","PrimaryId":"000045","WP":"","FMECA_Item":"1.4","Design_parameter":"Collapse loading\n\nHandling & transportation\n\nTDP compression","Main_issue":"Carcass layer or interlock failure (due to weld issue)","Evidence_Item":"a","Evidence_Item_Description":"Manufacturing Guidelines\nCollapse modelling and methodology\nExperimental results and correlation of evidence","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE3MDc1MzIzODUn\"","PrimaryId":"000046","WP":"","FMECA_Item":"1.5","Design_parameter":"Collapse loading\n\nHandling & transportation\n\nTDP compression (collapse under combined bending, dynamic compression and external pressure)","Main_issue":"Carcass layer or interlock failure (due to non uniform loading)","Evidence_Item":"a","Evidence_Item_Description":"Manufacturing Guidelines\nCollapse modelling and methodology\nExperimental results and correlation of evidence","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"Jzc3Nzg2ODU2Myc=\"","PrimaryId":"000047","WP":"","FMECA_Item":"2.1","Design_parameter":"Transient and Combined cyclic pressure, temperature and axial stress\n\nDry and flooded annulus","Main_issue":"Carcass barrier interface sealing and slippage","Evidence_Item":"a","Evidence_Item_Description":"Single layer program overview - DNV appraisal\nManufacturing guidelines\nLocal and global modelling combined with experimental correlation","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzM5NDIxNTQ1MSc=\"","PrimaryId":"000048","WP":"","FMECA_Item":"2.2","Design_parameter":"Transient and Combined cyclic pressure, temperature and axial stress\n\nDry and flooded annulus","Main_issue":"Controlling carcass nub ( full ingress scenario) and related behaviour","Evidence_Item":"a","Evidence_Item_Description":"Single layer program overview - DNV appraisal\nManufacturing guidelines - API 4th edition compliance\nLocal and global modelling combined with experimental correlation","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE3NjUxMDg4NjYn\"","PrimaryId":"000049","WP":"","FMECA_Item":"3.1","Design_parameter":"Annulus, bore fluid conditions (evolution of material's properties, i.e., ageing, micro voids etc.)\nNub (tip) geometry and tolerances\nOperational conditions such as pressure, thermal, RGD and bending cycling","Main_issue":"Controlling carcass nub ( high KT scenario) and related behaviour","Evidence_Item":"a","Evidence_Item_Description":"Single layer program overview - DNV appraisal\nManufacturing guidelines - API 4th edition compliance\nLocal and global modelling combined with experimental correlation - dynamic fatigue behaviour of 60512 material","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzExNTAyMDY4NDQn\"","PrimaryId":"000050","WP":"","FMECA_Item":"3.2","Design_parameter":"Long term performance of barrier under creep loading","Main_issue":"Creep/stress rupture during storage and operation","Evidence_Item":"a","Evidence_Item_Description":"Polymer material data review - creep\nFMECA item 5.1 refers - combined composite PA & barrier polymer creep data","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzIwMzgxMjU2MDgn\"","PrimaryId":"000051","WP":"","FMECA_Item":"3.3","Design_parameter":"Inclusion acceptance criteria / or product (barrier) quality & performance thresholds","Main_issue":"inclusion or moisture in barrier layer","Evidence_Item":"a","Evidence_Item_Description":"QC procedures - manufacturing & material supply specification\nBarrier layer extrusion parameters / guidelines","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE0ODE5Mzc0MDUn\"","PrimaryId":"000052","WP":"","FMECA_Item":"3.4","Design_parameter":"Start up and Shut Down\n\nCyclic fatigue","Main_issue":"Thermal stress in barrier layer","Evidence_Item":"a","Evidence_Item_Description":"FMECA Item 5.4 - RGD performance of composite barrier interface\nPolymer material RGD categorisation data review - Note to include historical RGD data (WSI 008)","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5Nzg0ODQ3MjUn\"","PrimaryId":"000053","WP":"","FMECA_Item":"3.5","Design_parameter":"Pressure loading\nDynamic vessel movement\nPipe handling or interaction with Sea bed\nPolymer layer Kt value guidelines / limitation refer -\ndesign methodology - Kt analysis, ageing (creep) and load case calculation for service life survival","Main_issue":"Combined pressure and bend","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5NzY0MjIxOTgn\"","PrimaryId":"000054","WP":"","FMECA_Item":"4.1","Design_parameter":"Reel storage\n\nTime dependent stress and creep performance","Main_issue":"Long term storage on reel/ Stress rupture","Evidence_Item":"a","Evidence_Item_Description":"Standard flexible testing data+ refer to 5.1 and 5.3","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"Jzg1MTk4MTQxMyc=\"","PrimaryId":"000055","WP":"","FMECA_Item":"4.2","Design_parameter":"Start up and shut down operation including RGD\n\nChanges in pressure during operation\n\nDelamination due to riser bending cycling and differential stiffness between the pressure armour and the barrier\n\nAccumulated fluids at the interface from barrier","Main_issue":"Rapid gas decompression effect on polymer layer","Evidence_Item":"a","Evidence_Item_Description":"FMECA Item 5.4 - RGD performance of composite barrier interface\nPrediction of barrier movement under the sealing mechanism (seal ring) and the establishment of criteria / limitations","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzQ4MDkxNjc3Nyc=\"","PrimaryId":"000056","WP":"","FMECA_Item":"5.1","Design_parameter":"Stress rupture / Static fatigue","Main_issue":"Creep/stress rupture during storage","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverable (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzMxMTQ1MjU2Mic=\"","PrimaryId":"000057","WP":"","FMECA_Item":"5.2","Design_parameter":"Exceeding MBR that results in excessive strain and pipe failure","Main_issue":"Normal and excessive Bending strain","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverable (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzcyMzU1MTYxOCc=\"","PrimaryId":"000058","WP":"","FMECA_Item":"5.3","Design_parameter":"Storage Bend Radius\n\nReeling time and rates\n\nApplied tension and twist reference (effect on EF)","Main_issue":"Long term storage on reel/ Stress rupture","Evidence_Item":"a","Evidence_Item_Description":"Refer to FMECA item 5.1 for evidence requirement","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzM0MDc5ODg0Myc=\"","PrimaryId":"000059","WP":"","FMECA_Item":"5.4","Design_parameter":"Delta P (e.g. due to RGD)\n\nRate of change\n\nTemperature\n\nGas composition/ co2 and High Co2 content / supercritical under pressure","Main_issue":"Rapid gas decompression","Evidence_Item":"a","Evidence_Item_Description":"Detailed testing program to be proposed to DNV & LIBRA for endorsement\nGo / No-go decision gate proposed by GE for alternative test to PB spec. If no outcome is achieved the PB spec prevails.","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzY0NjIzOTc4MCc=\"","PrimaryId":"000060","WP":"","FMECA_Item":"5.5","Design_parameter":"Low temperature during Installation","Main_issue":"Low temperature brittle cracking","Evidence_Item":"a","Evidence_Item_Description":"WP1 to WP2 & Thermal analysis (for end fitting) tool matched predictions before and after test.","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE4NDA2MjE3Nzkn\"","PrimaryId":"000061","WP":"","FMECA_Item":"5.6","Design_parameter":"Pipe Fatigue (static and dynamic) during reeling and installation","Main_issue":"cyclical fatigue (high strain)","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5NTUwNjkzNTAn\"","PrimaryId":"000062","WP":"","FMECA_Item":"5.7","Design_parameter":"Pipe Fatigue and Life of riser during operation. With reference to operational fluids and change of use WAG from Libra spec.","Main_issue":"cyclical fatigue (Low strain)","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzY4MzMzMjQwOSc=\"","PrimaryId":"000063","WP":"","FMECA_Item":"5.8","Design_parameter":"Temperature changes during operation effecting CPA (thermal history due to Manufacturing process)","Main_issue":"Thermal stress during Manufacturing","Evidence_Item":"a","Evidence_Item_Description":"WP1 (Complete) to WP2 (Q3 17)","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzEyOTQyMjgyOTMn\"","PrimaryId":"000064","WP":"","FMECA_Item":"5.9","Design_parameter":"Temperature changes during operation effecting CPA (thermal history due to operating parameters)","Main_issue":"Thermal shock during operation (mainly EF)","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to mid scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 3)\nDesign tool calibration & simulation of actual field operating conditions during thermal shock test","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzUwOTY0Nzc3MSc=\"","PrimaryId":"000065","WP":"","FMECA_Item":"5.10","Design_parameter":"Product acceptance criteria related to inclusion / voids/ moisture etc.","Main_issue":"Defects, inclusion and flaws","Evidence_Item":"a","Evidence_Item_Description":"WP 1 & 2 (Complete - WP 3 & 4 to be completed\nEvidence of methodology to define minimum defect size limitations for manufacturing QA / QC\nThird party approval of GE's internal QA process for composite pressure armour manufacture.","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzIzNjA0ODUxJw==\"","PrimaryId":"000066","WP":"","FMECA_Item":"5.11","Design_parameter":"Compressive loads and cyclical bending due to:\nTensioner crushing during installation (including time dependent effect)\nRegular operating TDP due to bend collapse stress field\nCyclical compressive axial loads due to vessel motion (tensile)","Main_issue":"1. Cyclical compression loads \n2. Crush and slippage resistance of layers","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE1NzIzMDA2ODIn\"","PrimaryId":"000067","WP":"","FMECA_Item":"5.12","Design_parameter":"Pressure loading\n\nDynamic vessel movement\n\nPipe handling or interaction with Sea bed","Main_issue":"Combined pressure and bend loading","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 3)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5NzIwMjQ0OTcn\"","PrimaryId":"000068","WP":"","FMECA_Item":"5.13","Design_parameter":"Operational Offshore dynamic conditions and OBR (Operating bending Radius), MBR (Minimum Bending Radius)\n\nEnvironmental Conditions\n\nResidual Strength of the CPA after the failure of a pre-determined agreed number of wires (3 TBC) in the tensile layer","Main_issue":"Bend fatigue including twist / shear \neffect of tension on interface layers","Evidence_Item":"a","Evidence_Item_Description":"Design Premise & prediction of small to large scale testing\nTest records / reporting for referenced work package deliverables (WP 1 to 4)\nDesign tool calibration & simulation of actual field operating conditions","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzYwNTU2MjgzNyc=\"","PrimaryId":"000069","WP":"","FMECA_Item":"6.4","Design_parameter":"Tensile capacity","Main_issue":"","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE1MzEwNzA5NTIn\"","PrimaryId":"000070","WP":"","FMECA_Item":"6.5","Design_parameter":"Tensile capacity","Main_issue":"","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzUwMjMwNDQwMic=\"","PrimaryId":"000071","WP":"","FMECA_Item":"6.1","Design_parameter":"Incorrect Permeation model, material selection\nIngress of sea water from ambient external env due to breach of outer sheath or leakage at ports and sealing at End fitting or vent valve \nCondensation of water from internal fluids\nStress induced due intern","Main_issue":"","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5NjE0NDYwMTgn\"","PrimaryId":"000072","WP":"","FMECA_Item":"6.3","Design_parameter":"Tensile capacity","Main_issue":"","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE0NTkxMjA2NjAn\"","PrimaryId":"000073","WP":"","FMECA_Item":"9.11","Design_parameter":"Loads transferred from the pipe layers to the carcass termination, including own weight (self weight)\n\nContact Pressure from the sealing system over the Seal contact area (resulting in excessive deformation of the carcass inwards)\n\nSystem to anchor the c","Main_issue":"Carcass self weight and termination","Evidence_Item":"a","Evidence_Item_Description":"WP1 Modelling & test result prediction\nWP 2,3 & 4 Testing & dissection (mid and full scale )\nModel calibration & validation - Based on WP 2,3 & 4 & dissection results","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzIwMzkxNTQ0Mjgn\"","PrimaryId":"000074","WP":"","FMECA_Item":"9.21","Design_parameter":"Axial strain, swaging and effect on pressure seal","Main_issue":"Problems with Flexwear and related sleeve","Evidence_Item":"a","Evidence_Item_Description":"Should dual layer design be included in future product qualification, the following points will apply:\nWP1 Modelling & test result prediction\nWP 2,3 & 4 Testing & dissection (mid and full scale )\nModel calibration & validation - Based on WP 2,3 & 4 & dis","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzE5MTIxODg5MzMn\"","PrimaryId":"000075","WP":"","FMECA_Item":"9.31","Design_parameter":"Swaging and effect on pressure seal\n\nSwaging assembly component manufacturing and assembly tolerances","Main_issue":"Problems with swaging with Barrier layer","Evidence_Item":"a","Evidence_Item_Description":"Modelling & test result prediction\nWP 1,2 Testing & dissection (mid - scale)\nModel calibration & validation - Based on WP 1 & 2 dissection results","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzIwODI5NjE5NTUn\"","PrimaryId":"000076","WP":"","FMECA_Item":"9.32","Design_parameter":"Local heating during further layer End fitting terminations","Main_issue":"Epoxy curing during EF assembly","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzEyOTg3MTM4MDcn\"","PrimaryId":"000077","WP":"","FMECA_Item":"9.33","Design_parameter":"Specific to sealing system (ring) contact with barrier:\nEffect of thermal and pressure cycling (under weight of composite liner and carcass)\nCyclic axial component due to tensile loading transfer to EF\nBarrier sealing degradation to exposure to fluid \nSt","Main_issue":"Self weight of carcass+ polymer on Liner seal \n\neffect of Axial strain","Evidence_Item":"a","Evidence_Item_Description":"","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzY1OTYyNzExOCc=\"","PrimaryId":"000078","WP":"","FMECA_Item":"9.41","Design_parameter":"thermal stress resulting in movement of the seal \nRefer to 9.33 for details of this failure mode","Main_issue":"Same as above, but study the effect of thermal stress","Evidence_Item":"a","Evidence_Item_Description":"FMECA item 9.33 refers","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"JzU4MDg1MDMwNic=\"","PrimaryId":"000079","WP":"","FMECA_Item":"9.42","Design_parameter":"Pressure and cyclical loads transfer generating additional tension; \n\nThermal cycling; \n\nComponent of own weight of composite pressure armour+liner+carcass not transferred to the tensile armour; \n\nGeneral comment: A hundred percent contact pressure must b","Main_issue":"Self weight of carcass+ polymer + bonded CPA \nthermal stress\neffect of Axial strain","Evidence_Item":"a","Evidence_Item_Description":"WP1 Modelling & test result prediction\nWP 2,3 & 4 Testing & dissection (mid and full scale )\nModel calibration & validation - Based on WP 2,3 & 4 & dissection results","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}
{"@odata.etag":"W/\"Jzg0NzE3NTAwNyc=\"","PrimaryId":"000080","WP":"","FMECA_Item":"9.43","Design_parameter":"Stress concentration as described in section 8.5 of DNVGL-RP-F119:2015. - The composite pressure armour interaction from the termination point through to the free pipe body should not result in stress concentrations created by the ballooning effect.\n\nGE","Main_issue":"effect of Axial stress& twist on tensile armour anchoring in epoxy wedge and CPA","Evidence_Item":"a","Evidence_Item_Description":"WP1 Modelling & test result prediction\nWP 2 & 3 Testing & dissection (full scale )\nModel calibration & validation - Based on WP 2 & 3 & dissection results","Due_date":"1900-01-01T12:00:00Z","Statud":null,"Owner_GivenName":null,"Owner_MiddleName":null,"Owner_Surname":null}