# FIDIC® Conditions of Contract for

# EPC/TURNKEY PROJECTS

Second Edition 2017

ISBN 978-2-88432-083-2

Reprinted 2022 with amendments

Particular Conditions - Part B Special Provisions

FEDERATION INTERNATIONALE DES INGENIEURS-CONSEILS INTERNATIONAL FEDERATION OF CONSULTING ENGINEERS INTERNATIONALE VEREINIGUNG BERATENDER INGENIEURE FEDERACION INTERNACIONAL DE INGENIEROS CONSULTORES

Particular Conditions Part B – Special Provisions

# INTRODUCTION

The terms of the Conditions of Contract for EPC/Turnkey Projects have been prepared by the Fédération Internationale des Ingénieurs-Conseils (FIDIC) and are recommended where one entity takes total responsibility for an engineering project, including design, manufacture, delivery and installation of Plant, and for the design and execution of building or engineering works, and where tenders are invited on an international basis.

Modifications to the General Conditions may well be required to account for local legal requirements, particularly if they are to be used on domestic contracts.

Turnkey projects generally require some negotiation between the parties during the tender stage of the project. Having studied the variety of options offered by tenderers, the Employer may consider it essential to meet and discuss with them the technical and commercial options which the Employer considers preferable. Under the usual arrangements for this type of contract, the Contractor carries out the Engineering, Procurement and Construction, and provides a fully-equipped facility, ready for operation (at the “turn of the key”).

These Conditions allow for the possibility that the Employer may include (in the Employer’s Requirements) an outline design for the Works, but they are not intended for use where the Contractor is to construct the Works in accordance with a detailed design by the Employer. In this latter case, it is recommended that the Employer consider using FIDIC’s Conditions of Contract for Construction, Second Edition 2017.

The guidance hereafter is intended to assist drafters of the Special Provisions (Particular Conditions – Part B) by giving options for various sub-clauses where appropriate. In some cases example wording is included between lines, while in other instances only an aide-memoire is given.

FIDIC strongly recommends that the Employer, the Contractor and all drafters of the Special Provisions take all due regard of the five FIDIC Golden Principles:

GP1: The duties, rights, obligations, roles and responsibilities of all the Contract Participants must be generally as implied in the General Conditions, and appropriate to the requirements of the project.

GP2:  The Particular Conditions must be drafted clearly and unambiguously.

GP3: The Particular Conditions must not change the balance of risk/reward allocation provided for in the General Conditions.

GP4:  All time periods specified in the Contract for Contract Participants to perform their obligations must be of reasonable duration.

GP5: Unless there is a conflict with the governing law of the Contract, all formal disputes must be referred to a Dispute Avoidance/Adjudication Board (or a Dispute Adjudication Board, if applicable) for a provisionally binding decision as a condition precedent to arbitration.

These FIDIC golden principles are described and explained in the publication FIDIC’s Golden Principles (https://fidic.org/books/fidic-golden-principles-2019†), and are necessary to ensure that modifications to the General Conditions:

- are limited to those necessary for the particular features of the Site and the project, and necessary to comply with the applicable law; and

- the Contract remains recognisable as a FIDIC contract.

Before incorporating any new or changed sub-clauses, the wording must be carefully checked to ensure that it is wholly suitable for the particular circumstances. Unless it is considered suitable, example wording should be amended before use.

Where any amendments or additions are made to the General Conditions, great care must be taken to ensure that the wording does not unintentionally alter the meaning of other clauses in the Conditions of Contract, does not inadvertently change the obligations assigned to the Parties or the balance of risks shared between them and/or does not create any ambiguity or misunderstanding in the rest of the Contract documents.

Each time period stated in the General Conditions is what FIDIC believes is reasonable, realistic and achievable in the context of the obligation to which it refers, and reflects the appropriate balance between the interests of the Party required to perform the obligation, and the interests of the other Party whose rights are dependent on the performance of that obligation. If consideration is given to changing any such stated time period in the Special Provisions (Particular Conditions – Part B), care should be taken to ensure that the amended time period remains reasonable, realistic and achievable in the particular circumstances.

There are a number of Sub-Clauses in the General Conditions which require data to be provided by the Employer and/or the Contractor and inserted into the Contract Data (Particular Conditions – Part A). However, there are no Sub-Clauses in the General Conditions which require data or information to be included in the Special Provisions (Particular Conditions – Part B).

Provisions found in the Contract documents under Special Provisions (Particular Conditions – Part B) indicate that the General Conditions have been amended or supplemented.

In describing the Conditions of Contract in the tender documents, the following text can be used:

“The Conditions of Contract comprise the “General Conditions”, which form part of the “Conditions of Contract for EPC/Turnkey Projects” Second Edition 2017, reprinted 2022 with amendments, published by the Fédération Internationale des Ingénieurs-Conseils (FIDIC), the Contract Data (Particular Conditions – Part A) and the following “Special Provisions” (Particular Conditions – Part B), which include amendments and additions to such General Conditions.”

The provisions of the Special Provisions (Particular Conditions – Part B) will always over-rule and supersede the equivalent provisions in the General Conditions, and it is important that the changes are easily identifiable by using the same clause numbers and titles as appear in the General Conditions. Furthermore, it is necessary to add a statement in the tender documents for a contract that:

“The provisions to be found in the Special Provisions (Particular Conditions – Part B) take precedence over the equivalent provisions found under the same Sub-Clause number(s) in the General Conditions, and the provisions of the Contract Data (Particular Conditions – Part A) take precedence over the Special Provisions (Particular Conditions – Part B).”

† Please Note: all web links referred to in these guidance notes are up-to-date as of the date of this publication but it is recommended that users of these guidance notes check online, at the time that they wish to reference the relevant document, for the most up-to-date version of the document.

# NOTES ON THE PREPARATION OF TENDER DOCUMENTS

When preparing the tender documents and planning the tender process, Employers should read the publication FIDIC Procurement Procedures Guide 1st edition 2011 (https://fidic.org/books/ fidic-procurement-procedures-guide-1st-ed-2011†) which presents a systematic approach to the procurement of engineering and building works for projects of all sizes and complexity, and gives invaluable help and advice on the contents of the tender documents, and the procedures for receiving and evaluating tenders. This publication provides internationally acceptable, comprehensive, best practice procedures designed to increase the probability of receiving responsive, clear and competitive tenders using FIDIC forms of contract. FIDIC intends to update the FIDIC Procurement Procedures Guide (planned for publication at a later date) to make specific reference to these Conditions of Contract for EPC/Turnkey Projects, Second Edition 2017.

The tender documents should be prepared by suitably qualified engineers who are familiar with the technical aspects of the required works and the particular requirements and contractual provisions of a design-build project. Furthermore, a review by suitably-qualified lawyers is advisable.

The tender documents issued to tenderers should normally include the following:

- Letter of invitation to tender

- Instructions to Tenderers (including advice on any matters which the Employer wishes tenderers to include in their Tenders but which do not form part of the Employer’s Requirements)

- Form of Letter of Tender and required appendices (if any)

- Conditions of Contract: General and Particular

- General information and data

- Technical information and data (including the data referred to in Sub-Clause 2.5 [ Site Data and Items of Reference ] of the General Conditions)

- the Employer’s Requirements

- Schedules (and perhaps drawings of outline design) from the Employer

- details of schedules and drawings and other information required from tenderers

- required forms of agreement, securities and guarantees.

The publication FIDIC Procurement Procedures Guide referred to above provides useful guidance as to the content and format of each of the above.

For this type of contract where the Works are normally valued on a lump sum basis, the Schedules may include a Schedule of Payments (as referred to under Sub-Clause 14.4 [ Schedule of Payments ] in the General Conditions). A Daywork Schedule may also be necessary to cover minor works to be executed at cost. In addition, each of the tenderers should receive the data referred to in Sub-Clause 2.5 [ Site Data and Items of Reference ], and the lnstructions to Tenderers should advise them of any special matters which the Employer wishes them to take into account when pricing the Works but which are not to form part of the Contract.

When the Contract Agreement is signed by the Employer and the Contractor, the Contract (which then comes into full force and effect) includes the completed Schedules.

The Employer’s Requirements should specify the particular requirements for the completed Works, including functional requirements, quality and scope. If the Contractor is required to supply certain items, such as consumables, these should be listed in a Schedule. Drafters of the Employer’s Requirements must remember that if any matters are not referred to or covered, the Contractor may well be relieved of any responsibility in respect of such matters.

The following Sub-Clauses make express reference to matters to be included in the Employer’s Requirements. However, it may also be necessary under other Sub-Clauses for the Employer to give specific information in the Employer’s Requirements (for example, under Sub-Clause 7.2 [ Samples ]).

| 1.8 | Care and Supply of Documents |
| --- | --- |
| 1.12 | Compliance with Laws |
| 2.1 | Right of Access to the Site |
| 2.5 | Site Data and Items of Reference |
| 2.6 | Employer-Supplied Materials and Employer’s Equipment |
| 4.1 | Contractor’s General Obligations |
| 4.5 | Nominated Subcontractors |
| 4.6 | Co-operation |
| 4.8 | Health and Safety Obligations |
| 4.9 | Quality Management and Compliance Verification Systems |
| 4.16 | Transport of Goods |
| 4.18 | Protection of the Environment |
| 4.19 | Temporary Utilities |
| 4.20 | Progress Reports |
| 5.1 | General Design Obligations |
| 5.2 | Contractor’s Documents |
| 5.4 | Technical Standards and Regulations |
| 5.5 | Training |
| 5.6 | As-Built Records |
| 5.7 | Operation and Maintenance Manuals |
| 6.1 | Engagement of Staff and Labour |
| 6.6 | Facilities for Staff and Labour |
| 6.7 | Health and Safety of Personnel |
| 6.12 | Key Personnel |
| 7.3 | Inspection |
| 7.4 | Testing by the Contractor |
| 7.8 | Royalties |
| 8.3 | Programme |
| 9.1 | Contractor’s Obligations |
| 10.2 | Taking Over of Parts of the Works |
| 11.11 | Clearance of Site |
| 12.1 | Procedure for Tests after Completion |

Many Sub-Clauses in the General Conditions make reference to data being contained in the Contract Data (Particular Conditions – Part A). This data must be provided in the tender documents, and these Conditions of Contract assume that all such data will be provided by the Employer, except as expressly noted in the example form of Contract Data included in this publication. If the Employer requires tenderers to provide any of the other information required in the Contract Data, the tender documents must make this clear.

If the Employer requires tenderers to provide additional data or information, a convenient way of doing this is to provide a suitably worded questionnaire with the tender documents.

The Instructions to Tenderers may need to specify any constraints on the completion of the Contract Data and/or Schedules, and/or specify the extent of other information which each tenderer is to include with his/her Tender. If each tenderer is to produce a tender security and/or a parent company guarantee, these requirements should be included in the Instructions to Tenderers: example forms are included at the end of this publication.

The Instructions to Tenderers may require the tenderer to provide information on the matters referred to in some or all of the following Sub-Clauses:

4.3	Contractor’s Representative

6.12	Key Personnel

19	Insurance

It is important for the Parties to understand which of the documents included in the tender dossier, and which of the documents submitted by tenderers, will form part of the Contract and therefore have continuing effect. For example, the Instructions to Tenderers are not, by definition, a part of the Contract. They are simply instructions and information on the preparation and submission of the tender, and they should not contain anything of a binding or contractual nature.

In many EPC/Turnkey Projects the contract includes fixtures, fittings and equipment and other similar items. In this case, full consideration should be given to including in the Employer’s Requirements the detailed requirements for these items, such as the extent to which the Works are to be fully equipped, ready for operation, with spare parts and consumables provided for operation (for a specified period), typically by the Employer. If the Contractor is required to operate the Works, either for a few months’ trial operation under sub-paragraph (c) of Sub-Clause 9.1 [ Contractor’s Obligations ] or for some years’ operation, this must also be specified and detailed in the Employer’s Requirements.

If tenderers are required to carry out any preliminary design or study for their proposals, the Employer should bear in mind that tenderers are understandably often reluctant to incur great expense in the preparation of tender designs. Therefore, when preparing the Instructions to Tenderers, thought should be given as to the extent of detail which tenderers can realistically be expected to prepare and include in their proposals. The extent of detail required should be clearly described in the Instructions to Tenderers (it should be noted that there can be no description in the documents which will later constitute the Contract, which only comes into full force and effect when the Contract Agreement has been signed by the Contractor and the Employer). Employers should also consider remunerating tenderers if, in order to provide a responsive Tender, they have to undertake studies or carry out preliminary design work.

Finally, when planning the overall programme for the project, Employers must remember to allow a realistic time for:

- tenderers to inspect the Site, to carry out any survey and sub-surface investigations, to obtain all necessary information as to risks, contingencies and other circumstances which may influence or affect the Works (as stated under Sub-Clause 4.12 [ Unforeseeable Difficulties ]), and to scrutinise the Employer’s Requirements (as stated under Sub-Clause 5.1 [ General Design Obligations ]);

- tenderers to prepare and submit a responsive Tender (avoiding time that is either too short which can reduce competition and result in inadequate submittals, or too long which can be wasteful to all parties involved); and

- the review and evaluation of tenders and the award of the Contract to the successful tenderer. This will be the minimum time which tenderers should be asked to hold their tenders valid and open to acceptance.

# NOTES ON THE PREPARATION OF SPECIAL PROVISIONS

It is very important that Employers (and all drafters of the Special Provisions) work with their professional advisers to review specific terminology in the General Conditions for compliance and consistency with accepted practice in the legal jurisdiction they are operating in.

For example:

- under a number of legal systems (notably in some common law jurisdictions) the term “gross negligence” has no clear definition and, as such, is often avoided in legal documents; and

- under English law, the term “indemnity” or “indemnify” has a specific meaning, entitling the indemnified party to recover certain losses that may not otherwise be recoverable at law. For example, a Contractor’s indemnity may be construed to permit the Employer to recover losses or damages that might otherwise be considered indirect or consequential, whereas for some events which may arise both Parties’ losses or damages are intended to be limited by Sub-Clause 1.14 [ Limitation of Liability ] to direct damages only.

The following references and examples show some of the Sub-Clauses in the General Conditions which may need amending to suit the needs of the project or the requirements of the Employer. The selected Sub-Clauses and the example wording are included as examples only. They also include, as an aide-memoire, references to other documents such as the Employer’s Requirements and the Contract Data, where particular issues may need to be addressed.

The selected Sub-Clauses do not necessarily require changing and the example wording may not suit the needs of a particular project or Employer. It is the responsibility of the drafter of the Special Provisions to ensure that the selection of the Sub-Clauses and the choice of wording is appropriate to the project concerned.

Furthermore, there may be other Sub-Clauses, not mentioned below, which need to be amended. Great care must be taken when amending the wording of Sub-Clauses from the General Conditions, or adding new provisions, to ensure that the balance of obligations and rights of the Parties are not unintentionally compromised.

# Clause 1	General Provisions

## Sub-Clause 1.1	Definitions

The opening words of Sub-Clause 1.1 mean that the definitions apply, not only to the Conditions of Contract, but to all the documents of the Contract. Therefore, the Employer should take care (particularly when drafting the Employer’s Requirements) and the Contractor should take care (particularly when drafting the documents to be submitted with the Tender) to use terms in accordance with those as defined in the definitions.

The defined term “Site”, under Sub-Clause 1.1.67, is used for a number of different purposes in the General Conditions (for example: insurances and security) and so, if it is anticipated that any item(s) of equipment, Plant, Materials and Temporary Works are to be located or stored in places other than where the Permanent Works are to be executed, it is recommended that consideration be given to specifying such places in the Contract (by the Employer in the Employer’s Requirements and/or by the Contractor in documents to be submitted with the Tender).

In general, changes should not be made to the definitions as this could have serious consequences on the interpretation of the documents of the Contract, particularly the Conditions of Contract.

However, there are limited circumstances where it may be desirable to amend some of the definitions. For example:

1.1.2	the Base Date could be defined as a particular calendar date

1.1.37 one particular Foreign Currency may be required

1.1.44 a different currency may be required to be the contract Local Currency

Also, some of the defined terms in the General Conditions may not be appropriate and may need changing or developing.

For example, if the extent of the Site crosses the border between two countries, it is recommended that consideration be given to the following changes:

EXAMPLE	1.1.18

“ “Country” means either xxxxx or yyyyy depending on the location to which the reference will apply.”

EXAMPLE	1.1.44

“ “Local Currency” means the currency of (insert name of Country) or (insert name of Country).”

If it is necessary to introduce new terminology into the text of the Special Provisions, each term should be carefully and properly defined, using a clear Sub-Clause numbering system for the new/additional defined terms. It is recommended that the numbering of new definitions does not interfere with the numbering as originally included in the General Conditions. For example:

EXAMPLE	New definition 1.1.x

“ “Safety Regulations” means the Employer’s safety regulations existing on the Site which the Contractor is required to follow.”

In some jurisdictions, it may be advisable to add additional definitions to clarify certain terms/ expressions which appear in the General Conditons but are not defined. A typical example might be:

EXAMPLE	New definition 1.1.x

“ “Gross Negligence” means any act or omission of a party which is contrary to the most elementary rules of diligence which a conscientious employer or contractor would have observed in similar circumstances, and/or which show serious reckless disregard for the consequences of such act or omission. It involves materially more want of care than mere inadvertence or simple negligence.”

## Sub-Clause 1.2	Interpretation

In relation to the meaning of “consent” under sub-paragraph (g), it should be noted that this does not mean “approve” or “approval” which, under some legal jurisdictions, may be interpreted as accepting or acceptance that the requested matter is wholly satisfactory – following which the requesting party may no longer have any responsibility or liability for it.

## Sub-Clause 1.3	Notices and Other Communications

If Notices are only to be given in paper format by post, then consideration may be given to increasing the particular timescales for Notices in the Conditions of Contract to allow extra days for the Notice to be delivered to the recipient.

## Sub-Clause 1.5	Priority of Documents

An order of precedence is usually necessary, in case a conflict is subsequently found between the documents of the Contract.

If the Employer’s Requirements are to comprise a number of documents, it may be useful to amend sub-paragraph (e) of this Sub-Clause 1.5 by adding an order of precedence between the documents of the Employer’s Requirements.

If no order of precedence of any of the documents of the Contract is to be prescribed, this Sub-Clause may be varied:

EXAMPLE	Delete Sub-Clause 1.5 and substitute:

“The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found, the priority shall be such as may be accorded by the governing law. The Employer’s Representative has authority to issue any instruction which he/she considers necessary to resolve an ambiguity or discrepancy.”

## Sub-Clause 1.6	Contract Agreement

It is important that the form of the Contract Agreement be included in the tender documents as an annex to the Special Provisions: an example form is included at the end of this publication (in the section “Forms”).

If lengthy tender negotiations were necessary, it is recommended that consideration be given to recording in the Contract Agreement: the Base Date and/or the Commencement Date.

## Sub-Clause 1.9	Employer’s Use of Contractor’s Documents

Additional provisions may be required if all rights to particular items of computer software (for example) are to be assigned to the Employer. These provisions should take account of the applicable law.

## Sub-Clause 1.12	Compliance with Laws

For a plant contract, alternative arrangements may be appropriate:

EXAMPLE	Insert after sub-paragraph (d) of Sub-Clause 1.12:

“The Contractor shall submit, in good time, the details of Goods to the Employer, who shall then promptly obtain all import permits or licences required for these Goods.

The Employer shall also obtain or grant all consents including permits-to-work, rights-of-way and approvals required for the Works.”

In respect of sub-paragraphs (b) and (c) of this Sub-Clause, if (in addition to the provisions of Sub-Clause 4.18 [ Protection of the Environment ]) the applicable law requires the Contractor to apply for and/or comply with particular environmental permits, these permits should be clearly described in detail in the Employer’s Requirements together with the Contractor’s obligations associated with each permit.

## Sub-Clause 1.13	Joint and Several Liability

If it is likely that one or more of the tenderers will be a Joint Venture, detailed requirements for the JV may need to be specified in addition to those listed in the definition of “JV Undertaking” under Sub-Clause 1.1.41. For example, it may be desirable for each member of the JV to produce a parent company guarantee: an example form is included at the end of this publication (in the section “Forms”).

These requirements should be included in the Instructions to Tenderers. Normally the Employer will wish the leader of the JV to be appointed at an early stage, providing a single point of contact thereafter, and will not wish to be involved in a dispute between the members of a JV.

The Employer should scrutinise the JV Undertaking carefully and, where relevant, check if the project’s financing institution(s) has/have to give consent.

## Sub-Clause 1.14	Limitation of Liability

If it is required that the limitation of each Party’s liability to the other Party is to include certain “indirect or consequential loss or damage” and is also to take into account liabilities which are to be insured under Clause 19 [ Insurance ], the Contract Data and this Sub-Clause may be varied:

EXAMPLE	In the Contract Data, add the following: “ 1.14   Amount of Sum A:

Amount of Sum B:   Amount of Sum C:     ”

Delete Sub-Clause 1.14 and substitute:

“Except as stated in this Sub-Clause, neither Party shall be liable to the other Party for loss of use of any Works, loss of profit, loss of any contract or for any indirect or consequential loss or damage which may be suffered by the other Party in connection with the Contract.

The Contractor’s liability to the Employer under or in connection with the Contract shall be limited as follows:

- for failure to comply with Sub-Clause 8.2 [ Time for Completion ], the limit shall be the maximum amount of Delay Damages stated in the Contract Data;

- for loss of profit, loss of any contract or loss of use of any part of the Permanent Works (after taking over under the Contract), caused by:

  - defects attributable to the Contractor, the limit shall be the sum A stated in the Contract Data;

  - damage to the Works caused by the Contractor, the limit shall be the sum B stated in the Contract Data;

  - damage caused by the Contractor to the Employer’s property other than the Works, the limit shall be fifty percent (50%) of the sum B stated in the Contract Data; and

  - any other matter attributable to the Contractor, the limit shall be fifty percent (50%) of the sum A stated in the Contract Data;

- for damage caused by the Contractor to the Works, the limit shall be the required value of cover of the insurance under Sub-Clause 19.2.1 [ The Works ];

- for damage caused by the Contractor to the Employer’s property other than the Works, the limit shall be the required value of cover of the insurance under Sub-Clause 19.2.4 [ Injury to persons and damage to property ];

- for death or injury to the Employer’s personnel by a cause attributable to the Contractor, the limit shall be the required value of cover of the insurance under Sub-Clause 19.2.5 [ Injury to employees ];

- for the Contractor’s indemnity to the Employer for third party claims under the first paragraph of Sub-Clause 17.4 [ Indemnities by Contractor ], there shall be no limit; and

- for the Contractor’s indemnity to the Employer under the second paragraph of Sub-Clause 17.4 [ Indemnities by Contractor ], the limit shall be the required value of cover of the insurance under Sub-Clause 19.2.3 [ Liability for breach of professional duty ];

- for all matters other than those described in sub-paragraphs

(b) to (g) above and other than those under Sub-Clause

17.3 [ Intellectual and Industrial Property Rights ], the limit shall be the sum C stated in the Contract Data.

The Employer’s liability to the Contractor under or in connection with the Contract shall be limited as follows:

- for loss of profit, loss of any contract or any other direct loss caused by termination of the contract under Sub-Clause 15.5 [ Termination for Employer’s Convenience ] and Sub-Clause 16.2 [ Termination by Contractor ], the limit shall be twenty percent (20%) of the Contract Price stated in the Contract Agreement;

- for damage caused by the Employer or Employer’s Personnel to the Temporary Works or Plant and Materials not included in the Permanent Works, the limit shall be thirty percent (30%) of the required value of cover of the insurance under Sub-Clause 19.2.1 [ The Works ];

- for damage caused by the Employer or Employer’s Personnel to the Contractor’s Equipment, Materials, Plant and/or Temporary Works, the limit shall be

the required value of cover of the insurance under Sub-Clause 19.2.2 [ Goods ];

- for death or injury to the Contractor’s Personnel by a cause attributable to the Employer the limit shall be the required value of cover of the insurance under Sub-Clause 19.2.5 [ Injury to employees ];

- for the Employer’s indemnity to the Contractor for third party claims under Sub-Clause 17.5 [ Indemnities by Employer ], there shall be no limit; and

- for all matters other than those described in sub-paragraph (i) to (v) above and other than under Sub-Clause 17.3 [ Intellectual and Industrial Property Rights ], the limit shall be in accordance with Sub-Clause 14.14 [ Cessation of Employer’s Liability ] as may be amended under Sub-Clause

  - [ Obtaining  DAAB’s  Decision ],  Sub-Clause

  - [ Amicable Settlement ] or Sub-Clause 21.6 [ Arbitration ].

This Sub-Clause shall not limit liability in any case of fraud, gross negligence, deliberate default or reckless misconduct by the defaulting Party.”

# Clause 2	The Employer

## Sub-Clause 2.1	Right of Access to the Site

It may be necessary for the Contractor to have early access to the Site for the purposes of survey and sub-surface investigations. If so, the details of such early right of access should be given in the Employer’s Requirements, including any restrictions on such access and whether or not it shall be exclusive to the Contractor.

If right of access to, and possession of, the Site cannot be granted by the Employer in the normal way, details should be given in the Employer’s Requirements and appropriate amendments made to the first paragraph of this Sub-Clause and, if necessary, to the second paragraph.

## Sub-Clause 2.3	Employer’s Personnel and Other Contractors

The provisions concerning co-operation between contractors should be reflected in the Employer’s contracts with any other contractors working on or near the Site.

## Sub-Clause 2.6	Employer-Supplied Materials and Employer’s Equipment

If Employer-Supplied Materials are listed in the Employer’s Requirements for the Contractor’s use in the execution of the Works, the following provisions may be added:

EXAMPLE	After the last paragraph of Sub-Clause 2.6, add:

“The Employer shall supply to the Contractor the Employer- Supplied Materials listed in the Employer’s Requirements, at the time(s) stated in the Employer’s Requirements (if not stated, within the times that shall be required to enable the Contractor to proceed with execution of the Works in accordance with the Programme).

When made available by the Employer, the Contractor shall visually inspect the Employer-Supplied Materials and shall promptly give a Notice to the Employer’s Representative of any shortage, defect or default in them. Thereafter, the Contractor shall rectify such shortage, defect or default to the extent instructed by the Employer’s Representative. Such instruction shall be deemed to have been given under Sub-Clause 13.3.1 [ Variation by Instruction ].

After this visual inspection, the Employer-Supplied Materials shall come under the care, custody and control of the Contractor. The Contractor’s obligations of inspection, care, custody, and control shall not relieve the Employer of liability for any shortage, defect or default not apparent from a visual inspection.”

In the last paragraph of Sub-Clause 17.1 [ Responsibility for Care of the Works ] after the two instances of “Goods” add:

“, Employer-Supplied Materials,”.

If Employer’s Equipment is listed in the Employer’s Requirements for the Contractor’s use in the execution of the Works, the following provisions may be added:

EXAMPLE	After the last paragraph of Sub-Clause 2.6, add:

“The Employer shall make the Employer’s Equipment listed in the Employer’s Requirements available to the Contractor at the time(s) stated in the Employer’s Requirements (if not stated, within the times that shall be required to enable the Contractor to proceed with execution of the Works in accordance with the Programme).

Unless expressly stated otherwise in the Employer’s Requirements, the Employer’s Equipment shall be provided for the exclusive use of the Contractor.

When made available by the Employer, the Contractor shall visually inspect the Employer’s Equipment and shall promptly give a Notice to the Employer’s Representative of any shortage, defect or default in them. Thereafter, the Contractor shall rectify such shortage, defect or default to the extent instructed by the Employer’s Representative. Such instruction shall be deemed to have been given under Sub-Clause 13.3.1 [ Variation by Instruction ].

The Contractor shall be responsible for the Employer’s Equipment while it is under the Contractor’s control and/or any of the Contractor’s Personnel is operating it, driving it, directing it, using it, or in control of it.

The Contractor shall not remove from the Site any items of the Employer’s Equipment without the consent of the Employer. However, consent shall not be required for vehicles transporting Goods or Contractor’s Personnel to or from the Site.”

In the last paragraph of Sub-Clause 17.1 [ Responsibility for Care of the Works and Indemnities ] after the two instances of “Goods” add:

“, Employer’s Equipment”,

# Clause 3	The Employer’s Administration

## Sub-Clause 3.1	The Employer’s Representative

In the appointment of the Employer’s Representative, the Employer may consider using the form of agreement FIDIC Clients/Consultants Model Services Agreement fifth Edition, 2017 (https://fidic.org/books/clientconsultant-model-services-agreement-5th-ed-2017-white- book†).

In performing the Employer’s Representative’s duties and in exercising his/her authority under the Contract, it is recommended that the Employer’s Representative takes due regard of:

- FIDIC’s Code of Ethics for consulting engineers: http://fidic.org/about-fidic/ fidic-policies/fidic-code-ethics†;

and

- the duty to prevent corruption and bribery as described in the publications:

  - FIDIC Guidelines for Integrity Management (FIM) in the consulting industry, Part 1 - Policies and principles first edition, 2011 (https:// fidic.org/books/integrity-management-system-fims-guidelines-1st- ed-2011-part1†) and

  - FIDIC Guidelines for Integrity Management System in the Consulting Industry 1st Ed (2015) Part 2, FIMS Procedures (https://fidic.org/ books/guidelines-integrity-management-system-consulting-industry- 1st-ed-2015-part-2†).

## Sub-Clause 3.2	Other Employer’s Personnel

If it is anticipated that the Employer’s Representative’s assistants may not all be fluent in the language for communications defined in Sub-Clause 1.4 [ Law and Language ], consideration should be given to amending this Sub-Clause:

EXAMPLE	In the last paragraph of Sub-Clause 3.2, after “Sub-Clause 1.4 [ Law and Language ]” add the following:

“If any assistants are not fluent in this language the Employer’s Representative shall make competent interpreters available during all working hours, in a number sufficient for those assistants to properly perform their assigned duties and/or exercise their delegated authority.”

## Sub-Clause 3.4	Instructions

If the applicable law prevents the Contractor from complying with any instruction that may have an adverse effect on the health and safety of the Contractor’s Personnel, sub-paragraph

(b) of this Sub-Clause may be amended:

EXAMPLE	At the end of sub-paragraph (b) of Sub-Clause 3.4, add the following:

“or will adversely affect the health and safety of the Contractor’s Personnel”.

If the Conditions of Contract are to allow for the giving of oral instructions by the Employer’s Representative, this Sub-Clause may be amended:

EXAMPLE	At the end of Sub-Clause 3.5, add the following:

“If the Employer’s Representative or a delegated assistant:

- gives an oral instruction;

- receives a written confirmation of the instruction, from the Contractor, within two working days after giving the oral instruction; and

- does not reply by issuing a written rejection and/or instruction within two working days after receiving the confirmation

then the Contractor’s confirmation shall constitute the written instruction of the Employer’s Representative or delegated assistant (as the case may be).”

## Sub-Clause 3.5	Agreement or Determination

The Employer’s Representative shall not delegate any of his/her duties under this Sub-Clause to any assistant, as stated under Sub-Clause 3.2 [ Other Employer’s Personnel ].

As an alternative to determination of a matter or Claim by the Employer’s Representative envisaged under this Sub-Clause, the Parties may prefer that, where agreement cannot be reached in respect of any Claim or matter, it is referred to the DAAB for a decision in which case the following amendments will be needed:

EXAMPLE	Delete the last paragraph of Sub-Clause 3.5.1 [ Consultation to reach agreement ], and replace with:

“If:

- no agreement is achieved within the time limit for agreement under Sub-Clause 3.5.3 [ Time limits ]; or

- both Parties advise the Employer’s Representative that no agreement can be achieved within this time limit

whichever is the earlier, the matter or Claim shall be deemed to be a Dispute which may be referred by either Party to the DAAB for its decision under 21.4 [ Obtaining DAAB’s Decision ] and sub-paragraph (a) of 21.4.1 [ Reference of a Dispute to the DAAB ] shall not apply.”;

delete Sub-Clause 3.5.2 [ Employer’s Representative’s determination ];

delete the second and last paragraphs of Sub-Clause 3.5.3 [ Time Limits ] and replace with:

“If the Employer’s Representative does not give the Notice of agreement within this time limit, the matter or Claim shall be deemed to be a Dispute which may be referred by either Party to the DAAB for its decision under 21.4 [ Obtaining DAAB’s Decision ] and sub-paragraph (a) of 21.4.1 [ Reference of a Dispute to the DAAB ] shall not apply.”;

in Sub-Clause 3.5.4 [ Effect of the agreement or determination ]:

- in the first paragraph, delete the words “or, in the case of a determination, it is revised under Clause 21 [ Disputes and Arbitration ]”; and

- replace all instances of “agreement or determination” with “agreement”; and

delete Sub-Clause 3.5.5 [ Dissatisfaction with Employer’s Representative’s determination ].

## Sub-Clause 3.6	Meetings

It may be useful to give information in the Employer’s Requirements of a planned timetable of meetings such as management meetings, site meetings, technical meetings, and progress meetings.

# Clause 4	The Contractor

## Sub-Clause 4.1	Contractor’s General Obligations

FIDIC strongly recommends that the Employer ensures that the Employer’s Requirements contain a clearly identified, defined and described specific purpose or purposes for which the facility will be used when complete, in order that the Contractor can comply with the obligation to provide Works which are “fit for the purpose(s) for which they are intended” as stated in this Sub-Clause.

## Sub-Clause 4.2	Performance Security

The acceptable form(s) of Performance Security should be included in the tender documents. Example forms are included at the end of this publication (in the section “Forms”). They incorporate two sets of Uniform Rules published by the International Chamber of Commerce (the “ICC”, which is based at 33-43 Avenue du Président Wilson, 75116 Paris, France), which also publishes guides to these Uniform Rules.

These example forms and the wording of the Sub-Clause may have to be amended to comply with applicable law.

EXAMPLE	At the end of the first paragraph of Sub-Clause 4.2.1 [ Contractor’s obligations ], insert:

“If the Performance Security is in the form of a bank guarantee, it shall be issued either (i) by a bank located in the Country, or (ii) directly by a foreign bank to which the Employer gives consent. If the Performance Security is not in the form of a bank guarantee, it shall be issued by a financial entity registered, or licensed to do business, in the Country.”

The example forms of Performance Security that are included at the end of this publication (in the section “Forms”) provide for the option to reduce the amount of the Performance Security following issue of the Taking-Over Certificate for the whole of the Works under Clause 10. If neither of the example forms is to be used, consideration should be given to adding provisions for this option to Sub-Clause 4.2.1.

## Sub-Clause 4.3	Contractor’s Representative

If the Contractor’s Representative is known at the time of submission of the tender, the tenderer may propose that person in his/her tender. The tenderer may wish to propose alternatives, especially if the contract award seems likely to be delayed.

The “main engineering discipline applicable to the Works” in which the Contractor’s Representative is required to be qualified, experienced and competent should be the engineering discipline of the Works which is of highest value proportionate to the value of the Works. If it is necessary to stipulate that the Contractor’s Representative shall be qualified, experienced and competent in a particular engineering discipline in relation to the Works, the following amendment will need to be made to this Sub-Clause:

EXAMPLE	In the second paragraph of Sub-Clause 4.3 delete “the main engineering discipline applicable to the Works” and replace with:

[ Insert description of engineering discipline ],

If it is necessary that the Contractor’s Representative shall also be fluent in a particular language other than the language for communications defined in Sub-Clause 1.4 [ Law and Language ], the following amendment may be made:

EXAMPLE	At the end of the second paragraph of Sub-Clause 4.3, add:

“The  Contractor’s  Representative  shall  also  be  fluent  in

(insert name of language).”

If it is permissible that the Contractor’s Representative is not fluent in the language for communications defined in Sub-Clause 1.4 [ Law and Language ], consideration should be given to amending this Sub-Clause:

EXAMPLE	Insert at the end of the second paragraph of Sub-Clause 4.3:

“If the Contractor’s Representative is not fluent in this language the Contractor shall make competent interpreter(s) available during all working hours, sufficient for the Contractor’s Representative to properly perform his/her duties and exercise his/her authority under the Contract.”

If it is permissible that the Contractor’s Representative’s delegates are not all fluent in the language for communications defined in Sub-Clause 1.4 [ Law and Language ], consideration should be given to amending this Sub-Clause:

EXAMPLE	Insert at the end of the last paragraph of Sub-Clause 4.3:

“If any of these persons is not fluent in this language the Contractor shall make competent interpreters available during all working hours, in a number sufficient for those persons to properly perform their delegated powers, functions and/or authority.”

## Sub-Clause 4.4	Subcontractors

It may be appropriate and/or desirable, taking account of the circumstances and locality of the project, to encourage the Contractor to employ local contractors in the execution of the Works:

EXAMPLE	At the end of the second paragraph of Sub-Clause 4.4, add:

“The Contractor shall give reasonable opportunity to contractors from the Country to tender for subcontracts for the Works, and shall use reasonable endeavours to employ such contractors as Subcontractors.”

If the Employer requires that all the Contractor’s subcontracts should provide for assignment of the subcontract to the Employer in the event that Sub-Clause 15.2 [ Termination for Contractor’s Default ] applies, the following amendment will need to be made to this Sub-Clause:

EXAMPLE	Insert at the end of the last paragraph of Sub-Clause 4.4:

“All subcontracts relating to the Works shall include provisions which entitle the Employer to require the subcontract to be assigned to the Employer under sub-paragraph (a) of Sub-Clause 15.2.3 [ After Termination ].”

If the Employer requires that the Contractor assigns the benefit of the relevant subcontract in the event that a Subcontractor’s obligations continue after expiry of the DNP relating to that Subcontractor’s work, the following amendment will need to be made to this Sub-Clause:

EXAMPLE	Insert at the end of the last paragraph of Sub-Clause 4.4:

“If a Subcontractor’s obligations to the Contractor extend beyond the expiry date of the DNP which is applicable to the Subcontractor’s work and if the Contractor receives an instruction from the Employer’s Representative to do so not less than 7 days before this expiry date, the Contractor shall assign the benefit of such obligations to the Employer. Unless otherwise stated in the assignment, the Contractor shall have no liability to the Employer for work carried out by the Subcontractor after the assignment takes effect.”

## Sub-Clause 4.5	Nominated Subcontractors

Normally the Contractor will select and employ subcontractor(s), (subject to any constraints stated in the Contract), but this Sub-Clause provides for the situation where the Employer may wish to select a particular subcontractor or subcontractors to be employed by the Contractor in the execution of the Works.

If this is the case, it is recommended that the Employer names the particular subcontractor(s) in the Employer’s Requirements so that tenderers are aware of this requirement before submitting their tenders - although this Sub-Clause also makes provision for the Employer to instruct the Contractor to employ a subcontractor or subcontractors after contract award. It should be noted that:

- once the Contractor has employed a subcontractor who has been nominated by the Employer, the second paragraph of Sub-Clause 4.4 [ Subcontractors ] applies; and

- sub-paragraph (b) of Sub-Clause 13.4 [ Provisional Sums ] should provide for payment to the Contractor for works or services to be purchased by the Contractor from a nominated Subcontractor.

If the Employer anticipates that a Subcontractor is to be instructed under Sub-Clause 13.3 [ Variation Procedure ] but is not to be a nominated Subcontractor this Sub-Clause should be amended, describing the particular circumstances.

## Sub-Clause 4.8	Health and Safety Obligations

If the Contractor is sharing occupation of the Site with others, it may not be appropriate for him/her to provide some of the listed items. In these circumstances:

- this Sub-Clause should be amended to specify exactly what health and safety obligations are the Contractor’s under the Contract, and

- the health and safety obligations which are to be fulfilled by the Employer and/or others should be specified in the Employer’s Requirements

so that it is clear which Party is responsible for what in respect of the health and safety obligations for the Site and for the Works.

## Sub-Clause 4.9.1	Quality Management System

In the performance of the Contractor’s obligations under this Sub-Clause, it is recommended that the Contractor and the Employer take due regard of the FIDIC publication Improving the Quality of Construction – a guide for actions, 2004 (https://fidic.org/books/improving-quality- construction-2004†).

If the Employer requires the Contractor to have a Quality Manager employed on the Site, such position should be specified in the Employer’s Requirements as one of the positions of Key Personnel.

If the Employer requires the Contractor to interface with others and/or with the Employer, the Employer’s Requirements should clearly describe all such interfaces and should specify the extent to which the Contractor shall allow for such interfaces in the QM System.

## Sub-Clause 4.12	Unforeseeable Difficulties

If the Works include tunnelling or other substantial sub-surface construction, it is usually preferable for the risk of unforeseen ground conditions to be allocated to the Employer.

Responsible contractors will be reluctant to take the risks of unknown ground conditions which are difficult or impossible to estimate in advance. FIDIC’s Conditions of Contract for Plant and Design-Build, Second Edition 2017 should be used in these circumstances for works designed by (or on behalf of) the Contractor.

## Sub-Clause 4.16	Transport of Goods

In some cases, the Contractor may be required to get permission prior to delivery of Goods to the Site. In such cases those Goods for which permission is required should be stated in the Employer’s Requirements, and the following wording may be added to this Sub-Clause:

EXAMPLE	Insert at the end of Sub-Clause 4.16:

“The Contractor shall obtain the Employer’s Representative’s permission prior to delivering to the Site any item of Goods which is identified in the Employer’s Requirements as requiring such permission. No such Goods shall be delivered without this permission, which shall not relieve the Contractor from any duty, obligation or responsibility under or in connection with the Contract.”

## Sub-Clause 4.17	Contractor’s Equipment

If the Contractor is not to provide all the Contractor’s Equipment necessary to execute the Works, the Employer’s obligations should be specified: please see Sub-Clause 2.6 [ Employer-Supplied Materials and Employer’s Equipment ] and the guidance notes for Sub-Clause 2.6 above.

If vesting of Contractor’s Equipment to the Employer is required, and such vesting is consistent with the Laws of the Country, further paragraphs may be added to this Sub-Clause:

EXAMPLE	At the end of Sub-Clause 4.17, add the following paragraphs:

“Each item of Contractor’s Equipment shall become the property of the Employer (free from liens and other encumbrances) when it arrives on the Site.

This vesting of property from the Contractor to the Employer shall not:

- affect the responsibility or liability of the Employer under the Contract;

- prejudice the Contractor’s right to exclusive use of all items of Contractor’s Equipment for the purpose of the Works; and/or

- relieve the Contractor from any duty, obligation or responsibility to operate and maintain all items of Contractor’s Equipment.

The property in each item of Contractor’s Equipment shall be deemed to re-vest in the Contractor (free from liens and other encumbrances) when he/she is entitled to remove it from the Site

or to receive the Taking-Over Certificate for the Works, whichever is the earlier.”

## Sub-Clause 4.18	Protection of the Environment

If the applicable environmental law requires the Contractor to prepare project-specific environmental management plans, for review by the Employer’s Representative and/or the Employer and approval by regulatory authorities, these plans should be clearly described in detail in the Employer’s Requirements together with the review/approval process associated with each plan.

## Sub-Clause 4.19	Temporary Utilities

If services are to be available on the Site for the Contractor to use, details of such services should be set out in the Employer’s Requirements, including a description of each utility, the capacity of each utility that is available for the Contractor’s use, its location and the price per unit of consumption.

## Sub-Clause 4.21	Security of the Site

If the Contractor is sharing occupation of the Site with others, it may not be appropriate for the Contractor to be responsible for its security. In these circumstances, it is recommended that:

- this Sub-Clause should be amended to specify exactly what security obligations are the Contractor’s under the Contract,

and

- the security obligations which are to be fulfilled by the Employer and/or others should be specified in the Employer’s Requirements

so that it is clear which Party is responsible for what in respect of the security of the Site.

## Sub-Clause 4.22	Contractor’s Operations on Site

If the Contractor is sharing occupation of the Site with others, it is recommended that this Sub-Clause is amended by identifying and allocating responsibility for clearance and removal from the Site of any wreckage, rubbish, hazardous waste, temporary works and surplus material.

## Additional Sub-Clause  Milestones

If the Employer wishes to have certain parts of the Works completed within certain times but does not wish to take over such parts when completed (as distinct from the parts of the Works which the Employer wishes to take over after completion, which should be defined as Sections in the Contract Data), such parts of the Works should be clearly described in the Employer’s Requirements as ‘Milestones’ and it is recommended that the following provisions are added to the Contract Data and to the Conditions of Contract:

EXAMPLE PROVISIONS FOR MILESTONES

In the Contract Data, add the following:

“4.24.	Definition of Milestones:

| Description of a | Time for Completion | Delay Damages |
| --- | --- | --- |
| part of the Plant or |  | (as a percentage of |
| of the Works that |  | final Contract Price |
| shall be designated |  | per day of delay) |
| a Milestone for the |  |  |
| purposes of the |  |  |
| Contract |  |  |
|  | days | % |
|  | days | % |
|  | days | % |
|  | days | % |

Maximum amount of Delay Damages for Milestones (percent of final Contract Price)   %.”

Insert two new definitions under Sub-Clause 1.1:

“ “Milestone” means a part of the Plant and/or a part of the Works stated in the Contract Data (if any), and described in detail in the Employer’s Requirements as a Milestone, which is to be completed by the time for completion stated in Sub-Clause 4.24 [ Milestones ] but is not to be taken over by the Employer after completion.

“Milestone Certificate” means the certificate issued by the Employer’s Representative under Sub-Clause 4.24 [ Milestones ].”

Add new Sub-Clause 4.24 [ Milestones ].

“If no Milestones are specified in the Contract Data, this Sub-Clause shall not apply.

The Contractor shall complete the works of each Milestone (including all work which is stated in the Employer’s Requirements as being required for the Milestone to be considered complete) within the time for completion of the Milestone, as stated in the Contract Data, calculated from the Commencement Date.

The Contractor shall include, in the initial programme and each revised programme, under sub-paragraph (a) of Sub-Clause 8.3 [ Programme ], the time for completion for each Milestone.

Sub-paragraph (d) of Sub-Clause 8.4 [ Advance Warning ] and Sub-Clause 8.5 [ Extension of Time for Completion ] shall apply to each Milestone, such that “Time for Completion” under Sub-Clause

8.5 shall be read as the time for completion of a Milestone under this Sub-Clause.

The Contractor may apply, by Notice to the Employer’s Representative, for a Milestone Certificate not earlier than 14 days before the works of a Milestone will, in the Contractor’s opinion, be complete. The Employer’s Representative shall, within 28 days after receiving the Contractor’s Notice:

  - issue the Milestone Certificate to the Contractor, stating the date on which the works of the Milestone were completed

in accordance with the Contract, except for any minor outstanding work and defects (as shall be listed in the Milestone Certificate); or

  - reject the application, giving reasons and specifying the work required to be done and defects required to be remedied by the Contractor to enable the Milestone Certificate to be issued.

The Contractor shall then complete the work referred to in sub-paragraph (b) of this Sub-Clause before issuing a further Notice of application under this Sub-Clause.

If the Employer’s Representative fails either to issue the Milestone Certificate or to reject the Contractor’s application within the above period of 28 days, and if the works of a Milestone are complete in accordance with the Contract, the Milestone Certificate shall be deemed to have been issued on the date which is 14 days after the date stated in the Contractor’s Notice of application.

If Delay Damages for a Milestone are stated in the Contract Data, and if the Contractor fails to complete the works of the Milestone within the time for completion of the Milestone (with any extension under this Sub-Clause):

    - the Contractor shall, subject to Sub-Clause 20.1 [ Claims ], pay Delay Damages to the Employer for this default;

    - such Delay Damages shall be the amount stated in the Contract Data, for every day which shall elapse between the time for completion for the Milestone (with any extension under this Sub-Clause) and the date stated in the Milestone Certificate;

    - these Delay Damages shall be the only damages due from the Contractor for such default; and

    - the total amount of Delay Damages for all Milestones shall not exceed the maximum amount stated in the Contract Data (this shall not limit the Contractor’s liability for Delay Damages in any case of fraud, gross negligence, deliberate default or reckless misconduct by the Contractor).”

If certain payment(s) to the Contractor is/are to be made on completion of each Milestone, such payment(s) should be specified in a Schedule of Payments in the Contract and consideration should be given to amending Sub-Clause 14.4 [ Schedule of Payments ] to make express reference to the Milestone payments.

# Clause 5	Design

## Sub-Clause 5.1	General Design Obligations

It is recommended that the Instructions to Tenderers require tenderers to include the name, address, detailed particulars and relevant experience of each proposed designer/design Subcontractor so that the Employer can assess whether and to what extent each tenderer’s proposed designers/design Subcontractors comply with the three conditions set out in sub-paragraphs (a) to (c) of this Sub-Clause.

If the Employer’s Requirements include an outline design, tenderers should be advised of the extent to which the Employer’s outline design is a suggestion or a requirement.

If there are to be portions of the Employer’s Requirements, and/or data and information provided by (or on behalf of) the Employer, which are to be immutable or are to be the responsibility of the Employer, then these should be stated in the Contract (by the Employer in the Employer’s Requirements or by the Contractor in the documents to be submitted with

the Tender),

## Sub-Clause 5.2	Contractor’s Documents

It is important that the Employer’s Requirements should clearly specify which Contractor’s Documents the Employer requires the Contractor to prepare, which may not necessarily include (for example) all the technical documents which the Contractor’s Personnel will need in order to execute the Works.

For example, it may be appropriate for the Employer’s Requirements for a plant contract to specify that the Contractor’s Documents shall include drawings showing how the Plant is to be installed and any other information required for:

- preparing suitable foundations or other means of support,

- providing suitable access on the Site, for the Plant and any necessary equipment, to the place where the Plant is to be erected, and/or

- making necessary connections to the Plant.

## Sub-Clause 5.2.2	Review by Employer

The “Contractor’s Documents” under this Sub-Clause 5.2.2 are the documents that the Contractor must submit to the Employer for review, as specified in the Employer’s Requirements or as stated in the Conditions of Contract (namely, as-built records under Sub-Clause 5.6 [ As-Built Records ] and O&M Manuals under Sub-Clause 5.7 [ Operation and Maintenance Manuals ]). It is important, therefore, that the Employer’s Requirements clearly identify which of the Contractor’s Documents the Employer requires the Contractor to submit to the Employer for review.

If a different Review Period than that stated under this Sub-Clause 5.2.2 is considered necessary, or different Review Periods are considered necessary for different (types of) Contractor’s Documents, taking account of the time required to review the different types of Contractor’s Documents and/or of the possibility of substantial submissions at particular stages of the design-build process, such different Review Period(s) should be clearly stated in the Employer’s Requirements.

In some jurisdictions there may be a requirement under the applicable law for the mandatory review/checking of certain elements of design (by an authorised professional or other legally recognised individual) and/or verification that such design is in accordance with the applicable law, before such design can be implemented in the Works. If this is the case, it is essential that it is drawn to tenderers’ attention in the Instruction to Tenderers and necessary amendments will need to be made to this Sub-Clause – taking due care and attention that the following is clear and unambiguous:

- the mandatory review/checking and/or verification process(es) required by the applicable law, and details of the submission procedure(s) associated with such process(es);

- which element(s) of design, and which type(s) of Contractor’s Documents associated with such element(s), shall be subject to the mandatory review/checking and/or verification process(es);

- whether, and to what extent, the mandatory review/checking and/or verification process(es) of an element of design (and the Contractor’s Documents associated with such element) shall replace the Employer’s review under this Sub-Clause;

- a statement that any Notice of No-objection (or deemed Notice of No-objection) from the Employer with respect to any Contractor’s Document shall not replace the mandatory review/checking and/or verification of the design (or a revised design).

It is strongly recommended that the Employer is advised by legal and engineering professionals with extensive experience in the mandatory review/checking and/or verification process(es)

required by the applicable law when preparing the revised wording of this Sub-Clause.

## Sub-Clause 5.5	Training

If the Works include Plant that comprises (in whole or in part) new or innovative technology in the Country or at the Employer’s location, it is recommended that the Parties consider including in the Contract provision for training (by the Employer in the Employer’s Requirements and/ or by the Contractor in the documents to be submitted with the Tender) of the Employer’s Personnel at the location of another plant facility, or at a number of other plant facilities, that are similar in nature to the Works.

## Sub-Clause 5.7	Operation and Maintenance Manuals

If the Contractor is required to supply spare parts under the Contract, these should be detailed in the Employer’s Requirements, which should also specify the required guarantee period for these spare parts.

# Clause 6	Staff and Labour

## Sub-Clause 6.3	Recruitment of Persons

It may be necessary to review and revise this Sub-Clause (or delete it in its entirety) if the relevant labour Laws applicable to the Contractor’s Personnel and/or the Employer’s Personnel do not permit any restriction on the right of any worker to seek other positions.

## Sub-Clause 6.6	Facilities for Staff and Labour

If the Employer plans to make any facilities and/or accommodation (for example, office accommodation) available for the Contractor’s occupation and/or use, the Employer’s obligations to do so and details of such facilities and/or accommodation should be specified in the Employer’s Requirements. See also the guidance under Clause 17 [ Care of the Works and Indemnities ] below for the suggested additional sub-clause in respect of responsibility for care of such facilities and/or accommodation.

## Sub-Clause 6.8	Contractor’s Superintendence

If it is permissible that the Contractor’s superintending staff are not all fluent in the language for communications defined in Sub-Clause 1.4 [ Law and Language ], then consideration should be given to amending this Sub-Clause:

EXAMPLE	Insert at the end of sub-paragraph (a) of Sub-Clause 6.8:

“or, if not, the Contractor shall make competent interpreters available during all working hours, in a number sufficient for those persons to properly perform their superintendence duties.”

If it is necessary to stipulate that the Contractor’s superintending staff shall be fluent in a particular language, the following sentence should be added.

EXAMPLE	Insert at the end of Sub-Clause 6.8:

“A reasonable proportion of the Contractor’s superintending staff shall have a working knowledge of

[ Insert name of language ],

or the Contractor shall make interpreters available on Site during all working hours in a number deemed sufficient by the Employer’s

Representative.”

## Sub-Clause 6.12	Key Personnel

If it is permissible that all Key Personnel are not fluent in the language for communications defined in Sub-Clause 1.4 [ Law and Language ], then consideration should be given to amending this Sub-Clause:

EXAMPLE	Insert at the end of the last paragraph of Sub-Clause 6.12:

“If any of the Key Personnel are not fluent in this language the Contractor shall make competent interpreter(s) available during all working hours, sufficient for that person to properly perform his/her duties under the Contract.”

## Additional Sub-Clauses

It may be necessary, appropriate and/or desirable to include additional sub-clauses to take account of the circumstances and locality of the Site:

EXAMPLE SUB-CLAUSE FOR FOREIGN PERSONNEL

“The Contractor may bring into the Country any foreign personnel who are necessary for the execution of the Works to the extent allowed by the applicable Laws. The Contractor shall ensure that these personnel are provided with the required residence visas and work permits. The Employer shall, if requested by the Contractor, use all reasonable endeavours in a timely and expeditious manner to assist the Contractor in obtaining any local, state, national, or government permission required for bringing in the Contractor’s personnel.

The Contractor shall be responsible for the return of these personnel to the place where they were recruited or to their domicile. In the event of the death in the Country of any of these personnel or members of their families, the Contractor shall similarly be responsible for making the appropriate arrangements for their return or burial.”

EXAMPLE SUB-CLAUSE FOR SUPPLY OF FOODSTUFFS

“The Contractor shall arrange for the provision of a sufficient supply of suitable food as may be stated in the Employer’s Requirements at reasonable prices for the Contractor’s Personnel for the purposes of or in connection with the Contract.”

EXAMPLE SUB-CLAUSE FOR SUPPLY OF WATER

“The Contractor shall, having regard to local conditions, provide on the Site an adequate supply of drinking and other water for the use of the Contractor’s Personnel.”

EXAMPLE SUB-CLAUSE FOR MEASURES AGAINST INSECT AND PEST NUISANCE

“The Contractor shall at all times take the necessary precautions to protect the Contractor’s Personnel employed on the Site from insect and pest nuisance, and to reduce the danger to their health. The Contractor shall comply with all the regulations of the local health authorities, including use of appropriate insecticide.”

EXAMPLE SUB-CLAUSE FOR ALCOHOLIC LIQUOR OR DRUGS

“The Contractor shall not, other than in accordance with the Laws of the Country, import, sell, give, barter or otherwise dispose of any

alcoholic liquor or drugs, or permit or allow importation, sale, gift, barter or disposal thereto by the Contractor’s Personnel.”

EXAMPLE SUB-CLAUSE FOR ARMS AND AMMUNITION

“The Contractor shall not give, barter, or otherwise dispose of, to any person, any arms or ammunition of any kind, or allow the Contractor’s Personnel to do so.”

EXAMPLE SUB-CLAUSE FOR FESTIVALS AND RELIGIOUS CUSTOMS

“The Contractor shall respect the Country’s recognised festivals, days of rest and religious or other customs.”

EXAMPLE SUB-CLAUSE FOR FUNERAL ARRANGEMENTS

“The Contractor shall be responsible, to the extent required by local regulations, for making any funeral arrangements for any of the Contractor’s local employees who may die while engaged upon the Works.”

EXAMPLE SUB-CLAUSE FOR FORCED LABOUR

“The Contractor shall not employ forced labour, which consists of any work or service, not voluntarily performed, that is exacted from an individual under threat of force or penalty, and includes any kind of involuntary or compulsory labour, such as indentured labour, bonded labour or similar labour-contracting arrangements.”

EXAMPLE SUB-CLAUSE FOR CHILD LABOUR

“The Contractor shall not employ children (any natural persons under the age of eighteen years) in a manner that is economically exploitative, or is likely to be hazardous, or to interfere with the child’s education, or to be harmful to the child’s health or physical, mental, spiritual, moral, or social development. Where the relevant labour Laws of the Country have provisions for employment of minors, the Contractor shall follow those Laws applicable to the Contractor.”

EXAMPLE SUB-CLAUSE FOR EMPLOYMENT RECORDS OF WORKERS

“The Contractor shall keep complete and accurate records of the employment of labour at the Site. The records shall include the names, ages, genders, hours worked and wages paid to all workers. These records shall be summarised on a monthly basis and submitted to the Employer’s Representative. These records shall be included in the details to be submitted by the Contractor under Sub-Clause 6.10 [ Contractor’s Records ].”

EXAMPLE SUB-CLAUSE FOR WORKERS’ ORGANISATIONS

“In countries where the relevant labour Laws recognise workers’ rights to form and to join workers’ organisations of their choosing without interference and to bargain collectively, the Contractor shall comply with such Laws. Where the relevant labour Laws substantially restrict workers’ organisations, the Contractor shall enable alternative means for the Contractor’s Personnel to express their grievances and protect their rights regarding working conditions and terms of employment. In either case described above, and where the relevant labour Laws are silent, the Contractor shall not discourage the Contractor’s Personnel from

forming or joining workers’ organisations of their choosing or from bargaining collectively, and shall not discriminate or retaliate against the Contractor’s Personnel who participate, or seek to participate, in such organisations and bargain collectively. The Contractor shall engage with such workers’ representatives. Workers’ organisations are expected to fairly represent the workers in the workforce.”

EXAMPLE SUB-CLAUSE FOR NON-DISCRIMINATION AND EQUAL OPPORTUNITY

“The Contractor shall not make employment decisions on the basis of personal characteristics unrelated to inherent job requirements. The Contractor shall base the employment relationship on the principle of equal opportunity and fair treatment, and shall not discriminate with respect to aspects of the employment relationship, including recruitment and hiring, compensation (including wages and benefits), working conditions and terms of employment, access to training, promotion, termination of employment or retirement, and discipline. In countries where the relevant labour Laws provide for non-discrimination in employment, the Contractor shall comply with such Laws. When the relevant labour Laws are silent on non-discrimination in employment, the Contractor shall meet the requirements under this Sub-Clause. Special measures of protection or assistance to remedy past discrimination or selection for a particular job based on the inherent requirements of the job shall not be deemed discrimination.”

# Clause 7	Plant, Materials and Workmanship

## Sub-Clause 7.7	Ownership of Plant and Materials

If the Contractor is to provide high-value items of Plant and/or Materials under the Contract, consideration may be given to amending this Sub-Clause:

EXAMPLE	Insert at the end of Sub-Clause 7.7:

“No Plant and/or Materials that is the property of the Employer shall be removed from the Site. If it becomes necessary to:

  - remove any item of such Plant from the Site for the purposes of repair, the Contractor shall give a Notice, with reasons, to the Employer’s Representative requesting consent to remove the defective or damaged item off the Site. This Notice shall clearly identify the item of defective or damaged Plant, and shall give details of: the defect or damage to be repaired; the place to which defective or damaged item of Plant is to be taken for repair; the transportation to be used (and insurance cover for such transportation); the proposed inspections and testing off the Site; and the planned duration required before the repaired item of Plant shall be returned to the Site. The Contractor shall also provide any further details that the Employer may reasonably require; or

  - replace any item(s) of such Plant and/or Materials, the Contractor shall give a Notice, with reasons, to the Employer’s Representative clearly identifying the item(s) of Plant and/or Materials to be replaced, and giving details of the due date of delivery to the Site of the replacement item(s).

Where any item of Plant and/or Materials has become the property of the Employer under this Sub-Clause before it has been delivered

to the Site, the Contractor shall ensure that such an item is not moved except for its delivery to the Site.

The Contractor shall indemnify and hold the Employer harmless against and from the consequences of any defect in title or encumbrance or charge (except any reasonable restriction arising from the intellectual property rights of the manufacturer or producer) on any item of Plant and/or Materials that has become the property of the Employer under this Sub-Clause.”

## Additional Sub-Clause

If the Contract is being financed by an institution whose rules or policies require a restriction on the use of its funds, a further sub-clause may be added:

EXAMPLE SUB-CLAUSE FOR GOODS FROM ELIGIBLE SOURCE COUNTRIES

“All Goods shall have their origin in eligible source countries as defined in

[ Insert name of published guidelines for procurement ].

Goods shall be transported by carriers from these eligible source countries, unless exempted by the Employer in writing on the basis of potential excessive costs or delays. Surety, insurance and banking services shall be provided by insurers and bankers from the eligible source countries”.

# Clause 8	Commencement, Delays and Suspension

## Sub-Clause 8.2	Time for Completion

If the Works are to be completed and taken over in stages it is important that each stage is defined as a Section, and the Time for Completion of each Section is stated, in the Contract Data (please also see the guidance below under Sub-Clause 10.1 [ Taking Over the Works and Sections ].

## Sub-Clause 8.3	Programme

It is strongly recommended that the programming software that is preferred by the Employer be clearly identified in the Employer’s Requirements, and that such software is drawn to the attention of tenderers in the Instructions to Tender.

For less complex projects, the Employer may consider simplifying the requirements for the Contractor’s programme as listed in sub-paragraphs (a) to (k) in this Sub-Clause (for example, by replacing sub-paragraphs (a) to (k) in this Sub-Clause with sub-paragraphs (a) to (d) as they appear under Sub-Clause 8.3 [ Programme ] of FIDIC’s Conditions of Contract for EPC/ Turnkey Projects, First Edition 1999).

## Sub-Clause 8.5	Extension of Time for Completion

It should be noted that this Sub-Clause does not entitle the Contractor to any extension of the Time for Completion for adverse climatic conditions. If it is preferable that the Contractor is to be entitled to EOT for “exceptionally adverse climatic conditions”, consideration may be given to:

- adding the provisions of sub-paragraph (c) of Sub-Clause 8.5 [ Extension of Time for Completion ] of FIDIC’s Conditions of Contract for Plant and Design-Build, Second Edition 2017 to this Sub-Clause; and

- setting out in the Employer’s Requirements what constitutes an “exceptionally adverse” event – for example, by reference to available weather statistics and return

periods. It may also be appropriate to compare the adverse climatic conditions that have been encountered with the frequency with which events of similar adversity have previously occurred at or near the Site. For example, an exceptional degree of adversity might be regarded as one which has a probability of occurrence of once every four or five times the Time for Completion of the Works (for example, once every eight to ten years for a two-year contract).

The final paragraph of this Sub-Clause provides that the rules and procedures for assessing the Contractor’s entitlement to an EOT where there is concurrency between delays attributable to both Parties shall be stated in the Special Provisions. This provision has been drafted by FIDIC in this manner because there is no one standard set of rules/procedures in use internationally (though, for example the approach given in the Delay and Disruption Protocol published by the Society of Construction Law (UK): https://www.scl.org.uk/sites/default/files/SCL_Delay_Protocol_2nd_Edition_Final.pdf†	is increasingly being adopted internationally and different rules/procedures may apply in different legal jurisdictions).

In preparing the Special Provisions, therefore, it is strongly recommended that the Employer be advised by a professional with extensive experience in construction programming, analysis of delays and assessment of extension of time in the context of the governing law of the Contract.

## Sub-Clause 8.8	Delay Damages

Under the laws of many countries or other jurisdictions, the amount of these pre-defined damages must be a reasonable estimate of the anticipated or actual loss caused to the Employer by the delay. Therefore if the Delay Damages are fixed at an unreasonably large amount, they may be unenforceable in common law jurisdictions or subject to downward adjustment in civil law jurisdictions.

If the Contract Price stated in the Contract Agreement is to be quoted as the sum of figures in more than one currency, it may be preferable to define these damages (per day) as a percentage to be applied to each of these figures. If the Contract Price stated in the Contract Agreement is expressed in the Local Currency, the damages per day may either be defined as a percentage or be defined as a figure in Local Currency: see Sub-Clause 14.15(c).

## Additional Sub-Clause

Incentives for early completion may be included (in addition to sub-paragraph (a) of Sub-Clause

  - [ Value Engineering ] which refers to accelerated completion):

EXAMPLE SUB-CLAUSE FOR INCENTIVES FOR EARLY COMPLETION

“The Contractor shall be entitled to a bonus payment if the Works and/or each Section is completed earlier than the Time for Completion for the Works or Section (as the case may be). The amount of bonus for early completion of the Works and/or each Section is stated in the Employer’s Requirements.

For the purposes of calculating any bonus payment, the applicable Time for Completion stated in the Contract Data is fixed and no adjustments of this time by reason of granting an EOT will be allowed.”

# Clause 9	Tests on Completion

## Sub-Clause 9.1	Contractor’s Obligations

The Employer’s Requirements should describe the tests which the Contractor is to carry out

before being entitled to a Taking Over Certificate. It may also be appropriate for the Contractor to include, in documents submitted with the Tender, detailed arrangements, instrumentation, etc. If the Works are to be tested and taken over in Sections, it is strongly recommended that consideration be given to testing requirements in the Employer’s Requirements that take due account of the effect of other parts of the Works being incomplete.

The Employer may wish the Employer’s permanent operating and maintenance personnel to witness the operational tests and/or trial operation (including during the training of the Employer’s Personnel under Sub-Clause 5.5 [ Training ]), in which case, this should be clearly stated in the Employer’s Requirements.

The wording in sub-paragraphs (a) to (c) of this Sub-Clause includes the conditions which are typically applicable for a plant contract, but otherwise may require amendment. In particular, sub-paragraph (c) refers to trial operation, during which any product produced by the Works becomes the property of the Employer. As such, the Employer becomes responsible for disposing of such product, and entitled to retain the proceeds if the product is sold. If the product is to be retained by the Contractor, this Sub-Clause should be amended accordingly.

For less complex projects, the Employer may consider simplifying the testing requirements under this Sub-Clause.

# Clause 10	Employer’s Taking Over

## Sub-Clause 10.1	Taking Over the Works and Sections

If the Works are to be completed and taken over in stages it is important that each stage is defined as a Section in the Contract Data. Precise geographical definitions are advisable, and the Contract Data should include a table to also define for each Section:

- the relevant percentage for release of Retention Money,

- the Time for Completion, and

- the applicable Delay Damages.

An example form of such a table is shown in the example form of Contract Data included in this publication.

# Clause 11	Defects after Taking Over

## Sub-Clause 11.3	Extension of Defects Notification Period

Depending on the complexity of the project and the nature of the Works, the Employer may consider amending the period of “two years” stated at the end of the first paragraph of this Sub-Clause to be a longer or a shorter period.

## Sub-Clause 11.10	Unfulfilled Obligations

It may be necessary to review the effect of this Sub-Clause in relation to the period of liability imposed by the applicable law.

In particular, the second paragraph of this Sub-Clause may require amending to take account of the applicable law.

## Additional Sub-Clause

If the Works include the Plant that comprises (in whole or in part) new or innovative technology in the Country or at the Employer’s location, consideration may be given to including in the Employer’s Requirements a requirement for the Contractor to provide supervisory assistance to the Employer’s permanent operating personnel in the operation and maintenance of the Plant during the DNP of the Works.

EXAMPLE SUB-CLAUSE FOR SUPERVISORY ASSISTANCE DURING DNP

“The Contractor shall provide supervisory assistance to the Employer during the DNP for the Works. Such supervisory assistance shall be as described in the Employer’s Requirements for the purpose of supporting the Employer’s operation and maintenance of the Plant for the period of [ insert number of months ] after the Date of Completion.”

# Clause 12	Tests after Completion

## Sub-Clause 12.1	Procedure for Tests after Completion

In an EPC turnkey project, the Contractor is typically required to prove the reliability and performance of the Plant during the Tests on Completion, and the Works are only taken over after successful completion of these tests. Exceptionally, it may be considered necessary for Tests after Completion to be carried out after the Employer has taken over and operated the Works, so that the guaranteed performance can be demonstrated under normal operating conditions: for example, after operational fouling of the plant.

The Employer’s Requirements should describe the tests the Employer requires the Contractor to carry out after taking-over to verify that the Works fulfil the Employer’s performance requirements. For some types of Works, these Tests may be the most difficult to specify well, although they are critical to a successful outcome. It may be appropriate for the Instructions to Tenderers to require tenderers to include, in the documents to be submitted with the Tender, detailed arrangements, and/or to define and allow for the provision of any instrumentation or other items required in addition to that included in the Plant, to demonstrate compliance with the Employer’s performance requirements.

With many types of Works, it is essential to specify, in the Schedule of Performance Guarantees, the performance criteria which the Plant will be required to achieve. In such cases, the Instructions to Tenderers should include information on the base physical input conditions (such as raw water quality for a water treatment Plant) the Contractor can rely on to design and construct the facility to achieve such performance criteria.

The provisions in the General Conditions are based upon the Tests after Completion being carried out by the Contractor, with the assistance of the Employer as regards personnel, consumables, etc. These details may need to be specified in the Employer’s Requirements. If other arrangements are envisaged, they should be specified in the Employer’s Requirements, and this Sub-Clause should be amended accordingly. For example, the provisions of Sub-Clause 12.1 in FIDIC’s Conditions of Contract for Plant and Design-Build, Second Edition 2017 are based upon these Tests being carried out by the Employer and his operating personnel, with guidance from the Contractor’s staff.

If the works of a Section are to be tested under this Sub-Clause, it is strongly recommended that consideration be given to testing requirements in the Employer’s Requirements that take due account of the effect of other parts of the Works being incomplete.

The Tests after Completion may comprise:

    - performance tests – to be carried out shortly after taking-over (the exact timing of such tests should be specified in the Employer’s Requirements or as otherwise stated in the O&M Manuals referred to under sub-paragraph (f)(iii) of this Sub-Clause), to measure the performance of the Works or Section against the performance criteria specified under the Contract; and

    - availability tests – to be carried out during an initial period of the DNP (which period should be specified in the Employer’s Requirements), to measure the availability of the Works or Section during that period.

In some jurisdictions there may be a requirement under the applicable law for mandatory testing of the Works after taking-over and before operation. If this is the case, it is essential that it is drawn to tenderers’ attention in the Instruction to Tenderers, giving details of such mandatory testing.

## Sub-Clause 12.4	Failure to Pass Tests after Completion

If the first paragraph of this Sub-Clause is to apply, the method of calculating the Performance Damages (based on the extent of the failure) should be defined in the Schedule of Performance Guarantees, which should also clearly specify the minimum acceptable performance criteria.

# Clause 13	Variations and Adjustments

Variations can be initiated by any of three ways:

- the Contractor may initiate his own proposals under Sub-Clause 13.2 [ Value Engineering ], which are intended to benefit both Parties;

- the Employer may instruct Variations under Sub-Clause 13.3.1 [ Variation by Instruction ]; or

- the Employer may request a proposal from the Contractor under Sub-Clause 13.3.2 [ Variation by Request for Proposal ].

## Sub-Clause 13.4	Provisional Sums

Provisional Sums may be required for parts of the Works which are not required to be priced at the risk of the Contractor. For example, a Provisional Sum may be necessary to cover goods or services which the Employer wishes to select after award of the Contract, or to deal with a major uncertainty regarding sub-surface conditions. It is essential to define the scope of each Provisional Sum (it is recommended that this be included in a Schedule prepared by the Employer), since the amount of each Provisional Sum corresponding to the defined scope will then be excluded from the other elements of the Contract Price stated in the Contract Agreement.

## Sub-Clause 13.7	Adjustments for Changes in Cost

The provision for adjustments under this Sub-Clause may be required if it would be unreasonable for the Contractor to bear the risk of escalating costs due to inflation.

If the amounts payable to the Contractor are to be adjusted for rises or falls in the cost of labour, Goods and other inputs to the Works, for this Sub-Clause to apply it is important that a Schedule (or Schedules) of cost indexation is (are) included in the Contract and that such Schedule(s) include a formula or formulae for calculation of the applicable adjustment under this Sub-Clause.

For a plant contract, it may be preferable to adopt a formula or formulae which is/are more directly related to the timing of the costs incurred by manufacturers.

It is recommended that the Employer be advised by a professional with experience in construction costs and the inflationary effect on construction costs when preparing the contents of the Schedule(s) of cost indexation.

SCHEDULE OF COST INDEXATION: EXAMPLE FORMULA FOR ADJUSTMENT FOR CHANGE IN COST

| Pn = a + b | Ln + c | En | + d | Mn +...... |
| --- | --- | --- | --- | --- |
|  | Lo | Eo |  | Mo |

where:

“Pn” is the adjustment multiplier to be applied to the estimated contract value in the relevant currency of the work carried out in period “n”, this period being a month;

“a” is a fixed coefficient, representing the non-adjustable portion in contractual payments;

“b”, “c”, “d”, … are coefficients representing the estimated proportion of each cost element related to the execution of the Works, such tabulated cost elements may be indicative of resources such as labour, equipment and materials;

(particular care should be taken in the calculation of the weightings/ coefficients (“a”, “b”, “c”,...,) the total of which must not exceed unity)

“Ln”, “En”, “Mn”, … are the current cost indices or reference prices (stated in the Schedule of cost indexation) for period “n”, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the date 49 days prior to the last day of the period (to which the particular payment relates); and

“Lo”, “Eo”, “Mo”, … are the base cost indices or reference prices, expressed in the relevant currency of payment, each of which is applicable to the relevant tabulated cost element on the Base Date.

The weightings (coefficients) for each of the factors of cost stated in the following table(s) of adjustment data shall only be adjusted if they have been rendered unreasonable, unbalanced or inapplicable, as a result of Variations.

Table(s) of adjustment data for payments each month/[ YEAR ] (delete as appropriate) in	(currency)

Coefficient; scope of index

Country of origin; currency of index

Source of index; Title/definition

Value on stated date(s)*

Value	Date

a= 0.10  Fixed

b= 	Labour c=

d= e=

* These values and dates confirm the definition of each index, but do not define Base Date indices

# Clause 14	Contract Price and Payment

The procedures and timing for making payments under this Clause 14 should be checked to ensure that they are acceptable to both the Employer and any financing institution the Employer may be using to fund the project.

## Sub-Clause 14.1	The Contract Price

When writing the Special Provisions, consideration should be given to the amount and timing of payment(s) to the Contractor. A positive cash-flow is clearly of benefit to the Contractor, and tenderers will take account of the interim payment procedures when preparing their tenders.

Normally, an EPC/turnkey contract is based on a lump sum price, with little or no measurement. The Contractor thus takes the risk of changes in cost arising from the Contractor’s design. The

lump sum price may consist of two or more amounts, quoted in the currencies of payment (which may, but need not, include the Local Currency).

In order to value Variations, tenderers may be required to include in their Tenders detailed price break-downs, including quantities, unit rates and other pricing information. This information can also be useful for the assessment of interim payments but may not have been priced competitively. When the tender documents are being prepared, the Employer must therefore decide whether he/she will accept being bound by the tenderer’s price break-downs. If not, the Employer should ensure that the Employer’s Representative has the necessary expertise to value any Variations which may be required.

Additional Sub-Clauses may be required to cover any exceptions to the provisions set out in Sub-Clause 14.1, and any other matters relating to payment.

If the Contractor is not required to pay import duties on Goods imported by the Contractor into the Country, an additional Sub-Clause should be added and sub-paragraph (b) of Sub-Clause

  - [ The Contract Price ] of the General Conditions should be amended accordingly:

EXAMPLE SUB-CLAUSE FOR EXEMPTION FROM DUTIES

“All Goods imported by the Contractor into the Country shall be exempt from customs and other import duties, if the Employer’s prior written approval is obtained for import. The Employer shall endorse the necessary exemption documents prepared by the Contractor for presentation in order to clear the Goods through Customs, and shall also provide the following exemption documents:

(describe the necessary documents, which the Contractor will be unable to prepare)

If exemption is not then granted, the customs duties payable and paid shall be reimbursed by the Employer.

All imported Goods, which are not incorporated in or expended in connection with the Works, shall be exported on completion of the Contract.

If not exported, the Goods will be assessed for duties as applicable to the Goods involved in accordance with the Laws of the Country.

However, exemption may not be available for:

    - Goods which are similar to those locally produced, unless they are not available in sufficient quantities or are of a different standard to that which is necessary for the Works; and

    - any element of duty or tax inherent in the price of goods or services procured in the Country, which shall be deemed to be included in the Contract Price stated in the Contract Agreement.

Port dues, quay dues and, except as set out above, any element of tax or duty inherent in the price of goods or services shall be deemed to be included in the Contract Price stated in the Contract Agreement.”

If expatriate staff are exempted from paying local income tax, a suitable Sub-Clause should be added and sub-paragraph (b) of Sub-Clause 14.1 [ The Contract Price ] of the General

Conditions should be amended accordingly. However, advice should be sought from a qualified tax expert before drafting any such additional Sub-Clause.

EXAMPLE SUB-CLAUSE FOR EXEMPTION FROM TAXES

“Expatriate (foreign) personnel shall not be liable for income tax levied in the Country on earnings paid in any foreign currency, or for income tax levied on subsistence, rentals and similar services directly furnished by the Contractor to Contractor’s Personnel, or for allowances in lieu. If any Contractor’s Personnel have part of their earnings paid in the Country in a foreign currency, they may export (after the conclusion of their term of service on the Works) any balance remaining of their earnings paid in foreign currencies.

The Employer shall seek exemption for the purposes of this Sub-Clause. If it is not granted, the relevant taxes paid shall be reimbursed by the Employer.”

## Sub-Clause 14.2	Advance Payment

When writing the Particular Conditions, consideration should be given to the benefits of the Employer making an advance payment to the Contractor. Unless this Sub-Clause is not to apply, the advance payment and the currencies in which it is to be paid must be specified in the Contract Data. The rate of deduction for the repayments should be checked to ensure that repayment is achieved before the Contractor’s completion of the Works. The typical figures in sub-paragraphs (a) and (b) of Sub-Clause 14.2.3 [ Repayment of Advance Payment ] of the General Conditions are based on the assumption that the advance payment is less than 22% of the Contract Price stated in the Contract Agreement.

The acceptable form of Advance Payment Guarantee should be included in the tender documents, annexed to the Particular Conditions: an example form is included at the end of this publication (in the section “Forms”).

If the Employer wishes to provide the advance payment in instalments, the Contract Data and this Sub-Clause will need to be amended.

EXAMPLE	The Contract Data:

- delete the words “14.2	total amount of Advance Payment (as a

percentage of the final Contract Price):	” and replace with:

“14.2	total Advance Payment of the

Contract Price stated in the

Contract Agreement		%

  - number and timing of instalments: 	”.

- delete the words “14.2 ………. currency or currencies of Advance Payment	” and replace with:

14.2 ………….	currencies and proportions		% in

% in 	”.

Delete the second sentence of the second paragraph of Sub-Clause 14.2 and replace with:

“The total amount of the advance payment, the number and timing of instalments, and the applicable currencies and proportions shall be as stated in the Contract Data.”.

Sub-Clause 14.2.1 [ Advance Payment Guarantee ]:

- delete the words “equal to the advance payment” from the first sentence and replace with: “equal to the total amount of the advance payment”.

- in the second paragraph before “the advance payment has been repaid” add the words: “the total amount of”.

- in the third paragraph before “the advance payment has not been repaid” add the words: “the total amount of”.

- in sub-paragraph (a) before “the advance payment has been repaid” add the words: “the total amount of”.

- in the last sentence, before “the advance payment” add the words: “the first instalment of”.

Sub-Clause 14.2.2 [ Advance Payment ]:

- in the first sentence before “the advance payment” add the words: “the first instalment of”.

- delete sub-paragraph (b) replace with: “(b) the Employer has received a copy of the Contractor’s application for the first instalment of the advance payment.”

- at the end of this Sub-Clause add the following wording: “Thereafter, the Employer shall pay each subsequent instalment of the advance payment, which the Contractor is entitled to under the Contract, within 14 days after the Employer has received the Contractor’s application (in the form of a Statement) for that instalment of advance payment.”

Sub-Clause 14.2.3 [ Repayment of Advance Payment ]:

- in the last sentence before “the advance payment has not been repaid” add the words: “the total amount of”.

## Sub-Clause 14.4	Schedule of Payments

The General Conditions contain provisions for interim payments to the Contractor, which may be based on a Schedule of Payments. If another basis is to be used for determining interim valuations, details should be added in the Special Provisions.

If payments are to be specified in a Schedule of Payments, consideration may be given to the Schedule of Payments being in one of the following forms:

- an amount, or percentage of the estimated final Contract Price, for each month (or other period) during the Time for Completion (but this can prove unreasonable if the Contractor’s progress differs significantly from the expectation on which the Schedule was based); or

- amounts based on the actual progress achieved by the Contractor in executing the Works, which necessitates careful definition of the payment milestones (but disagreements may arise when the work required for a payment milestone is nearly achieved but the balance of the work, albeit minor, cannot be completed until some months later).

The figures inserted by a tenderer in the Schedule of Payments may be compared with his/ her tender programme (if any), in order to assess whether they are reasonably consistent with each other.

Alternatively, if the Works consist of only a few different types of operations, a simple measurement approach for interim valuations may be appropriate.

EXAMPLE SUB-CLAUSE FOR INTERIM VALUATION PROCEDURE

Prior to commencing construction of the Permanent Works, the Contractor shall submit a bill of principal quantities of the Permanent Works (the “BPQPW”), together with any supporting information and calculations reasonably required by the Employer. The BPQPW shall include the anticipated final quantities of the principal items of Permanent Works, which shall have been priced using all-in rates such that the total amount equals the estimated final Contract Price. The BPQPW shall not contain priced items for design or for Temporary Works. The value of each element of this work, and of any other work elements not described in the BPQPW, shall each be included in the rates for Permanent Works which are to be constructed after the element is carried out.

The BPQPW shall be subject to review and a Notice of No-objection by the Employer, and shall be without prejudice to the final amount due under the Contract. The BPQPW shall be revised and reissued by the Contractor if it appears at any time before Taking-Over that it will not fully represent the Permanent Works when complete.

During the Time for Completion, the contract value for the purposes of sub-paragraph (i) of Sub-Clause 14.3 [ Application for Interim Payment ] shall not exceed the amount calculated from the current BPQPW, based on the quantities of Permanent Works which have been constructed in accordance with the Contract. Each Statement shall:

  - be in the same form as that of the current BPQPW,

  - include statement signed by the Contractor’s Representative that the current BPQPW (including anticipated final quantities) and the as-constructed quantities are all correct, and

  - be accompanied by a certificate signed by the Contractor’s Representative, certifying that the part of the Permanent Works constructed to date complies with the Contract.

## Sub-Clause 14.7	Payment

Periods for payment should be long enough for the Employer to meet, but not so long as to prejudice the Contractor’s positive cash-flow.

If the country or countries of payment need to be specified, details may be included in a Schedule.

## Sub-Clause 14.8	Delayed Payment

As an alternative to the second paragraph of this Sub-Clause, consideration may be given to the payment of the Contractor’s actual financing Costs, taking account of local financing arrangements.

## Sub-Clause 14.9	Release of Retention Money

If part of the Retention Money is to be released and substituted by an appropriate guarantee, an additional Sub-Clause may be added. The acceptable form(s) of guarantee should be included in the tender documents, annexed to the Particular Conditions: an example form is included at the end of this publication (in the section “Forms”). Also, a limit of Retention Money should be stated in the Contract Data.

EXAMPLE SUB-CLAUSE FOR RELEASE OF RETENTION

When the Retention Money has reached three-fifths (60%) of the limit of Retention Money stated in the Contract Data, after the Employer has received the guarantee referred to below the Employer shall make payment of half (50%) of the limit of Retention Money to the Contractor.

The Contractor shall obtain (at the Contractor’s cost) a guarantee in amounts and currencies equal to half (50%) of the limit of Retention Money stated in the Contract Data, and shall submit it to the Employer. This guarantee shall be issued by an entity and from within a country (or other jurisdiction) to which the Employer gives consent, and shall be based on the sample form included in the tender documents or on another form agreed by the Employer (but such consent and/or agreement shall not relieve the Contractor from any obligation under this Sub-Clause).

The Contractor shall ensure that the guarantee is valid and enforceable until the Contractor has executed the Works, as specified for the Performance Security in Sub-Clause 4.2.1. If the terms of the guarantee specify an expiry date, and the Contractor has not so executed the Works by the date 28 days before the expiry date, the Contractor shall extend the validity of the guarantee.

The release of Retention Money under this Sub-Clause shall be in lieu of the release of the second half of the Retention Money under the second paragraph of Sub-Clause 14.9 [ Release of Retention Money ].

## Sub-Clause 14.15	Currencies of Payment

If all payments are to be made in Local Currency, this currency must be named in the Contract Agreement, and this Sub-Clause may be replaced:

EXAMPLE SUB-CLAUSE FOR A SINGLE CURRENCY CONTRACT

All payments made in accordance with the Contract shall be in Local Currency. The Local Currency payments shall be fully convertible, except those for local costs. The percentage attributed to local costs shall be as stated in the Contract Data.

## Financing Arrangements

For major contracts in some markets, there may be a need to secure finance from entities such as aid agencies, development banks, export credit agencies, or other international financing institutions. If financing is to be procured from any of these sources, the Special Provisions may need to incorporate the financing institution’s special requirements. The exact wording will depend on the relevant institution, so reference will need to be made to the institution to ascertain its requirements, and to seek approval of the draft tender documents.

These requirements may include tendering procedures which need to be adopted in order to render the eventual contract eligible for financing, and/or additional Sub-Clauses which may need to be incorporated into the Special Provisions. The following examples indicate some of the topics which the institution’s requirements may cover:

- prohibition from discrimination against the shipping companies of any one country;

- ensuring that the Contract is subject to a widely-accepted neutral law;

- provision for arbitration under recognised international rules and at a neutral location;

- giving the Contractor the right to suspend/terminate in the event of default under the financing arrangements;

- restricting the right to reject Plant;

- specifying the payments due in the event of termination;

- specifying that the Contract does not become effective until certain conditions precedent have been satisfied, including pre-disbursement conditions for the financing arrangements; and

- obliging the Employer to make payments from his own resources if, for any reason, the funds under the financing arrangements are insufficient to meet the payments due to the Contractor, whether due to a default under the financing arrangements or otherwise.

The financing institution may wish the Contract to include references to the financing arrangements, especially if funding from more than one source is to be arranged to finance different elements of supply. It is not unusual for the Special Provisions to include particular provisions identifying different categories of Works and specifying the documents to be presented to the relevant financing institution to obtain payment. If the financing institution’s requirements are not met, it may be difficult (or even impossible) to secure suitable financing for the project, and/or the institution may decline to provide finance for part or all of the Contract.

Where the financing is not tied to the export of goods and services from any particular country but is simply provided by commercial banks lending to the Employer, those banks may need to ensure that the Contractor’s rights are very restricted.

Alternatively, the Contractor may be prepared to initiate financing arrangements for the Contract and retain responsibility for them, although the Contractor would probably be unable or unwilling to provide finance from the Contractor’s own resources. The Contractor’s financing bank’s requirements are then likely to affect the Contractor during contract negotiations. For example, the financing bank may require the Employer to make interim payments, although a large proportion of the Contract Price might be withheld until the Works are complete. Since the Contractor would then have to arrange financing to cover the shortfall between the payments and the Contractor’s outgoings, the Contractor (and the financing bank) would probably require some form of security from the Employer, guaranteeing payment when due.

It may be appropriate for the Employer, when preparing the tender documents, to anticipate the latter requirement by undertaking to provide a guarantee for the element of payment which the Contractor is to receive when the Works are complete. The acceptable form(s) of guarantee should be included in the tender documents, annexed to the Particular Conditions: an example form is included at the end of this publication (in the section “Forms”). The following Sub-Clause may be added.

EXAMPLE SUB-CLAUSE FOR CONTRACTOR FINANCE

“The Employer shall obtain (at the Employer’s cost) a payment guarantee in the amount and currencies, and provided by an entity, as stated in the Contract Data. The Employer shall deliver the guarantee to the Contractor within 28 days after both Parties have entered into the Contract Agreement. The guarantee shall be in the form annexed to these Special Provisions, or in another form acceptable to the Contractor. Unless and until the Contractor receives the guarantee, the Employer’s Representative shall not give the notice under Sub-Clause 8.1 [ Commencement of Works ].

The guarantee shall be returned to the Employer at the earliest of the following dates:

- when the Contractor has been paid theContract Price;

- when obligations under the guarantee expire or have been discharged; or

- when the Employer has performed all obligations under the Contract.”

# Clause 15	Termination by Employer

## Sub-Clause 15.2	Termination for Contractor’s Default

Before inviting tenders, the Employer should verify that the wording of this Sub-Clause, and each anticipated ground for termination, is consistent with the law governing the Contract.

## Sub-Clause 15.2.1	Notice

Sub-paragraph (h) in this Sub-Clause is intended to include situations where the Contractor or any of the Contractor’s employees, agents, Subcontractors or Contractor’s Personnel gives or offers to give (directly or indirectly) to any person any bribe, gift, gratuity, commission or other thing of value, as an inducement or reward for showing or forbearing to show favour or disfavour to any person in relation to the Contract. However, this is not intended to include lawful inducements and rewards by the Contractor to the Contractor’s Personnel.

## Sub-Clause 15.2.3	After termination

If the Employer has made available any Employer-Supplied Materials and/or Employer’s Equipment in accordance with Sub-Clause 2.6, consideration should be given to an additional sub-paragraph under this Sub-Clause:

EXAMPLE	Insert the following new sub-paragraph at the end of sub-paragraph

(b) of Sub-Clause 15.2.3:

“(iv) all Employer-Supplied Materials and/or Employer’s Equipment made available to the Contractor in accordance with Sub-Clause 2.6 [ Employer-Supplied Materials and Employer’s Equipment ], and”.

## Sub-Clause 15.5	Termination for Employer’s Convenience

In many jurisdictions under the applicable law it may not be permissible for the Employer to terminate the Contract for convenience (termination of the Contract only being permitted in the event of default on the part of the Contractor and, thereafter, arranging an equitable, non-discriminatory and transparent procurement process to select a replacement contractor). Therefore, before inviting tenders the Employer should verify that the wording of this Sub-Clause is consistent with the law governing the Contract.

# Clause 16	Suspension and Termination by Contractor

## Sub-Clause 16.2	Termination by Contractor

Before inviting tenders, the Employer should verify that the wording of this Sub-Clause is consistent with the law governing the Contract.

## Sub-Clause 16.2.1	Notice

Sub-paragraph (i) in this Sub-Clause is intended to include situations, where the Employer or any of the Employer’s employees, agents or Employer’s Personnel gives or offers to give (directly or indirectly) to any person any bribe, gift, gratuity, commission or other thing of value, as an inducement or reward for showing or forbearing to show favour or disfavour to any person in relation to the Contract. However, this is not intended to include lawful inducements and rewards by the Employer to the Employer’s Personnel.

## Sub-Clause 16.3	Contractor’s Obligations After Termination

If the Employer has made available any Employer-Supplied Materials and/or Employer’s Equipment in accordance with Sub-Clause 2.6, consideration should be given to amending this Sub-Clause:

EXAMPLE	Delete sub-paragraph (c) in Sub-Clause 16.3 and replace with:

“(c) deliver to the Employer’s Representative all Employer-Supplied Materials and/or Employer’s Equipment made available to the Contractor in accordance with Sub-Clause 2.6 [ Employer-Supplied Materials and Employer’s Equipment ]; and

- remove all other Goods from the Site, except as necessary for safety, and leave the Site.”

# Clause 17	Care of the Works and Indemnities

## Sub-Clause 17.4	Indemnities by Contractor

In respect of the Contractor’s obligation to indemnify under the second paragraph of this Sub-Clause, it should be noted that:

- as this liability is not excluded under the first paragraph of Sub-Clause 1.14 [ Limitation of Liability ], the Contractor has no liability for any indirect or consequential loss or damage suffered by the Employer as a result of any negligence by the Contractor in designing the Works to be fit for purpose;

- as this liability is not excluded under the second paragraph of Sub-Clause 1.14 [ Limitation of Liability ], it falls within the Contractor’s limitation of liability under Sub-Clause 1.14; and

- this liability may be covered by the insurance to be taken out by the Contractor under Sub-Clause 19.2.3 [ Liability for breach of professional duty ], in which case a statement to this effect should be included in the Contract Data.

## Additional Sub-Clause

If the Contractor is to be allowed to use and/or occupy any of the Employer’s facilities and/ or accommodation temporarily during the Contract, it is recommended that an additional sub-clause be added to Clause 17 to cover the responsibility for care of such facilities and/ or accommodation:

EXAMPLE SUB-CLAUSE FOR CONTRACTOR’S USE OF EMPLOYER’S FACILITIES/ ACCOMMODATION

“The Contractor shall take full responsibility for the care of the items of the Employer’s facilities and/or accommodation listed below, from the date of use and/or occupation by the Contractor until the date on which such use and/or occupation is re-vested in the Employer.

[ List of items and details ]

If any loss or damage happens to any of the above items during a time when the Contractor is responsible for its care, arising from any cause other than a cause for which the Employer is responsible or liable, the Contractor shall promptly rectify the loss or damage at the Contractor’s risk and cost.”

# Clause 19	Insurance

If the Employer wishes to change the insurance provisions of this Clause – for example by providing some of the insurance cover under the Employer’s own policy(ies) – it will be necessary to review and revise the relevant Sub-Clause(s) under this Clause 19.

If this is the case, it is strongly recommended that:

- the tender documents include details of such insurances as an annex to the Special Provisions so that tenderers can estimate what other insurances they may wish to have for their own protection. The details should include the conditions of insurance, limits, exceptions and deductibles; preferably in the form of a copy of each insurance policy; and

- the Employer is advised by a professional with extensive experience in construction insurance and liability in the preparation of the wording of the revised sub-clauses. If the insurance provisions are changed without due care and attention, there is a risk that the Employer will inadvertently carry liabilities for which the Employer is neither prepared nor covered by insurance.

# Clause 20	Employer’s and Contractor’s Claims

## Sub-Clause 20.1	Claims

In respect of any Claim under sub-paragraph (c) of this Sub-Clause, it should be noted that “another entitlement or relief …or the execution of the Works” may include such matters as:

- interpretation of a provision of the Contract,

- rectification of an ambiguity or discrepancy found in the Contract documents,

- a declaration in favour of the claiming Party,

- access to the Site or to places where the Works are being (or to be) carried out, and/ or

- any other matter of entitlement under the Conditions of Contract or in connection with, or arising out of, the Contract that does not involve additional payment by one Party to the other Party and/or EOT and/or extension of the DNP.

Consideration may be given to replacing the words “within a reasonable time” in the last paragraph of this Sub-Clause with a specified time period.

# Clause 21	Disputes and Arbitration

## Sub-Clause 21.1	Constitution of the DAAB

It is generally accepted that construction projects depend for their success on the avoidance of Disputes between the Employer and the Contractor and, if Disputes do arise, the timely resolution of such Disputes.

Therefore, the Contract should include the provisions under Clause 21 which, while not discouraging the Parties from reaching their own agreement on Disputes as the Works proceed, allow them to bring contentious matters to an independent and impartial dispute avoidance/adjudication board (“DAAB”) for resolution.

The provisions of this Sub-Clause are intended to provide for the appointment of the DAAB, and FIDIC strongly recommends that the DAAB be appointed, as a ‘standing DAAB’ – that is, a DAAB that is appointed at the start of the Contract who visits the Site on a regular basis

and remains in place for the duration of the Contract to assist the Parties:

- in the avoidance of Disputes, and

- in the ‘real-time’ resolution of Disputes if and when they arise

to achieve a successful project.

It is for this reason that, under the first paragraph of this Sub-Clause, the Parties are under a joint obligation to appoint the member(s) of the DAAB within 28 days after the Parties signed the Contract Agreement if no other time is stated in the Contract Data. That said, it is preferable that the member(s) of the DAAB are appointed before signing the Contract Agreement.

At an early stage in the Employer’s planning of the project, consideration should be given as to whether a sole-member DAAB or a three-member DAAB is preferable for a particular project, taking account of its size, duration and the fields of expertise which will be involved.

This Sub-Clause provides for two alternative arrangements for the DAAB:

- a sole-member DAAB of one natural person, who has entered into a tripartite agreement with both Parties;

or

- a three-member DAAB of three natural persons, each of whom has entered into a tripartite agreement with both Parties.

The tripartite agreement above is referred to as the DAAB Agreement under the Conditions of Contract. It is recommended that the form of this agreement is the example form included at the end of this publication (in the section “Forms”).

It should be noted that the form of the DAAB Agreement incorporates (by reference) the General Conditions of DAAB Agreement with its Annex DAAB Procedural Rules, which are included as the Appendix to the General Conditions in this publication.

Under either of these alternative forms of DAAB Agreement, each natural person of the DAAB is referred to as a DAAB member.

A very important factor in the success of the dispute avoidance/adjudication procedure is the Parties’ confidence in the agreed individual(s) who will serve on the DAAB. Therefore, it is essential that candidates for this position are not imposed by either Party on the other Party. The appointment of the DAAB is facilitated by the provision in the Contract Data for each Party to name potential DAAB members. It is important that the Employer and the Contractor each avail himself/herself of the opportunity at the tender stage of the Contract to name potential DAAB members in the Contract Data.

The Contract Data includes two lists for potential DAAB members to be named: one for the Employer to list three names, the other for the Contractor to list three names. This ensures that both Parties have equal opportunity to put forward (the same number of) names for potential DAAB members, and so avoid any question that DAAB member(s) may be imposed on one Party by the other Party.

This provides a total of six potential DAAB members from which the sole member or three members (as the case may be) can be selected by the Parties. If it is considered necessary to have a wider selection of DAAB member(s) to choose from, then provision may be made for longer lists in the Contract Data for both the Contractor and the Employer to name (the same number of) additional DAAB members.

If the Parties cannot agree on any DAAB Member or replacement, or cannot agree the terms of the DAAB Agreement with any prospective DAAB Member or replacement, Sub-Clause

21.2 [ Failure to Appoint DAAB Member(s) ] applies. Therefore, unless otherwise agreed by the

Parties, the selection and appointment of the DAAB Member(s) will be made by the President of FIDIC or a person appointed by the President.

FIDIC is very knowledgeable about the nature and purpose of a DAAB and is an impartial entity to make such appointments in circumstances where it has not been possible to appoint the DAAB member or replacement member by the agreement of the Parties.

FIDIC has its appointment rules and maintains a list of approved and experienced adjudicators for this specific purpose: The FIDIC President’s List of Approved Dispute Adjudicators. This list is available to access on FIDIC’s website at fidic.org.

If no potential DAAB members’ names are given in the Contract Data, consideration should be given to stating a time period in the Contract Data that is greater than the default period of 28 days stated in the first paragraph of this Sub-Clause.

The period of 224 days stated in sub-paragraph (i) of this Sub-Clause has been arrived at by taking account of certain time allowances, as follows:

date of termination + 28 days to give a Notice of Claim under Sub-Clause 20.2.1 [ Notice of Claim ]

+ 56 days to submit detailed particulars for the Claim under Sub-Clause 20.2.4 [ Fully detailed Claim ] (the period of “84 days” stated in sub-paragraph (i) of Sub-Clause 20.2.4 is measured from the date that “the claiming Party became aware, or should have become aware of, the event or circumstance” which date, in this instance, will be the date of termination. Therefore, the period of 56 days here takes account of the above 28-day period for giving a Notice of Claim)

+ 28 days to allow for the Engineer to ask for further particulars in respect of the Claim, or for the Parties to agree a longer period for the Engineer’s agreement/determination of the Claim than that allowed under Sub-Clause 3.7 [ Agreement or Determination ] as referred to under Sub-Clause 20.2.5 [ Agreement or determination of the Claim ]

+ 84 days for the Employer’s Representative’s agreement/determination of the Claim under Sub-Clause 3.5 [ Agreement or Determination ]

+ 28 days for a NOD under Sub-Clause 3.5 [ Agreement or Determination ]

= 224 days after the date of termination.

As noted above, FIDIC strongly recommends that the DAAB be appointed at the start of the Contract and remain in place for the duration of the Contract. However, as an alternative to the ‘standing DAAB’ envisaged under this Sub-Clause, the Parties may prefer the dispute board to be appointed on an ‘ad-hoc’ basis. In such case, the dispute board would be appointed when a Dispute arises, its appointment would be limited to resolution of the Dispute, it would have no role to play in the avoidance of Disputes between the Parties, and its appointment would cease when it had given its decision on that Dispute. Should a new Dispute arise, a new ad-hoc DAAB would be appointed. Given that such a dispute board would have no role in dispute avoidance, it is more correctly referred to as a “Dispute Adjudication Board” or “DAB”. If the Parties wish to provide for an ‘ad-hoc DAB’, rather than the recommended ‘standing DAAB’, then the following amendments will be needed:

EXAMPLE	Delete the definitions under Sub-Clause 1.1.22 and 1.1.23 and replace with:

“ “Dispute Adjudication Board” or “DAB” means the person or three persons (as the case may be) so named in the Contract, or appointed under Clause 21.”

and replace all references in the Conditions of Contract to “DAAB” with “DAB”.

Sub-Clause 21.1, plus the Appendix General Conditions of DAAB Agreement with its Annex DAAB Procedural Rules, should be amended to comply with the wording contained in the corresponding provisions of FIDIC’s Conditions of Contract for EPC/Turnkey Projects, First Edition 1999.

Delete Sub-Clause 21.3 [ Avoidance of Disputes ];

in the first paragraph of Sub-Clause 21.4 [ Obtaining DAAB’s Decision ]:

- after the words “If a Dispute arises between the Parties then, ” add:

“after a DAB has been appointed”;

- delete the words “(whether or not any informal discussions have been held under Sub-Clause 21.3 [ Avoidance of Disputes ])”; and

delete sub-paragraph (a) of Sub-Clause 21.4.1 [ Reference of a Dispute to the DAAB ].

To facilitate the appointment of the member(s) of an ‘ad-hoc DAB’, it is important that the Employer and the Contractor each avail themselves of the opportunity at the tender stage of the Contract to name three potential members in the Contract Data.

## Sub-Clause 21.5	Amicable Settlement

In circumstances where the DAAB has given its decision but one or both Parties is/are dissatisfied with the decision, the provisions of this Sub-Clause are intended to encourage the Parties to settle a Dispute amicably, without the need for arbitration.

Rather than considering the 28 day period stated in this Sub-Clause as a ‘cooling-off period’, FIDIC recommends that the Parties avail themselves of this opportunity to actively engage with each other with a view to settling their Dispute.

Such active engagement may be by, for example:

- direct negotiation by senior executives from each of the Parties;

- mediation (please see below);

- expert determination (using, for example, the Expert Rules published by the International Chamber of Commerce (the “ICC”, which is based at 33-43 Avenue du Président Wilson, 75116 Paris, France) https://iccwbo.org/publication/icc-expert- rules-english-version/ †);

- or other form of alternative dispute resolution that is not as formal, time-consuming and costly as arbitration.

In this regard, it is recommended that consideration be given by the Parties to agree to a longer time period than the period of 28 days stated in this Sub-Clause in an effort to arrive at an amicable settlement procedure chosen by the Parties.

Amicable settlement procedures typically depend for their success on the consensual involvement of both Parties, on confidentiality and on both Parties’ acceptance of the particular procedure. Therefore, while it is recommended that both Parties engage actively to settle the Dispute amicably, neither Party should seek to impose the procedure on the other Party.

If the Parties wish to adopt a mediation procedure in their attempt to settle the Dispute amicably, then consideration may be given to the Mediation Rules, 2017 published by the

International Chamber of Commerce (the “ICC”, which is based at 33-43 Avenue du Président Wilson, 75116 Paris, France) https://iccwbo.org/dispute-resolution-services/mediation/ mediation-rules/ †

or, alternatively, to the following mediation rules:

EXAMPLE	MEDIATION RULES

## Appointment of Mediator

If the Parties are unable to agree on the choice of an independent and impartial mediator, or if the chosen mediator is unable or unwilling to act, then unless otherwise agreed by the Parties, either or both Parties may apply to the President of FIDIC or a person appointed by the President, to appoint a mediator.

Once the mediator has been appointed, the Dispute shall immediately be referred to the mediator by the Parties or by either Party.

## Obligations of the Parties

In addition to the Parties’ obligations as set out in the provisions that follow below, during the mediation process the Parties shall engage with the mediator and with each other in co-operation, in a timely manner and in good faith.

## Agreement of the Mediation Timetable

The mediator shall, within 7 days of his/her appointment, or other period as may be proposed by the mediator and agreed by both Parties, consult with the Parties to agree a timetable for the exchange of any relevant information, the date/time/venue of the mediation meeting, and the procedure to be adopted for the negotiations. The agreement of the timetable shall have regard to the period stated under Sub-Clause 21.5 [ Amicable Settlement ] of the Conditions of Contract or as may be amended by the agreement of the Parties.

## Confidentiality

The Parties’ negotiations facilitated by the mediator shall be conducted on a strictly private and confidential basis. Neither Party shall disclose to any third party any detail of the mediation process, including but not limited to: the fact of the mediation, the identity of the mediator, any matter discussed during the mediation process, any information or document exchanged with the mediator, any negotiations during the mediation meeting and/ or the outcome of the mediation.

The mediation, and/or any negotiations taking place during the mediation meeting, shall not be referred to by either Party in any concurrent or subsequent proceedings, unless such negotiations conclude with a written legally binding agreement.

## Written Agreement to be Binding

If the Parties accept the mediator’s recommendations, or otherwise reach agreement on the settlement of the Dispute, such agreement shall be recorded in writing and, once signed by the designated representative(s) of both Parties, shall be binding on the Parties.

## Mediator’s Opinion

If no agreement is reached by the Parties after negotiations have been facilitated by the mediator, either Party may invite the mediator to provide to both Parties a non-binding opinion in writing. Such opinion shall not be used in evidence in any concurrent or subsequent proceedings.

## Costs of Mediation

The Parties will bear their own costs of participating in the mediation, including but not limited to the costs of preparing and submitting evidence to the mediator and attending the mediation meeting.

Each Party shall be responsible for paying one-half of the remuneration of the mediator (and, if the mediator has been appointed by the President of FIDIC or a person appointed by the President, the remuneration of the appointing official).

However, if the mediator finds that a Party has initiated the mediation, or has engaged in the mediation, in a frivolous or vexatious manner, then the mediator shall have the power to order that Party to pay the reasonable costs of the other Party for preparing for and attending the mediation meeting. If these costs cannot be agreed, they will be assessed by the mediator, whose assessment shall be binding on the Parties.

## Sub-Clause 21.6	Arbitration

The Contract should include provisions for the resolution by international arbitration of any Dispute which is not settled amicably by the Parties. In international contracts, international commercial arbitration has numerous advantages over litigation in national courts and is likely to be more acceptable to the Parties.

Careful consideration should be given to ensuring that the international arbitration rules that are chosen are compatible with the provisions of Clause 21 and with the other elements to be set out in the Contract Data. The Arbitration Rules published by the International Chamber of Commerce (the “ICC”, which is based at 33-43 Avenue du Président Wilson, 75116 Paris, France) https://iccwbo.org/dispute-resolution-services/arbitration/rules-of-arbitration/† are frequently incorporated by reference in international contracts.

It is important that the Parties agree on the number of arbitrators and the language of arbitration. In the absence of specific stipulations as to the number of arbitrators and the place of arbitration in the Contract, the International Court of Arbitration of the ICC will decide these matters.

If the arbitration rules published by the United Nations Commission on International Trade Law (“UNCITRAL” which is based at the Vienna International Centre, A-1400 Vienna, Austria) http:// www.uncitral.org/pdf/english/texts/arbitration/arb-rules-revised/arb-rules-revised-2010-e. pdf† or other non-ICC arbitration rules are preferred, it may be necessary to designate, in the Contract Data, an institution to appoint the arbitrators or to administer the arbitration, unless the institution is named (and their role specified) in the arbitration rules. It may also be necessary to ensure, before so designating an institution in the Contract Data, that the institution is prepared to appoint or administer.

For major projects tendered internationally, it is desirable that the place of arbitration be situated in a country other than that of the Employer or Contractor. This country should have a modern and liberal arbitration law and should have ratified a bilateral or multilateral convention (such as the 1958 New York Convention on the Recognition and Enforcement of Foreign

Arbitral Awards), or both, that would facilitate the enforcement of an arbitral award in the states of the Parties.

It may be considered desirable in some cases for other parties to be joined into any arbitration between the Parties or for two or more pending arbitrations to be consolidated, thereby creating a multi-party arbitration. While the ICC Arbitration Rules address multi-party arbitration, such arbitration may in some cases be feasible only if the parties have included multi-party arbitration clauses in their contracts. Such clauses require skilful drafting, and usually need to be prepared on a case-by-case basis.

It is not unusual that the arbitration of a complex dispute is concluded sometime after performance of the Contractor’s obligations under the Contract have been completed, in which case it may not be fair and reasonable in the circumstances for any arbitral award which requires the payment of an amount by one Party to the other Party to be in the currencies of payment and in the proportions provided for under Sub-Clause 14.15 [ Currencies of Payment ]. For example, the Contractor may no longer have any need for local currency after completion of the Works; or the local currency may have declined in value in the interim or be a ‘blocked currency’ that, consequently, cannot be removed from the country concerned.

Advisory Notes to Users of FIDIC Contracts Where the Project Uses Building Information Modelling Systems

Building Information Modelling (BIM) is a process for managing information on a construction project throughout its whole life cycle. It is now being adopted widely across the world as all of those involved in the creation and operation of buildings and infrastructure assets seek ways to bring essential improvements in productivity and performance in response to ever increasing social, economic, and environmental challenges.

BIM is enabled by the continuous development of digital technologies used in all aspects of project planning, investigation, design, construction, and operation. Digital technologies include systems for: data acquisition; document management; design and process management; cost and carbon estimating; planning and scheduling; contract management; and performance management. BIM is a methodology that brings technology into an integrated and collaborative process with organised information at its heart.

BIM has varying degrees of implementation and complexity and its application should always be guided by the benefits that it brings to the project in pursuit of its intended outcomes. From its early adoption in some more developed territories, BIM is now a global phenomenon, with governments often encouraging or even mandating its use to improve quality, accuracy, and delivery times for projects as well as to provide cost savings. BIM has the potential to dramatically improve productivity and reduce construction and operational costs. Internationally, the BIM process and associated data structures are best defined in the ISO 19650 and 12006 series of standards.

BIM is not implemented through a set of contract conditions; it is a mechanism to provide a common data environment where parties have access to information relevant to their role in the design, construction, and operation of a project. Wherever possible, a combined (sometimes called federated or collaborative) model is developed for all parties to share, even if, as is often the case, various designers have used different computer aided design programs to develop their respective designs. This common data environment can be used by the parties for, amongst other things, clash detection, co-ordination of designs, communication of changes, and construction sequencing.

Co-ordination of goals and effort is essential across project participants. The BIM Protocol and Master Information Delivery Plan (often known as the BIM Execution Plan (BEP)) are both key documents in understanding the contractual position in relation to BIM on a project and set out how the parties are to work within the common data environment. All project participants need to understand and work to the Levels of Design (or Detail) (LOD) that will be spelled out in these documents to ensure that there is sufficient detail at each level to allow the works to progress efficiently and avoid unnecessary changes.

BIM is founded on a team approach and successful projects utilising BIM encourage collaboration. FIDIC contracts are designed to be fair to all parties and are considered suitable for use with projects featuring the use of BIM – providing that the parties recognise the difference in approach and use the contract appropriately.

This starts with proper planning and, unless an Employer has appropriate expertise in-house, they are well advised to retain a professional adviser who is appropriately qualified to assist them in the implementation of BIM. Legal advice is also necessary, of course, especially during the latter steps. The procurement methodology must clearly outline what the client’s (Employer’s) information requirements are for each contracted party. These expectations should focus on the purpose for which the information is required and be connected to the overall intended outcomes of the project. If properly developed, the procurement methodology will help the proposers be responsive and enable the Employer to select the consultant (or, in the case of a design-build project, the project team) best qualified to deliver the desired project outcome. This process will, in turn, help all parties develop appropriate contract terms and conditions. Ideally the selection process would use FIDIC’s Quality Based Selection (QBS) guidelines.

The improved quality of information in projects utilising BIM can result in a significant reduction in variations. It is worth thinking about how the traditional roles of Contractor and Employer fit into this structure. In general, BIM is well suited for integrated project delivery, including design-build and especially design-build-operate projects where early proactive involvement of the design engineer, Contractor, and Employer are essential. If advanced levels of BIM are anticipated for the project, the possibility of adding operation and maintenance elements of the constructed facility might be considered.

For advanced levels of BIM where fully open sharing of information is required, an appropriately qualified individual needs to be assigned the duty of managing the combined information. This role should be separate from the project manager’s role to ensure clear delineation of project responsibilities. This may require special outsourcing, if such skills are not available from the Employer or the Engineer. Managing the BIM elements of a project may also involve risks that are beyond the normal coverage of professional indemnity (PI) insurance policies. Specialist advice should be sought from PI insurers if there is any doubt on coverage for this role. The competence and responsibilities of this position need to be understood and should include experience in data back-up and integrity, continuity planning, and cyber security.

All parties involved in a project utilising BIM should take special care in checking their assigned scope and contract to ensure that they are aware of their BIM related responsibilities. The risks that FIDIC has identified in working in a BIM environment arise from these key features:

- misunderstanding of the scope of services

- use of data for an inappropriate purpose and reliance on inappropriate data

- ineffective information, document, or data management

- cyber security and responsibility for hosting information

- definition of deliverables, approval, and delivery.

To manage these and other digital technology related risks, the Employer should clearly set out their requirements with respect to the following matters, and see that the supplier proposals adequately address them:

- The specific technologies, including “versions” or “releases” that the supplier uses which must meet the overall project requirement for inter-operability and information management across all suppliers, including any specific technologies that the Employer may wish to adopt.

- The rights for all information produced by a supplier for the purposes of a project to be accessed and used by other project participants in the context of the project.

- Correct allocation of risk for correctness of external or open data upon which suppliers might rely in developing their own information.

- Service Level Agreements (SLAs) for all software that might be provided by a supplier upon which the Employer or other project participants might be dependent to continue to progress the works in a timely manner.

- Definition of liability in the event of cyber attack related to digital delivery systems.

- Requirements to establish and maintain a complete archive of all information transactions relating to model-based design to enable a complete audit trail and review of all changes to be established if required.

The suppliers’ proposals must adequately set out their detailed response to these requirements. At the completion of the project the digital representation of the asset should be brought up to as-built status so that it can be handed over with the physical asset. This involves not only the graphical elements but also the embedded data. Experience shows that this is a significant effort, so responsibilities for completing this task should be clear and appropriate allowances provided.

The process for the delivery of contractual notices should be checked to determine if this will be through the common data environment or by more traditional means or both.

If Subcontractors are to be utilised, they should be bound by the BIM Protocol and Master Information Delivery Plan.

For construction or building projects involving BIM, in addition to considering the general principles as introduced above, the following (non-exhaustive) list of Sub-Clauses of the General Conditions of FIDIC Conditions of Contract for EPC/Turnkey Projects, 2017 Second Edition, reprinted 2022 with amendments, should be thoroughly reviewed when drafting the Particular Conditions:

## Sub-Clause No.	Sub-Clause Title

1.1	Definitions

1.3	Notices and Other Communications

1.5	Priority of Documents

  - Employer’s Use of Contractor’s Documents

  - Contractor’s Use of Employer’s Documents

1.14	Limitation of Liability

2.3	Employer’s Personnel and Other Contractors

2.5	Site Data and Items of Reference

  - The Employer’s Representative

  - Other Employer’s Personnel

  - Contractor’s General Obligations

  - Co-operation

  - Setting Out

4.9	Quality Management and Compliance Verification Systems

4.20	Progress Reports

  - General Design Obligations

  - Contractor’s Documents

  - As-Built Records

  - Operation and Maintenance Manuals

  - Design Error

6.8	Contractor’s Superintendence

6.10	Contractor’s Records

8.3	Programme

9.1	Contractor’s Obligations

  - Variation Procedure

  - Intellectual and Industrial Property Rights

  - Indemnities by Contractor

  - Indemnities by Employer

  - Shared Indemnities

19.2.6	Other insurances required by Laws and by local practice

FIDIC Contracts do not require particular forms of BIM Protocol and BIM Execution or Master Information Delivery Plan to be used and so the Parties are free to choose a standard form set of documents which best suit the project or they can prepare their own. A suitable example for the delivery stage of assets is the Information Protocol published by the UK BIM Framework, currently at Edition 3, February 2021.

FIDIC maintains a network of international experts in the application of BIM, keeping the development of ISO 19650 under permanent review. We will continue to monitor ongoing developments to support the global drive for productivity and infrastructure performance improvement enabled by digital technology.